## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Narasingpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000174/2023-2024 | 1048/ALD | 20/07/2023 | 16/01/2024 | DILIP MAHATO | 567.48 | 252.96 | 44.58 | 80
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Narsingpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000898/2023-2024 | 2474/NMD-II | 11/08/2023 | 02/02/2025 | SUMON ELECTRICAL | 21.78 | 0 | 0 | 90
3 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of NARASINGPUR PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000322/2023-2024 | 2417/ALD | 09/11/2023 | 08/01/2024 | DILIP MAHATO | 36.67 | 0 | 0 | 80
4 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Laying of Rising main, delivery main, bypass arrangement, laying of HDPE pipeline for left out household connecting to Narasingpur PWSS (both H/W and 2nd site) (SM/15758) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000492/2023-2024 | 748/ALD | 12/03/2024 | 10/07/2024 | DILIP MAHATO | 91.41 | 0 | 0 | 85
5 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1480/ALD | 16/08/2023 |  | Resource Division | 21.43 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 2774 | 18/12/2023 |  | Resource Division | 15.16 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 2774/ALD | 18/12/2023 |  | Resource Division | 15.16 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | NEW SERVICE CONNECTION CHARGES FOR NARASINGPUR PWSS TW NO-II |  |  | BILL/03012/2023-2024 | BP-2023-24-689 | 14/03/2024 |  | WBSEDCL | 7.52 | 0 | 0 | null
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | NEW SERVICE CONNECTION CHARGES FOR NARASINGPUR PWSS TW NO-II |  |  | BILL/03012/2023-2024 | BP-2023-24-689 | 14/03/2024 |  | WBSEDCL | 7.52 | 0 | 0 | null
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | NEW SERVICE CONNECTION CHARGE FOR NARSINGHPUR PH NO-I |  |  | BILL/03017/2023-2024 | BP-2023-24-694 | 14/03/2024 |  | WBSEDCL | 7.52 | 0 | 0 | null
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 | New | NEW SERVICE CONNECTION CHARGE FOR NARSINGHPUR PH NO-I |  |  | BILL/03017/2023-2024 | BP-2023-24-694 | 14/03/2024 |  | WBSEDCL | 7.52 | 0 | 0 | null
Total | [13 empty] | 799.18 | 252.96 | 31.65