## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Umacharanpur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000895/2023-2024 | 2476/NMD-II | 11/08/2023 | 10/09/2023 | CINZANO | 21.9 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, Soil investigation at OHR site, constructions of 500 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uma Charanpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000251/2023-2024 | 1873/ALD | 07/09/2023 | 03/06/2024 | TAPASH KUMAR BHOWMICK | 608.41 | 242.55 | 39.87 | 37
3 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2775/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 18.81 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Laying of rising main DI (K7), interconnection work with HDPE pipe , Construction of sluice valve chamber for Umacharanpur PWSS under Birpara Sub- Division ,Alipurduar Division PHE Dte. under North Bengal Circle-I PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000210/2024-2025 | 2061/ALD | 12/07/2024 | 08/05/2025 | TAPASH KUMAR BHOWMICK | 101.24 | 93.17 | 92.03 | 90
5 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Umachndrapur Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000465/2023-2024 | 608/ALD | 29/02/2024 | 30/03/2024 | MANSAROVAR CASTING | 11.95 | 11.95 | 100 | 85
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | New Service Connection Charges for UMACHARANPUR PWSS P/H NO-I,10 mile |  |  | BILL/00050/2024-2025 | BP-10/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 12.04 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | New Service Connection for Umacharanpur PH NO-II PWSS |  |  | BILL/00987/2024-2025 | BP-276/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 10.48 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supply of CIDF Specials and Jeffy Coupling for Umacharanpur (SM/16114) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000413/2024-2025 | 4591/ALD | 03/01/2025 | 02/02/2025 | TAPASH KUMAR BHOWMICK | 19.81 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000137/2025-2026 | 1346/NMD-II | 19/06/2025 | 19/07/2025 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Falakata | Alipurduar Division | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 | New | Laying of HDPE pipeline (parallel and balance line ) at Umacharanpur PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000194/2025-2026 | 2077/ALD | 19/09/2025 | 03/12/2025 | TAPASH KUMAR BHOWMICK | 80.25 | 0 | 0 | 0
Total | [13 empty] | 1751.94 | 347.67 | 19.84