## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | SM/16115 | Augmentation | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000453/2022-2023 | 2970/ALD | 31/01/2023 | 01/05/2023 | BILTU DAS | 165.16 | 0 | 0 | 61
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | SM/16115 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF SIDHABARI PIPED WATER SUPPLY SCHEME | SM/16115 | Augmentation | Replacement of damaged pipeline with HDPE pipes for Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000076/2025-2026 | 974/ALD | 12/06/2025 | 11/08/2025 | SANKAR ROY | 8.53 | 0 | 0 | 0
Total | [13 empty] | 248.04 | 0 | 0