## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Construction of 200cum OHR as per departmental design and drawing, providing FHTC for 28 and 29 mile Busty PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000002/2023-2024 | 05/ALD | 04/04/2023 | 01/10/2023 | A B TECHNO ENTERPRISE | 91.25 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvention of 28 AND 29 MILE BASTI Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000939/2023-2024 | 2543/NMD-II | 16/08/2023 | 15/09/2023 | DILIP MAHATO | 22.96 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Providing balance FHTC from existing distribution system as per specification for 28 and 29 MILE BASTY PWSS under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000294/2023-2024 | 2103/ALD | 29/09/2023 | 28/11/2023 | EVEREST INFRATECH INC | 47.79 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Laying distribution system with new UPVC pipeline, Construction of 2 Nos Pump House ,Pipe Support Structure, Land Development, Boundary Wall, Path way, Providing FHTC, and other allied works for Gram Busty Area Under 28 & 29 Mile Basty (Zone-IV) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000357/2023-2024 | 2608/ALD | 04/12/2023 | 30/08/2024 | HITANGSHU CHOUDHURY | 70.82 | 14.23 | 20.1 | 45
5 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Hiring of additional Diesel Vehicle Maxi Cab (At least 7 seater) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kumargram Block | ORD/000391/2024-2025 | 3883/ALD | 22/11/2024 | 22/11/2025 | SOUVIK ROY PALADHI | 4.8 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Arrangement for online application in Paribesh Portal for getting Forest permission at 7nos BOPs under Alipurduar Division P.H.E Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000458/2023-2024 | 496/ALD | 16/02/2024 | 17/03/2024 | HILL GROUND CONSULTANCY | 1.83 | 0 | 0 | 100
7 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 113 nos. villages (Block - Falakata, Kalchini, Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.(SM/16506) | Birpara A.E | JUNIOR ENGINEER | ORD/000495/2023-2024 | 751/ALD | 12/03/2024 | 20/07/2024 | LIMRA SOCIAL WELFARE SOCIETY | 27.08 | 26.66 | 98.46 | 100
8 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 98/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 10.79 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 4251/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 31.69 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | payment against proposal No : FP/WB/Others/443310/2023for boundary demarcation and construction of boundary pillar for diversion of forest land of area 0.0464 ha for 28 and 29 mile basty PWSS ( Z-IV) Garam basty under JJM at garam basty forest Village under BTR ( West) Division under WDPO Range . |  |  | BILL/00182/2024-2025 | 144/24-25/PFMS | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg |  |  | BILL/00339/2024-2025 |  | 18/09/2024 | 18/09/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.21 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | New Service Connection Charges for REJUVINATION OF 28 & 29 Mile Basti PH NO-2 |  |  | BILL/00523/2024-2025 | BP-120/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 8.22 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | payment for NPV Demand Note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ii) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering Directorate for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERSI442029/2023). |  |  | BILL/00188/2024-2025 | 147/24-25/PFMS | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 15.59 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Cost of raising and maintenance of the compensatory afforestation ( 100 trees plantation and mtc for 10 years ) against proposed diversion of forest land for 28 and 29 mile basty PWSS (Z-IV) Garam Basty under JJM against Proposal No : FP/WB/Others/443310/2023 |  |  | BILL/00184/2024-2025 | 146/24-25/PFMS | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Payment for NPV for diversion of forest land of 0.0464 ha area against proposal No : FP/WB/Others/443310/2023 for water supply scheme 28 and 29 Mile Basty PWSS ( Z-VI) Garam Basty under JJM Garam Basty Forest Village under BTR(West ) Division under WDPO Range under DPO_9 Compartment |  |  | BILL/00183/2024-2025 | 145/24-25/PFMS | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 5.18 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg |  |  | BILL/00506/2024-2025 | 329/24-25/PFMS | 19/12/2024 | 19/12/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.31 | 0 | 0 | 0
17 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Cost of raising and maintenance of the Compensatory Afforestation demand note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ü) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for Directorate non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERS/442029/2023 |  |  | BILL/00189/2024-2025 | 148/24-25/PFMS | 08/08/2024 | 08/08/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | 0
18 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | New Service Connection Charges For Rejuvination of 28 & 29 Mile Basti PWSS PH NO-1 |  |  | BILL/00524/2024-2025 | BP-119/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
19 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Construction of 2nos Tw boring by ODEX-165 method of drilling including distribution system with new UPVC pipeline, 2 nos Pump house, Boundary wall, pathway, providing FHTC and other allied works for 28 and 29 mile busty PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000558/2022-2023 | 3502/ALD | 23/03/2023 | 12/11/2024 | HITANGSHU CHOUDHURY | 76.18 | 29.23 | 38.37 | 80
20 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000461/2023-2024 | 160/ALD | 11/01/2024 | 11/01/2025 | APSARI BHOWMICK | 4.8 | 0 | 0 | 0
21 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001209/2024-2025 | 823/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
22 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
23 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | RWS Kalchini Block | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
24 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
25 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | HQ-A.E | RWS Kumargram Block | ORD/000458/2024-2025 | 4553/ALD | 30/12/2024 | 30/03/2025 | DIPAK DAS | 1.2 | 1.07 | 88.95 | 0
26 | ALIPURDUAR | Kalchini | Alipurduar Division | 28&29 MILE BASTI PIPE WATER SUPPLY SCHEME | SM/16506 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | HQ-A.E | RWS Kumargram Block | ORD/000457/2024-2025 | 4552/ALD | 30/12/2024 | 30/03/2025 | APSARI BHOWMICK | 1.2 | 0 | 0 | 0
Total | [13 empty] | 1278.59 | 71.19 | 5.57