## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum, laying distribution system and providing FHTC at Buxa PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000563/2022-2023 | 3506/ALD | 23/03/2023 | 19/09/2023 | ASHOK SAPKOTA | 30.8 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1260/ALD | 10/08/2023 |  | Resource Division | 2.17 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BUXA PWSS,TW No.-I and II under NMDII, PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000947/2023-2024 | 2532/NMD-II | 16/08/2023 | 15/09/2023 | MUSTAFI CONCERN | 25.54 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 102/ALD | 10/01/2024 |  | Resource Division | 16.34 | 0 | 0 | 0
Total | [13 empty] | 74.85 | 0 | 0