## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BUXA PWSS,TW No.-I and II under NMDII, PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000947/2023-2024 | 2532/NMD-II | 16/08/2023 | 15/09/2023 | MUSTAFI CONCERN | 25.54 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1260/ALD | 10/08/2023 | 10/08/2023 | Resource Division | 2.17 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 102/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 16.34 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum, laying distribution system and providing FHTC at Buxa PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000563/2022-2023 | 3506/ALD | 23/03/2023 | 19/09/2023 | ASHOK SAPKOTA | 30.8 | 0 | 0 | 100
5 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | LAYING OF 25 MM DIA PP-R PIPES FROM TASHIGAON RIVER TO LEPCHAKHA AND LEPCHAKHA TO DUMBA AND OTHER ALLIED WORKS UNDER JJM PROGRAMME UNDER ALIPURDUAR DIVISION, PHE DTE. | HQ-A.E | Alipurduar Sub Division | ORD/000439/2024-2025 | 5042/ALD | 17/02/2025 | 17/06/2025 | S.D. PROJECT | 8.33 | 0 | 0 | 100
6 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Route surveying and revalidation of Household data with digitization of LDS for Lepchakha and Santalebari PWSS under Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000096/2025-2026 | 1180/ALD | 26/06/2025 | 26/07/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Solarization of grid connected pumping installation at Different PWSS at Kalchini Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000133/2025-2026 | 1334/NMD-II | 18/06/2025 | 16/09/2025 | M. M. ENTERPRISE | 16.38 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA PIPE WATER SUPPLY SCHEME | SM/16507 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 829.29 | 0 | 0