## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Supply of CIDF & CISS Pipes and specials for Uttar Majidkhana WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000227/2023-2024 | 1606/ALD | 25/08/2023 | 24/09/2023 | TAPASH KUMAR BHOWMICK | 7.89 | 7.88 | 99.82 | 100
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 223/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 16.73 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 2396/ALD | 08/11/2023 | 08/11/2023 | Resource Division | 11.63 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | New Service Connection at Uttar Masjidkhana P/H No.I |  |  | BILL/01688/2023-2024 | BP-2023-24-337 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.58 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | New service connection charge for Uttar majidkhana p/h-II |  |  | BILL/02151/2023-2024 | BP-2023-24-472 | 12/12/2023 | 12/12/2023 | WBSEDCL | 6.2 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Continuation order of "Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte." | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000548/2023-2024 | 314/ALD | 25/01/2024 | 23/07/2024 | TAPASH KUMAR BHOWMICK | 4.29 | 4.29 | 100 | 100
7 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Continuation order of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (in soft copy) to PHE Dte. PART-B" | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000547/2023-2024 | 313/ALD | 25/01/2024 | 23/07/2024 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100 | 100
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Material Requisition To Resource Division |  |  | RTOR000055/2024-2025 | 4275/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 26.21 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | CONS of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site , LDS with UPVC P/LINE , CONS of 200 Cum OHR , incl the Soil investigation works, providing FHTC and others allied works for Uttar Majidkhana PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000518/2022-2023 | 3416/ALD | 17/03/2023 | 27/09/2025 | TAPASH KUMAR BHOWMICK | 490.21 | 376.32 | 76.77 | 95
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Providing balance FHTC for UTTAR MAJIDKHANA PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000213/2023-2024 | 1567/ALD | 23/08/2023 | 04/04/2024 | TAPASH KUMAR BHOWMICK | 9.36 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
13 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000132/2025-2026 | 1333/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
15 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MAJIDKHANA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000690/2023-2024 | 2167/NMD-II | 27/07/2023 | 02/04/2025 | MALAY KUMAR SAHA | 21.13 | 14.79 | 70.03 | 90
16 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 1560/ALD | 31/07/2025 | 31/07/2025 | Resource Division | 5.52 | 0 | 0 | 0
17 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Material Requisition To Resource Division |  |  | RTOR000010/2025-2026 | 2034/ALD | 15/09/2025 | 15/09/2025 | Resource Division | 3.4 | 0 | 0 | 0
18 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 12/06/2026 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 20
Total | [13 empty] | 1523.77 | 407.96 | 26.77