## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1479/ALD | 16/08/2023 | 16/08/2023 | Resource Division | 21.37 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 2723/ALD | 13/12/2023 | 13/12/2023 | Resource Division | 84.45 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000172/2023-2024 | 1046/ALD | 20/07/2023 | 11/05/2025 | DILIP MAHATO | 539.38 | 0 | 0 | 61
4 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Uttar deogaon PWSS under Birpara Sub-Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000342/2024-2025 | 3230/ALD | 10/09/2024 | 09/11/2024 | DILIP MAHATO (OPC) PRIVATE LIMITED | 43.7 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | "Supply of DIDF Special and CI Jeffy Coupling for Uttar Deogaon TG Water Supply Scheme(SM/16817) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000528/2023-2024 | 847/ALD | 14/03/2024 | 12/06/2024 | SOUVIK ROY PALADHI | 16.48 | 0 | 0 | 59
6 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 3955/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 9.86 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | New Service connection charges for UTTAR DEOGAON PWSS TW No-I under Alipurduar District |  |  | BILL/00046/2024-2025 | BP-09/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | New Service Connection Cgarges for UTTAR DEOGAON PWSS P/H NO-II |  |  | BILL/00051/2024-2025 | BP-11/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 8.77 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of UTTAR DEOGAON water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000952/2023-2024 | 2558/NMD-II | 18/08/2023 | 17/09/2023 | SUNLIT | 22.2 | 0 | 0 | 50
10 | ALIPURDUAR | Falakata | Alipurduar Division | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Continuation work order for the work of "Construction of tube wells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/4/2024-EE(ALI_D) SEC-DPHE (Computer No-973240)) | Birpara A.E | Birpara Sub Division | ORD/000198/2024-2025 | 1912/ALD | 26/06/2024 | 25/08/2024 | DILIP MAHATO | 21.25 | 0 | 0 | 100
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001207/2024-2025 | 821/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000137/2025-2026 | 1346/NMD-II | 19/06/2025 | 19/07/2025 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
13 | ALIPURDUAR | Falakata | Northern Mechanical Division II | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1552.2 | 0 | 0