## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1476/ALD | 16/08/2023 | 16/08/2023 | Resource Division | 21.37 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 2773/ALD | 18/12/2023 | 18/12/2023 | Resource Division | 7.84 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2700/ALD | 12/12/2023 | 12/12/2023 | Resource Division | 84.45 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 300 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Lachhimandabri PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000183/2023-2024 | 1172/ALD | 03/08/2023 | 19/01/2026 | M/S T M CONSTRUCTION | 433.46 | 0 | 0 | 35
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of LACHHIAMANDABRI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000964/2023-2024 | 2571/NMD-II | 22/08/2023 | 21/09/2023 | DEY ENTERPRISE (MALDA) | 22.2 | 0 | 0 | 100
6 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Lachman Dabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000478/2023-2024 | 696/ALD | 07/03/2024 | 01/01/2025 | HARIDAS GHOSH | 18.07 | 0 | 0 | 65
7 | ALIPURDUAR | Falakata | Alipurduar Division | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 3952/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 7.84 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | New Service Connection Charges for Lacchi Mendabari, Lacchi Mendabari PWSS, TW No-I Under NMD-II |  |  | BILL/01896/2024-2025 | BP-431/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000137/2025-2026 | 1346/NMD-II | 19/06/2025 | 19/07/2025 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000134/2025-2026 | 1344/NMD-II | 19/06/2025 | 17/09/2025 | M/S SAJAHAN CHOWDHURY | 42.58 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1391.4 | 0 | 0