## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Boring of TW, Construction of PH, B/Wall and LDS for Augmentation of Gargenda PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000520/2022-2023 | 3473/ALD | 22/03/2023 | 14/07/2024 | SHYAMAL ROY | 36.57 | 18.74 | 51.25 | 60
2 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of GARGENDA TG Water Supply Scheme TW No.-I,II ,III and IV of Zone-I under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000957/2023-2024 | 2561/NMD-II | 18/08/2023 | 02/01/2027 | SARKAR ELECTRIC | 54.5 | 43.19 | 79.25 | 50
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Construction of boundary wall, Pump house, TW, Rising main for Gargenda PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000384/2023-2024 | 196/ALD | 16/01/2024 | 15/05/2024 | DILIP MAHATO | 27.12 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Construction of boundary wall, Pump house, TW, Rising main for Gargenda (Near Dukhiya Line) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | RWS Madarihat - Birpara Block | ORD/000386/2023-2024 | 197/ALD | 16/01/2024 | 07/09/2025 | MANI PRADHAN | 27.78 | 0 | 0 | 70
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER | ORD/000533/2023-2024 | 891/ALD | 15/03/2024 | 11/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 14.79 | 42.9 | 10
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Gargenda-1 no site (SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,JUNIOR ENGINEER | ORD/000532/2023-2024 | 890/ALD | 15/03/2024 | 11/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 17.23 | 15.62 | 90.65 | 5
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Supply of MSREW Pipe for modified DTH - ODEX of drilling at Site no. 01 of GARGENDA TE of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000232/2024-2025 | 2292/ALD | 06/08/2024 | 05/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 8.77 | 7.43 | 84.79 | 100
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Supply of MSREW Pipe for modified DTH - ODEX of drilling at 2 different locations under Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000233/2024-2025 | 2293/ALD | 06/08/2024 | 05/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 14.15 | 8.09 | 57.19 | 100
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR 15 NO LINE GARGENDA TG PWSS ZONE-I, TW NO-I |  |  | BILL/00298/2024-2025 | BP-82/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 3.74 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR GARGENDA TG JR. SCHOOL PWSS ZONE-I, TW NO-II |  |  | BILL/00299/2024-2025 | BP-81/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Renovation of Pump house and boundary wall at 2nd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000094/2025-2026 | 1178/ALD | 26/06/2025 | 24/09/2025 | AVNI CONSTRUCTION | 1.04 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Renovation of Pump house and boundary wall at 3rd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000093/2025-2026 | 1177/ALD | 26/06/2025 | 24/09/2025 | AVNI CONSTRUCTION | 1.04 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | Renovation of Pump house and boundary wall at H/W site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000095/2025-2026 | 1179/ALD | 26/06/2025 | 24/09/2025 | AVNI CONSTRUCTION | 1.3 | 0 | 0 | 0
14 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF GARGENDA TG PIPED WATER SUPPLY SCHEME. | SM/16824 | Augmentation | New Service Connection Charges for Gargenda TG PH-I Zone-II under NMD-II in the dist. of Alipurduar. |  |  | BILL/03114/2024-2025 |  | 19/03/2025 | 19/03/2025 | WBSEDCL | 16.58 | 0 | 0 | 0
Total | [13 empty] | 248.83 | 107.87 | 43.35