## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Soil investigation at OHR site, constructions of 300 Cum OHR at HW , distribution line and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000022/2023-2024 | 258/ALD | 08/05/2023 | 04/11/2023 | DILIP MAHATO | 217.32 | 0 | 0 | 80
2 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Cons. of tube wells at 2nd site by Reverse rotary method of drilling, cons. of pump house and boundary wall at 2nd site, rising main, distribution line(C) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000023/2023-2024 | 257/ALD | 08/05/2023 | 05/09/2023 | PRAMESH LAMA | 176.9 | 0 | 0 | 10
3 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Cons. Of tube wells at H/W site by Reverse rotary method of drilling , cons. of pump house and boundary wall at H/W , rising main, distribution line(B) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000053/2023-2024 | 422/ALD | 24/05/2023 | 21/09/2023 | MADHAB SAHA | 201.45 | 0 | 0 | 100
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for KHAGENHAT water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000991/2023-2024 | 2621/NMD-II | 25/08/2023 | 24/09/2023 | ASHOKE ADHIKARY | 21.88 | 7.18 | 32.8 | 40
5 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Providing FHTC from existing distribution system as per specification for Khagenhat PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000305/2023-2024 | 2170/ALD | 06/10/2023 | 05/12/2023 | TAPASH DAS | 5.58 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 101/ALD | 10/01/2024 |  | Resource Division | 12.67 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Alipurduar Division | Khagenhat Piped Water Supply Scheme | SM/18151 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 |  | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme | SM/18151 | New | New service connection charges for Khagenhat PWSS PH NO-2 |  |  | BILL/01179/2024-2025 | BP-330/24-25 | 03/10/2024 |  | WBSEDCL | 1.07 | 0 | 0 | null
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme | SM/18151 | New | New service connection charges for Khagenhat PWSS PH NO-2 |  |  | BILL/01179/2024-2025 | BP-330/24-25 | 03/10/2024 |  | WBSEDCL | 1.07 | 0 | 0 | null
11 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme | SM/18151 | New | New Service Connection charges for Khagenhat PWSS PH NO-1 under NMD-II |  |  | BILL/01180/2024-2025 | BP-327/24-25 | 03/10/2024 |  | WBSEDCL | 7.59 | 0 | 0 | null
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Khagenhat Piped Water Supply Scheme | SM/18151 | New | New Service Connection charges for Khagenhat PWSS PH NO-1 under NMD-II |  |  | BILL/01180/2024-2025 | BP-327/24-25 | 03/10/2024 |  | WBSEDCL | 7.59 | 0 | 0 | null
Total | [13 empty] | 781.14 | 7.18 | 0.92