## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | Dhantali Piped Water Supply Scheme | SM/18153 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE/DI pipeline, providing FHTC and others allied works for Dhantali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000016/2023-2024 | 234/ALD | 04/05/2023 | 25/02/2025 | SOUVIK ROY PALADHI | 190.55 | 131.42 | 68.97 | 70
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme | SM/18153 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DHANTALI water supply scheme, TW no I AND II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000994/2023-2024 | 2623/NMD-II | 25/08/2023 | 02/07/2025 | RUBY ENTERPRISE | 22 | 0 | 0 | 80
3 | ALIPURDUAR | Kumargram | Alipurduar Division | Dhantali Piped Water Supply Scheme | SM/18153 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 123/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 1.27 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Alipurduar Division | Dhantali Piped Water Supply Scheme | SM/18153 | New | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 4271/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 19.92 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme | SM/18153 | New | New Service Connection Charges for Dhantali PWSS PH NO-1 |  |  | BILL/01411/2024-2025 | BP-404/24-25 | 30/10/2024 | 30/10/2024 | WBSEDCL | 9.12 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Dhantali Piped Water Supply Scheme | SM/18153 | New | New Service Connection Charges for Dhantali PH NO-2 |  |  | BILL/01409/2024-2025 | BP-406/24-25 | 30/10/2024 | 30/10/2024 | WBSEDCL | 5.21 | 0 | 0 | 0
Total | [13 empty] | 248.07 | 131.42 | 52.98