## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site , Laying of distribution system with HDPE pipeline including rising main & delivery connection , Constructions of 100 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Uttar Dhalkar PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000021/2023-2024 | 237/ALD | 04/05/2023 | 31/10/2023 | TAPASH KUMAR BHOWMICK | 226.42 | 0 | 0 | 45
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for UTTAR DHALKAR Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/001067/2023-2024 | 2578/NMD-II | 22/08/2023 | 21/09/2023 | M/S B ENTERPRISE | 21.17 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | Construction of balance portion of boundary wall, pathway, surface drain and chatal, land development, laying of rising main line & delivery line connection along with the other allied works at Putimari PWSS adj. To Uttar Dhalkar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000339/2023-2024 | 2540/ALD | 28/11/2023 | 26/02/2024 | TAPASH KUMAR BHOWMICK | 25.47 | 0 | 0 | 100
4 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 3984/ALD | 27/11/2024 |  | Resource Division | 3.66 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | New Service Connection Charges for Uttar Dhalkar PWSS PH NO-2 under NMD-II |  |  | BILL/01894/2024-2025 | BP-428/24-25 | 16/12/2024 |  | WBSEDCL | 5.25 | 0 | 0 | null
6 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | New Service Connection Charges for Uttar Dhalkar PWSS PH NO-2 under NMD-II |  |  | BILL/01894/2024-2025 | BP-428/24-25 | 16/12/2024 |  | WBSEDCL | 5.25 | 0 | 0 | null
7 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | New Service Connection for Uttar Dhalkar PWSS PH NO-I in the dist of Alipurduar |  |  | BILL/01182/2024-2025 | BP-328/24-25 | 03/10/2024 |  | WBSEDCL | 4.9 | 0 | 0 | null
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Uttar Dhalkar Piped Water Supply Scheme | SM/18154 | New | New Service Connection for Uttar Dhalkar PWSS PH NO-I in the dist of Alipurduar |  |  | BILL/01182/2024-2025 | BP-328/24-25 | 03/10/2024 |  | WBSEDCL | 4.9 | 0 | 0 | null
Total | [13 empty] | 297.02 | 0 | 0