## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | NEW SERVICE CONNECTION FOR BHUTRI FOREST PWSS P/H NO I,KALCHINI APPLICATION NO 4003208197 |  |  | BILL/01827/2023-2024 | BP-2023-24-320 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.1 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 16/08/2023 | FAUDA SINGH CHHETRI | 34.7 | 4.07 | 11.74 | 100
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for BHUTRI FOREST Water Supply Scheme TW No- I under NMDII, PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001102/2023-2024 | 2836/NMD-II | 12/10/2023 | 11/11/2023 | PRAGATI CONSTRUCTION COMPANY | 10.18 | 10.07 | 98.93 | 100
4 | ALIPURDUAR | Kalchini | Alipurduar Division | Bhutri Forest Piped Water Supply Scheme | SM/18156 | New | Gap joint and restoration of HDPE line and repairing of FHTC and allied works at Radharani and Chuapara village under Radharani under Bhutri Forest PWSS within Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000065/2025-2026 | 817/ALD | 03/06/2025 | 17/08/2025 | PRAPTI DUTTA | 23.32 | 0 | 0 | 50
Total | [13 empty] | 72.29 | 14.14 | 19.56