## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Boring of Tube Well by reverse rotary method, Construction of Pump House, Boundary Wall, Laying Of Distribution System and providing FHTC for Parpatlakhawa PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000017/2023-2024 | 235/ALD | 04/05/2023 | 30/12/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 113.69 | 0 | 0 | 16
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARPATLA KHAWA water supply scheme, TW no I and II of under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000993/2023-2024 | 2625/NMD-II | 25/08/2023 | 24/09/2023 | HARA PROSAD DAS | 21.25 | 0 | 0 | 40
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | NEW SERVICE CONNECTION CHARGES FOR PAR PATLAKHAWA PWSS P/H NO-I |  |  | BILL/03128/2023-2024 | BP-235/24-25 | 29/07/2024 |  | WBSEDCL | 6.17 | 0 | 0 | null
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | NEW SERVICE CONNECTION CHARGES FOR PAR PATLAKHAWA PWSS P/H NO-I |  |  | BILL/03128/2023-2024 | BP-235/24-25 | 29/07/2024 |  | WBSEDCL | 6.17 | 0 | 0 | null
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | New Service Connection Charges for Parpatlakhowa PWSS PH NO-II under NMD-II |  |  | BILL/01893/2024-2025 | BP-427/24-25 | 16/12/2024 |  | WBSEDCL | 13.63 | 0 | 0 | null
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Parpatla Khawa Piped Water Supply Scheme | SM/18158 | New | New Service Connection Charges for Parpatlakhowa PWSS PH NO-II under NMD-II |  |  | BILL/01893/2024-2025 | BP-427/24-25 | 16/12/2024 |  | WBSEDCL | 13.63 | 0 | 0 | null
Total | [13 empty] | 174.55 | 0 | 0