## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Soil investigation work at 3 different places of Dalimpur within Alipurduar District under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000160/2023-2024 | 965/ALD | 12/07/2023 | 11/08/2023 | CITY ENGINEERING & TESTING LABORATORY | 3.67 | 3.67 | 100 | 100
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Dalimpur Zone-I PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000167/2023-2024 | 973/ALD | 12/07/2023 | 06/07/2024 | NARAYAN CHANDRA SAHA | 48.31 | 48.23 | 99.84 | 65
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dalimpur PWSS under Alipurduar Division, PHE Dte. Part-3 | Birpara A.E | RWS Falakata Block | ORD/000162/2023-2024 | 966/ALD | 12/07/2023 | 08/01/2024 | TAPASH DAS | 34.77 | 4.52 | 13 | 15
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for DALIMPUR PWSS under Alipurduar Division, PHE DTE. PART-2 | Birpara A.E | RWS Falakata Block | ORD/000165/2023-2024 | 970/ALD | 12/07/2023 | 03/11/2024 | MITHUN DAS | 67.93 | 63.74 | 93.84 | 65
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of Rising Main, road and culvert crossing and distribution pipeline in DALIMPUR PWSS (Zone-III) under Alipurduar Division, PHE Dte | Birpara A.E | RWS Falakata Block | ORD/000319/2023-2024 | 2411/ALD | 09/11/2023 | 06/07/2024 | NARENDRA BHADANI. | 17.66 | 16.47 | 93.27 | 10
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Road crossing, hume pipe culvert crossing, and bridge crossing by G.I. pipe at Dalimpur Zone-III PWSS including Laying of UPVC Pipeline for left out household connection of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/18254) | Birpara A.E | RWS Falakata Block | ORD/000512/2023-2024 | 830/ALD | 14/03/2024 | 13/05/2024 | MITHUN DAS | 9.04 | 8.79 | 97.22 | 10
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Laying of rising Main,Road and Calvert crossing and Balance distribution pipeline in Dalimpur(Zone-I) under Alipurduar Division,PHE Dte of North Bengal Circle-I, PHE Dte. under JJM Programme. | Birpara A.E | RWS Falakata Block | ORD/000466/2023-2024 | 670/ALD | 06/03/2024 | 31/12/2024 | UJJWAL ROY | 132.1 | 121.02 | 91.62 | 80
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of 150cum. OHR for DALIMPUR ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000169/2023-2024 | 972/ALD | 12/07/2023 | 06/07/2024 | UJJWAL ROY | 50.43 | 40.91 | 81.12 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3947/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 25.05 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New service connection Charges for Dalimpur PWSS Zone-I PH NO-I under NMD-II |  |  | BILL/01887/2024-2025 | BP-426/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.05 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New Service Connection Charges For Aug of Dalimpur Zone-III PH NO-I under NMD-II |  |  | BILL/01892/2024-2025 | BP-425/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 16.01 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New Service Connection Charges for Aug of Dalimpur Zone-I PH NO-II under NMD-II |  |  | BILL/01890/2024-2025 | BP-424/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.85 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of 400cum OHR for DALIMPUR ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000161/2023-2024 | 968/ALD | 12/07/2023 | 28/12/2025 | NARAYAN CHANDRA SAHA | 77.28 | 28.26 | 36.57 | 60
14 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for AUGUMENTATION OF DALIMPUR water supply scheme, TW no I and II of Zone - I and TW no I and II of Zone - II and TW no I and II of Zone - III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000875/2023-2024 | 2453/NMD-II | 11/08/2023 | 01/02/2025 | ALPHA ENTERPRISE | 65.55 | 7.99 | 12.19 | 35
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Providing FHTC from existing distribution system as per specification for DALIMPUR PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000287/2023-2024 | 1995/ALD | 15/09/2023 | 03/11/2025 | SREE MAA CONSTRUCTION | 28.8 | 9.96 | 34.59 | 45
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Balance work of rising main, delivery main, bypass arrangement, land development, pipeline for left out household connection and other allied works at Augmentation of Dalimpur(Zone-3)(H/W site) of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/18254) | Birpara A.E | RWS Falakata Block | ORD/000502/2023-2024 | 820/ALD | 14/03/2024 | 07/07/2025 | UJJWAL ROY | 41.61 | 0 | 0 | 40
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-A) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000401/2024-2025 | 4537/ALD | 26/12/2024 | 25/04/2025 | HITANGSHU CHOUDHURY | 55.82 | 0 | 0 | 80
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-B) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000452/2024-2025 | 5169/ALD | 25/02/2025 | 23/10/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 55.35 | 0 | 0 | 10
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Dalimpur Zone-III PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000164/2023-2024 | 967/ALD | 12/07/2023 | 31/07/2025 | NARENDRA BHADANI. | 45.9 | 44.65 | 97.27 | 100
20 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | New Service Connection charges for Aug of Dalimpur Zone-III PH NO-II under NMD-II |  |  | BILL/01889/2024-2025 | BP-423/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 14.15 | 0 | 0 | 0
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DALIMPUR PWSS | SM/18254 | Augmentation | Construction of tubewells (2 nos.) by Reverse rotary method of drilling, constructions of 150 Cum OHR at HW, Cons. of pump house and Boundary wall at HW site and 2nd site, Laying of rising main, part of distribution line and providing FHTC for Dalimpur zone-II under Birpara Sub-division, Alipurduar Division of North Bengal Circle-I, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000454/2023-2024 | 366/ALD | 31/01/2024 | 01/04/2026 | HARIDAS GHOSH | 199.7 | 117.92 | 59.05 | 90
Total | [13 empty] | 1000.03 | 516.15 | 51.61