## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation order for the work of Proposed logistic support to the CPMF/WBSAP for providing sanitary arrangement (i.e. Construction of Temporary Latrine ,providing Water arrangement i.e. water reservoir (VAT) making interconnection with existing water main pipeline ,Supply, hoisting of PVC water storage tank, elevated platform in connection with ensuing WBLAE-2021 at Nepalipara Sarada Hindi High School of Coke-oven PS under DWSD,PHE Dte,Paschim Bardhaman. |  |  | ORD/000648/2020-2021 | 662/DWSD | 26/03/2021 | 02/04/2021 | MD AAMIR KHAN | 0.78 | 0.78 | 100 | 100
2 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation of Sinking of 02 Nos 100X40 mm dia 100 mtr deep tube wells using PVC pipes with installation of submersible pump in connection with assembly election-2021 at Durgapur Police Station complex for CPMF/SAP of Durgapur Police Station under DWSD, PHE Dte. |  |  | ORD/000479/2021-2022 | 677/DWSD | 16/04/2021 | 01/05/2021 | BISHAL ENTERPRISE | 2.74 | 2.74 | 100 | 100
3 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation order for the work of Proposed logistic support to the CPMF/WBSAP for providing sanitary arrangement (i.e. Construction of Temporary Latrine ,providing Water arrangement i.e. water reservoir (VAT) making interconnection with existing water main pipeline ,Supply, hoisting of PVC water storage tank, elevated platform in connection with ensuing WBLAE-2021 at Nepalipara Hindi High School of Coke-oven PS under DWSD,PHE Dte,Paschim Bardhaman. |  |  | ORD/000655/2020-2021 | 611_DWSD | 26/03/2021 | 02/04/2021 | MD AAMIR KHAN | 0.78 | 0.78 | 100 | 100
4 | ALIPURDUAR | Alipurduar-I | Alipore Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Operation & Maintenance of 22 (Twenty Two) nos. Integrated Water Supply Scheme already installed in different Schools at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. [Part-F]. (Period from 01.12.2021 to 31.01.2022) [For 2 (Two) Months]. |  |  | ORD/000854/2021-2022 | 3898/AD | 26/11/2021 | 26/01/2022 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 3.59 | 3.43 | 95.45 | 10
5 | ALIPURDUAR | Alipurduar-I | Alipore Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Operation & Maintenance of 22 (Twenty Two) nos. Integrated Water Supply Scheme already installed in different Schools at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. [Part-F]. (Period from 01.10.2021 to 30.11.2021) [For 2 (Two) Months]. |  |  | ORD/000671/2021-2022 | 2649/AD | 29/09/2021 | 29/11/2021 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 3.59 | 3.43 | 95.45 | 10
6 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation order for the work of Proposed logistic support to the CPMF/WBSAP for providing sanitary arrangement (i.e. Construction of Temporary Latrine ,providing Water arrangement i.e. water reservoir (VAT) making interconnection with existing water main pipeline ,Supply, hoisting of PVC water storage tank, elevated platform in connection with ensuing WBLAE-2021 at Sagarbhanga Hindi High School of Coke-oven PS under DWSD,PHE Dte,Paschim Bardhaman. |  |  | ORD/000651/2020-2021 | 606_DWSD | 26/03/2021 | 02/04/2021 | MD AAMIR KHAN | 0.78 | 0.78 | 100 | 100
7 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Under ground cable fault finding & laying of cable (T/W-,4&5) and others at Tarapith Improvement water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000695/2022-2023 | 1039/AE-III | 28/10/2022 | 02/11/2022 | STANDARD ELECTRICALS | 0.15 | 0.15 | 100 | 100
8 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Withdrawing of lowering of Submersible pumping machinery and others allied work at Haridaspur Water Supply Scheme under Bolpur Mechanical Division, PHE. Dte. |  |  | ORD/000214/2022-2023 | 803/AE-III | 12/07/2022 | 15/07/2022 | QUAZI NOZRUL ISLAM | 0.17 | 0.17 | 100 | 100
9 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | 3rd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Ayma Nababpur & Rameswarpur W/S Scheme for the period of 01.01.2023 to 31.08.2023 under Chinsurah Sub- Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000201/2023-2024 | 1687/HUG | 08/06/2023 | 06/02/2024 | M/S KAMALA ENTERPRISE | 5.42 | 2.42 | 44.71 | 0
10 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Operation & Maintenance of OHR, Laying Distribution System including Street Stand post, FHTC, Rising main & other essential components of BAGNAN ZONE-I,BAGNAN ZONE-II, BHASTARA, SHIBRAI, AKNA, PANDUA Z-I, PANDUA Z-II, PANDUA Z-III , BELUN & DWARBASINI W/S Scheme for the period from 01/09/2023 to 31/08/2024 under CHINSURAH Sub-Division of Hooghly Division P.H.E.Dte. |  |  | ORD/000466/2023-2024 | 2658/HUG | 31/08/2023 | 31/08/2024 | TOTON MONDAL | 46.23 | 10 | 21.63 | 0
11 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | OPERATION AND GUARDING OF HIGH LIFT AND LOW LIFT PUMPING MACHINERY AT LAVPUR WATER SUPPLY SCHEME ZONE -I I (P.H-I). | Assistant Engineer,Assistant Engineer (HQ) | Junior Engineer | ORD/000663/2023-2024 | 3181/BOL.MD | 29/09/2023 | 29/09/2024 | M/S SWAPAN BANERJEE | 5.37 | 0.88 | 16.45 | 100
12 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | 7th Continuation order of Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at CHANDITALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2023 to 31.03.2024. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000694/2023-2024 | 3549/HUG | 01/12/2023 | 01/04/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 2.56 | 1.91 | 74.59 | 100
13 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | 7th Continuation order of Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SEAKHALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2023 to 31.03.2024. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000696/2023-2024 | 3550/HUG | 01/12/2023 | 01/04/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 2.53 | 1.91 | 75.21 | 100
14 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Pump House repairing including jungles cutting at Dubrajpur Aurgumentation water supply scheme under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000496/2023-2024 | 1054/AE-III | 11/08/2023 | 16/08/2023 | RAJIB GHOSH | 0.4 | 0.38 | 96.4 | 100
15 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Withdrawing-Lowering of Submersible pumping machinery and other allied work at Nachonsha water supply scheme (PH.No-II)) under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000503/2023-2024 | 945/AE-III | 04/07/2023 | 09/07/2023 | S.K.ELECTRICALS | 0.94 | 0.94 | 100 | 100
16 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supervision of different mini Water Supply Scheme under Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/001028/2023-2024 | 262/BMSD(D) | 10/08/2023 | 10/02/2024 | SATYAJIT GHOSH | 0.89 | 0.83 | 93.07 | 100
17 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Withdrawing & Lowering of Submersible pumping machinery and other allied work at Sekhpur water supply scheme (P.H.-II) under Bolpur Mechanical Division,PHE.Dte. |  |  | ORD/000506/2023-2024 | 948/AE-III | 04/07/2023 | 08/07/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.73 | 0.72 | 98.3 | 100
18 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply Delivery & Installation of Foot valve and check valve at Suri Sadar Hospital water supply scheme (Block-Suri-I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000995/2023-2024 | 1284-/AE-III | 09/10/2023 | 16/10/2023 | HINDOL ROY | 0.57 | 0.57 | 100 | 100
19 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Repairing and servicing of Gaseous chlorination system at Khoyrasole (Churror) water supply scheme under Bolpur Mechanical Division, PHE. Dte. |  |  | ORD/000900/2022-2023 | 288/AE-III | 15/03/2023 | 25/03/2023 | ORIENTAL ENGINEERING CO. | 0.19 | 0 | 0 | 100
20 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation order for the work of Engagement of 01 (one) no Gr-D staff , contractual through agency for 6 (six) month as per categories for the office of the Executive Engineer under Durgapur Water Supply Division , PHE Dte.(w.e.f - 01.10.2023 to 30.11.2023) (SL-01) |  |  | ORD/000244/2023-2024 | 1610/DWSD | 29/09/2023 | 29/11/2023 | K.M. ENTERPRISE | 0.31 | 0.31 | 100 | 100
21 | ALIPURDUAR | Alipurduar-I | Durgapur W/S Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Acceptance cum formal order for the work of Day to day establishment works of maintaining of files for releasing SD money of pending works 01 (One) no of additional support hand person engaged temporary monthly basis for the office of the Executive Engineer, Durgapur Water Supply Division , PHE Dte.(Period from 01.09.2023 to 30.11.2023) (For 3 Months) (Sl-01) |  |  | ORD/000266/2023-2024 | 97/SPOT/DWSD | 31/08/2023 | 30/11/2023 | K.M. ENTERPRISE | 0.47 | 0.47 | 100 | 100
22 | ALIPURDUAR | Alipurduar-I | Bolpur Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply and Delivery of Submersible pump for Zone-IX of Bolpur Water Supply Project under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001225/2023-2024 | 280/AE-III | 21/02/2024 | 28/02/2024 | TULIP ENTERPRISE | 0.81 | 0.81 | 100 | 100
23 | ALIPURDUAR | Alipurduar-I | Tamluk Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Maintenance of civil and plumbing works for Digha State General Hospital Main Building at Digha under Digha Sub -Division within Tamluk Division, PHE Dte. for the period 12 ( Twelve) months. (Tender No. 532/TAM/2021-22) |  |  | BILL/02408/2023-2024 | 696/W | 27/03/2024 | 27/03/2024 | LOKENATH ENTERPRISE | 1.89 | 0 | 0 | 0
24 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply and delivery of HSD oil to be hired inspection vehicle |  |  | BILL/03260/2023-2024 | 425 | 28/03/2024 | 28/03/2024 | RAM BHAGAT HARIPRASAD HP SERVICE STATION (BURDWAN) | 0.39 | 0 | 0 | 0
25 | ALIPURDUAR | Alipurduar-I | North 24 Pgs W/S Division I | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply of Stationary articles for the office of the EE, NWSD-I, P.H.E. Dte. W.O. No.485/NWSD-I dt.15/03/2024 & Invoice No.49051 Dt.18/03/2024 |  |  | BILL/00630/2023-2024 | 590/MAINT/23-24 | 30/03/2024 | 30/03/2024 | BARRACKPORE CENTRAL ZONE WHOLESALE CONSUMERS CO OPERATIVE SOCIETY LTD. | 0.04 | 0 | 0 | 0
26 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Providing guards round the clock for office of the DIC (BMSD), D, PHED |  |  | BILL/03266/2023-2024 | 420 | 28/03/2024 | 28/03/2024 | M/S CHANDIMATA | 2.31 | 0 | 0 | 0
27 | ALIPURDUAR | Alipurduar-I | Alipore Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Pest control and rat treatment to get rid of unwanted pest with in the entire office premises along with stop the menance of rat damaging computer cables most frequently, at office premises of the Executive Engineer, Alipore Division, PHE Dte. (Period from 16.07.2023 to 31.12.2023). |  |  | BILL/03548/2023-2024 | 2215204 | 27/03/2024 | 27/03/2024 | PIMI PEST CONTROL ENTERPRISE | 0.86 | 0 | 0 | 0
28 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New |  |  |  | BILL/02129/2023-2024 | 2215136 | 27/03/2024 | 27/03/2024 | PRASUN BISWAS | 2.21 | 0 | 0 | 0
29 | ALIPURDUAR | Alipurduar-I | Tamluk Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | PURCHASE OF INTEL CPU PC, DELL MOUSE USB OPTICAL MS 116 AND HEAT SINK PASTE SMALL SYRINGE FOR TAMLUK SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. |  |  | BILL/02246/2023-2024 | 707/W | 27/03/2024 | 27/03/2024 | E-TECH MALL | 0.05 | 0 | 0 | 0
30 | ALIPURDUAR | Alipurduar-I | Alipore Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Preparation of Income Tax Statement Data Entry E-Filling of Income Tax Return under Alipore Division, PHE Dte |  |  | BILL/03528/2023-2024 | 2215204 | 27/03/2024 | 27/03/2024 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0 | 0
31 | ALIPURDUAR | Alipurduar-I | North 24 Pgs W/S Division I | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply of Stationary articles for the office of the EE, NWSD-I, P.H.E. Dte. W.O. No.433/NWSD-I dt.07/03/2024 & Invoice No.49050 Dt.07/03/2024 |  |  | BILL/00631/2023-2024 | 590/MAINT/23-24 | 30/03/2024 | 30/03/2024 | BARRACKPORE CENTRAL ZONE WHOLESALE CONSUMERS CO OPERATIVE SOCIETY LTD. | 0.06 | 0 | 0 | 0
32 | ALIPURDUAR | Alipurduar-I | North 24 Pgs W/S Division I | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply of Stationary articles for the office of the EE, NWSD-I, P.H.E. Dte. W.O. No.521/NWSD-I dt.19/03/2024 & Invoice No.49053 Dt.21/03/2024 |  |  | BILL/00632/2023-2024 | 588/MAINT/23-24 | 31/03/2024 | 31/03/2024 | BARRACKPORE CENTRAL ZONE WHOLESALE CONSUMERS CO OPERATIVE SOCIETY LTD. | 0.03 | 0 | 0 | 0
33 | ALIPURDUAR | Alipurduar-I | Asansol Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Part payment of RCFA II for the month of Jan 2024 |  |  | BILL/01039/2023-2024 | 779/5 | 27/03/2024 | 27/03/2024 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 14.95 | 0 | 0 | 0
34 | ALIPURDUAR | Alipurduar-I | Tamluk Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Providing and Installation of Pumping Machineries and other electromechanical equipment for newly construed tubewell no. ¿ II of Administrative Complex Water Supply Scheme at Nimtouri, Purba Medinipur. |  |  | BILL/02344/2023-2024 | 754/W | 28/03/2024 | 28/03/2024 | PRANAB KUMAR DAS | 4.86 | 0 | 0 | 0
35 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New |  |  |  | BILL/02082/2023-2024 | 2215133 | 27/03/2024 | 27/03/2024 | GLOBAL POINT | 0.21 | 0 | 0 | 0
36 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New |  |  |  | BILL/02084/2023-2024 | 2215135 | 27/03/2024 | 27/03/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 2.06 | 0 | 0 | 0
37 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New |  |  |  | BILL/02113/2023-2024 | 2215132 | 27/03/2024 | 27/03/2024 | BURDWAN WHOLESALE CONSUMERS' CO- OPERATIVE SOCIETY LTD. | 0.21 | 0 | 0 | 0
38 | ALIPURDUAR | Alipurduar-I | Bankura Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Fuel charges |  |  | BILL/01782/2023-2024 | 172/W-1271-1274 | 27/03/2024 | 27/03/2024 | LALJI RAJA & SONS AGENCIES | 6.12 | 0 | 0 | 0
39 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply and delivery of HSD oil to be hired inspection vehicle |  |  | BILL/03259/2023-2024 | 427 | 28/03/2024 | 28/03/2024 | RAM BHAGAT HARIPRASAD HP SERVICE STATION (BURDWAN) | 0.4 | 0 | 0 | 0
40 | ALIPURDUAR | Alipurduar-I | Hooghly Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New |  |  |  | BILL/02083/2023-2024 | 2215134 | 27/03/2024 | 27/03/2024 | IMPRESSION | 0.55 | 0 | 0 | 0
41 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | SUPPLY OF POWER FROM GENERATOR |  |  | BILL/03261/2023-2024 | 424 | 27/03/2024 | 27/03/2024 | SK HARUN | 0.02 | 0 | 0 | 0
42 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Providing guards round the clock for office of the DIC (BMSD), D, PHED |  |  | BILL/03267/2023-2024 | 420 | 28/03/2024 | 28/03/2024 | M/S CHANDIMATA | 3.09 | 0 | 0 | 0
43 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Repairing of withdrawn damaged 7.5 hp pump motor set for TW-1 of Sajiara PWSS |  |  | BILL/03265/2023-2024 | 421/CMD/23-24 | 28/03/2024 | 28/03/2024 | P.K. ENGINEERING | 0.24 | 0 | 0 | 0
44 | ALIPURDUAR | Alipurduar-I | Tamluk Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Different petty expenditure and supply of Tiffine packets for monthly meeting under the office of the Executive Engineer, Tamluk Division, PHE Dte. |  |  | BILL/02245/2023-2024 | 707/W | 27/03/2024 | 27/03/2024 | SAYAN MAITY | 0.26 | 0 | 0 | 0
45 | ALIPURDUAR | Alipurduar-I | Central Mechanical | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Supply and delivery of HSD oil to be hired inspection vehicle |  |  | BILL/03258/2023-2024 | 426 | 28/03/2024 | 28/03/2024 | RAM BHAGAT HARIPRASAD HP SERVICE STATION (BURDWAN) | 0.37 | 0 | 0 | 0
46 | ALIPURDUAR | Alipurduar-I | Tamluk Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Engage daily wages labour as valve operator (for O.H.R) at Bheribaranga W/S Scheme under Digha Sub-Division of Tamluk Division P.H.E.Dte. (Tender No. 294/TAM/2023-24) |  |  | BILL/02409/2023-2024 | 694/W | 27/03/2024 | 27/03/2024 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.35 | 0 | 0 | 0
47 | ALIPURDUAR | Alipurduar-I | Alipore Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | Continuation work order for Car Parking Space at Ganesh Chandra Avenue, Kolkata - 700013 for 02 (Two) nos. Vehicle of Officials under Alipore Division, PHE Dte. [period from 01.09.2023 to 29.02.2024] (6 months) |  |  | BILL/03549/2023-2024 | 2215204 | 27/03/2024 | 27/03/2024 | PIONEER CO-OPERATIVE CAR PARKING SERVICING & CONSTRUCTION SOCIETY LTD. | 0.18 | 0 | 0 | 0
48 | ALIPURDUAR | Alipurduar-I | Coochbehar Division | Arrangement for supply of safe drinking water after commissioning of piped water supply scheme. | SM/19197 | New | exc. of different work at sikarpur PWSS |  |  | BILL/02126/2023-2024 | 173 | 28/03/2024 | 28/03/2024 | A.O BSNL | 2.85 | 0 | 0 | 0
Total | [13 empty] | 124.94 | 34.41 | 27.54