## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | SM/19376 | Augmentation | Construction of 25cum CWR with switch room with sanitary and water supply arrangement and Boundary wall, pathway, providing FHTC and Headwork pipe connection of Cha Sundori Project of Lankapara TG PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000569/2024-2025 | 4178/ALD | 03/12/2024 | 02/04/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 58.2 | 0 | 0 | 0
Total | [13 empty] | 58.2 | 0 | 0