## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | SM/19376 | Augmentation | Construction of 25cum CWR with switch room with sanitary and water supply arrangement and Boundary wall, pathway, providing FHTC and Headwork pipe connection of Cha Sundori Project of Lankapara TG PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000569/2024-2025 | 4178/ALD | 03/12/2024 | 02/08/2026 | DILIP MAHATO (OPC) PRIVATE LIMITED | 58.2 | 0 | 0 | 61
2 | ALIPURDUAR |  | Alipurduar Division | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | SM/19376 | Augmentation | Laying pipe line for (Mouza-Lankapara TG, JL No.30, Sheet no-5, Plot No-704) 404 units for Lankapara cha Sundori PWSS (Cluster-1) under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000571/2024-2025 | 5008/ALD | 10/02/2025 | 01/04/2026 | DILIP MAHATO (OPC) PRIVATE LIMITED | 33.88 | 0 | 0 | 55
3 | ALIPURDUAR |  | Alipurduar Division | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | SM/19376 | Augmentation | Laying of pipeline for (Mouza-Lankapara TG, JL No.30 Sheet no-5, Plot No. 920-923) 375 Units for Lankapara Cha sundari PWSS (Cluster-4) under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000200/2025-2026 | 2239/ALD | 16/10/2025 | 02/04/2026 | SATYABRATA BHATTACHERJEE | 20.42 | 8.54 | 41.83 | 60
4 | ALIPURDUAR |  | Alipurduar Division | Augmentation Of Lankapara Chasundari Piped Water Supply Scheme | SM/19376 | Augmentation | Supply delivery installation commissioning of submersible pumping machinery and others electro mechanical works for Newly proposed TW at Lankapara TG WSS at VES-4 under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000123/2025-2026 | 1476/ALD | 24/07/2025 | 22/09/2025 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 10.56 | 10.56 | 100 | 80
Total | [13 empty] | 123.06 | 19.1 | 15.52