## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
2 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
3 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
4 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
5 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
6 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
7 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
8 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Units (DPMU) at Aliporedure, Coochbehar, Jalpaiguri, Darjeeling Kalimpong, Uttar Dinajpur and Daskin Dinajpur districts under Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4461/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 453.13 | 434.06 | 95.79 | 52
9 | ALIPURDUAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
10 | COOCHBEHAR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
11 | DAKSHIN DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
12 | DARJEELING |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
13 | JALPAIGURI |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
14 | KALIMPONG |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
15 | MALDAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
16 | UTTAR DINAJPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Malda, Alipurduar, Coochbehar, Jalpaiguri, Uttar Dinajpur, Dakshin Dinajpur and Darjeeling & Kalimpong districts under Jal Jeevan Mission (JJM). | SM/11373 | Support-Admin-HRD | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Bardhaman, Paschim Bardhaman, Birbhum, Malda, and Murshidabadunder Jal Jeevan Mission / Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 4462/RS | 02/08/2022 | 29/01/2024 | MARS PLANING & ENGINEERING SERVICES PVT. LTD. | 408.24 | 126.04 | 30.88 | 49
Total | [13 empty] | 6890.98 | 4480.8 | 65.02