## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
2 | BANKURA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
3 | BIRBHUM |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
4 | COOCHBEHAR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
6 | DARJEELING |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
7 | HOOGHLY |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
8 | HOWRAH |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
9 | JALPAIGURI |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
10 | JHARGRAM |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
11 | KALIMPONG |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
12 | MALDAH |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
13 | MURSHIDABAD |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
14 | NADIA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
15 | NORTH 24 PARGANAS |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
18 | PURBA BARDHAMAN |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
19 | PURBA MEDINIPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
20 | PURULIA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
22 | UTTAR DINAJPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Upgradation of Water Testing laboratories to comply with NABL Accreditation/Recognition protocol related to Water Quality Monitoring & surveillance Activity under Jal Jeevan Mission |  | Junior Engineer | ORD/000709/2022-2023 | 5666/RS | 28/10/2022 | 26/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 229.15 | 177.43 | 77.43 | 0
23 | ALIPURDUAR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
24 | BANKURA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
25 | BIRBHUM |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
26 | COOCHBEHAR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
27 | DAKSHIN DINAJPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
28 | DARJEELING |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
29 | HOOGHLY |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
30 | HOWRAH |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
31 | JALPAIGURI |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
32 | JHARGRAM |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
33 | KALIMPONG |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
34 | MALDAH |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
35 | MURSHIDABAD |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
36 | NADIA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
37 | NORTH 24 PARGANAS |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
38 | PASCHIM BARDHAMAN |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
39 | PASCHIM MEDINIPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
40 | PURBA BARDHAMAN |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
41 | PURBA MEDINIPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
42 | PURULIA |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
43 | SOUTH 24 PARGANAS |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
44 | UTTAR DINAJPUR |  | Resource | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of Spare Parts for regular upkeep of laboratory equipments and installation of new instruments required for different water testing laboratories related to Water Quality Monitoring and Survelliance Activities under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 5668/RS | 28/10/2022 | 28/10/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 240.84 | 240.84 | 100 | 99
45 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
46 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
47 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
48 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
49 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
50 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
51 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
52 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
53 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
54 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
55 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
56 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
57 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
58 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
59 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
60 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
61 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
62 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
63 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
64 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
65 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
66 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
67 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
68 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
69 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
70 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
71 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
72 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
73 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
74 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
75 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
76 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
77 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
78 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
79 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
80 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
81 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
82 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
83 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
84 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
85 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
86 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
87 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
88 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
89 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
90 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
91 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
92 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
93 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
94 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
95 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
96 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
97 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
98 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
99 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
100 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
101 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
102 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
103 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
104 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
105 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
106 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
107 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
108 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
109 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
110 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
111 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
112 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
113 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
114 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
115 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
116 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
117 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
118 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
119 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
120 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
121 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
122 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
123 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
124 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
125 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
126 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
128 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
129 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
130 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
131 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
132 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
133 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
134 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
135 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
136 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
137 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
138 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
139 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
140 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
141 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
142 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
143 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
144 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
145 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
146 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
147 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
148 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
149 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
150 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
151 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
152 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
153 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
154 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
155 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
156 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
157 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
158 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
159 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
160 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
161 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
162 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
163 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
164 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
165 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
166 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
167 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
168 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
169 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
170 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
171 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
172 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
173 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
174 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
175 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
176 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
177 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
178 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
179 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
180 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
181 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
182 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
183 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
184 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
185 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
186 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
187 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
188 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
189 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
190 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
191 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
192 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
193 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
194 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
195 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
196 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
197 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
198 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
199 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
200 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
201 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
202 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
203 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
204 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
205 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
206 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
207 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
208 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
209 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
210 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
211 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
212 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
213 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
214 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
216 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
217 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
218 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
219 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
220 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
221 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
222 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
223 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
224 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
225 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
226 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
227 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
228 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
229 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
230 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
231 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
232 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
233 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
234 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
235 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
236 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
237 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
238 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
239 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
240 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
241 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
242 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
243 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
244 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
245 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
246 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
247 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
248 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
249 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
250 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
251 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
252 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
253 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
254 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
255 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
256 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
257 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
258 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
259 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
260 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
261 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
262 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
263 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
264 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
265 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
266 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
267 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
268 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
270 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
271 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
272 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
273 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
274 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
275 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
276 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
277 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
278 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
284 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | MATERIAL PROCUREMENT FOR PRA COMPLY NABL ACCREDITATION WITH SOP FOR KALYANI STATE REFFERAL LABORATORY,KALYANI ,NADIA |  |  | BILL/00330/2024-2025 | 317/PFMS | 06/12/2024 | 06/12/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.79 | 0 | 0 | 0
287 | ALIPURDUAR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
288 | BANKURA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
289 | BIRBHUM |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
290 | COOCHBEHAR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
291 | DAKSHIN DINAJPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
292 | DARJEELING |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
293 | HOOGHLY |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
294 | HOWRAH |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
295 | JALPAIGURI |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
296 | JHARGRAM |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
297 | KALIMPONG |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
298 | MALDAH |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
299 | MURSHIDABAD |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
300 | NADIA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
301 | NORTH 24 PARGANAS |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
302 | PASCHIM BARDHAMAN |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
303 | PASCHIM MEDINIPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
304 | PURBA BARDHAMAN |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
305 | PURBA MEDINIPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
306 | PURULIA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
307 | SOUTH 24 PARGANAS |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
308 | UTTAR DINAJPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
309 | ALIPURDUAR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
310 | BANKURA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
311 | BIRBHUM |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
312 | COOCHBEHAR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
313 | DAKSHIN DINAJPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
314 | DARJEELING |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
315 | HOOGHLY |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
316 | HOWRAH |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
317 | JALPAIGURI |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
318 | JHARGRAM |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
319 | KALIMPONG |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
320 | MALDAH |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
321 | MURSHIDABAD |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
322 | NADIA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
323 | NORTH 24 PARGANAS |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
324 | PASCHIM BARDHAMAN |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
325 | PASCHIM MEDINIPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
326 | PURBA BARDHAMAN |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
327 | PURBA MEDINIPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
328 | PURULIA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
329 | SOUTH 24 PARGANAS |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
330 | UTTAR DINAJPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 13/11/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 50
331 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
332 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
333 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
334 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
335 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
336 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
337 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
338 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
339 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
340 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
341 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
342 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
343 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
344 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
345 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
346 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
347 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
348 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
349 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
350 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
351 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
352 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, Commissioning followed by at least five days necessary training of Optical true double beam atomic absorption spectrophotometer (AAS) with vapour generation assembly for water testing laboratory at Arsenic affected areas of West Bengal complete with the following items as per detailed specification and as per satisfaction of Engineer-in-charge. |  |  | BILL/01809/2024-2025 | 609-MSD/2024-25 | 27/01/2025 | 27/01/2025 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
353 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
354 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
355 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
356 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
357 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
358 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
359 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
360 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
361 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
362 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
363 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
364 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
365 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
366 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
367 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
368 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
369 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
370 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
371 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
372 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
373 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
374 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, delivery, installation training on application and 6 Months operation of computer controlled bench top inductive coupled Plasma Mass Spectro Meter ( ICP - MS) Coupled with Ion Chromatograph ( IC) with a single software for ICP MS & IC required for analysis of heavy metal in trace level & Specification studies as well as analysis of anions & Cations in water sample at Kalyani state Referal Laboratory under Nadia Arsenic Division- I, P. H. E Dte ( Operation supply of computer Controlled bench top Indicative Coupled Plasma mass Spe) |  |  | BILL/00511/2024-2025 |  | 17/02/2025 | 17/02/2025 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.49 | 0 | 0 | 0
Total | [13 empty] | 22147.44 | 9823.09 | 44.35