## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
2 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
3 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
4 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
5 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
6 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
7 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
8 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
9 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
10 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
11 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
12 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
13 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
14 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
15 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
16 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
17 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
18 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
19 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
20 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
21 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Islampur Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000564/2022-2023 | 1027/RD/PHE | 31/03/2023 | 30/05/2023 | PRINCE BUILDERS | 8.54 | 8.53 | 99.95 | 0
23 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
24 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
25 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
26 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
27 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
28 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
29 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
30 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
31 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
32 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
33 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
34 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
35 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
36 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
37 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
38 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
39 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
40 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
41 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
42 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
43 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
44 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Electrification for Repair and Maintenance of Islampur Sub Division Laboratory under Islampur Sub-Division, PHE Dte. (PART - B) | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2022-2023 | 501/RD/PHE | 17/02/2023 | 27/02/2023 | JHUNU SAHA JHUNU.RNJ@GMAIL.COM | 1.44 | 1.44 | 99.91 | 0
45 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
46 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
47 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
48 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
50 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
51 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
52 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
53 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
54 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
55 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
56 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
57 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
58 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
64 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00499/2023-2024 | 386/PFMS | 08/12/2023 | 08/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 174.69 | 0 | 0 | 0
67 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
68 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
69 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
70 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
71 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
72 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
73 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
74 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
75 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
76 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
77 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
78 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
79 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
80 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
81 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
82 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
83 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
84 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
85 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
86 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
87 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
88 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000563/2022-2023 | 1026/RD/PHE | 31/03/2023 | 30/04/2023 | M/S.SADHANA ENTERPRISE | 3.43 | 3.36 | 98.02 | 100
89 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
90 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
91 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
92 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
93 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
94 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
95 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
96 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
97 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
98 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
99 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
100 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
101 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
102 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
103 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
104 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
105 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
106 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
107 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
108 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
109 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
110 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply of microprocessor-based gas box for Thermo ICE 3500 AAS with VGA. Complete with gas box with processor board & burner interface assembly, cable, bracket, tube insert, flow restrictor, hook and look cable tie with mounting with required hose assey & Atomic Absorption spray chamber kit & any other accessories (Thermo Scientific mk) required to install and smooth running the system of AAS of Murshidabad District Laboratory. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000736/2023-2024 | 9/MURD | 03/01/2024 | 02/02/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.38 | 10.38 | 100 | 100
111 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
112 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
113 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
114 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
115 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
116 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
117 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
118 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
119 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
120 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
121 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
122 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
123 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
124 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
125 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
126 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
127 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
128 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
129 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
130 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
131 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
132 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Infrastructural development of Domkal S.D Laboratory and Jangipur S.D Laboratory to accommodate the installation of AAS (Atomic Apsorption Spectrometry) under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2,Junior Engineer, Estimating Section | ORD/000843/2023-2024 | 781/MURD | 14/03/2024 | 13/04/2024 | ROY & SAMANTA CONSTRUCTION | 4.57 | 4.52 | 98.9 | 95
133 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
134 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
135 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
136 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
137 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
138 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
139 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
140 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
141 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
142 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
143 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
144 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
145 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
146 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
147 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
148 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
149 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
150 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
151 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
152 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
153 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
154 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply & Installation of AC Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00592/2023-2024 | 505/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 1.4 | 0 | 0 | 0
155 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
156 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
157 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
158 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
159 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
160 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
161 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
162 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
163 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
164 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
165 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
166 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
167 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
168 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
169 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
170 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
171 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
172 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
173 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
174 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
175 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
176 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Bill for Supply of Laboratory Furniture at Kalyani State Referral Laboratory Nadia. under Nadia Arsenic Division -I, PHED. |  |  | BILL/00593/2023-2024 | 506/PFMS | 23/02/2024 | 23/02/2024 | EASY DAY ENTERPRISE | 2.12 | 0 | 0 | 0
177 | ALIPURDUAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
178 | BANKURA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
179 | BIRBHUM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
180 | COOCHBEHAR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
181 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
182 | DARJEELING |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
183 | HOOGHLY |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
184 | HOWRAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
185 | JALPAIGURI |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
186 | JHARGRAM |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
187 | KALIMPONG |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
188 | MALDAH |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
189 | MURSHIDABAD |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
190 | NADIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
191 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
192 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
193 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
194 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
195 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
196 | PURULIA |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
197 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
198 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply delivery, Installation, training on application and 6 months operation of computer Controlled bench top inductive Coupled Plasma Mass Spectro meter (ICP-MS) coupled with Ion chromatograph (IC) with a single software for ICP MS & IC required for analysis of heavy metals in trace level & speciation studies as well as analysis of anions & cations in water sample for water testing laboratories in Kalyani State Referral Laboratory. |  |  | BILL/00694/2023-2024 | 540/PFMS | 16/03/2024 | 16/03/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 116.46 | 0 | 0 | 0
199 | ALIPURDUAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
200 | BANKURA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
201 | BIRBHUM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
202 | COOCHBEHAR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
203 | DAKSHIN DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
204 | DARJEELING |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
205 | HOOGHLY |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
206 | HOWRAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
207 | JALPAIGURI |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
208 | JHARGRAM |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
209 | KALIMPONG |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
210 | MALDAH |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
211 | MURSHIDABAD |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
212 | NADIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
213 | NORTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
214 | PASCHIM BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
216 | PURBA BARDHAMAN |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
217 | PURBA MEDINIPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
218 | PURULIA |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
219 | SOUTH 24 PARGANAS |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
220 | UTTAR DINAJPUR |  | Murshidabad Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Supply, installation, commissioning followed by at least five days necessary trainning of Optical True Double - Beam Atomic Absorption Spectrophotometer (AAS) with Vapour Generation Assembly for water Testing Laboratory at arsenic affected areas of West Bengal complete with the following items as per detailsed specification and as per satisfaction of Engineer - in-charge. Buyer - Executive Engineer, Murshidabad Division, PHE Dte. |  |  | BILL/01356/2023-2024 | 689-MSD/2023-24 | 23/03/2024 | 23/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 49.06 | 0 | 0 | 0
221 | ALIPURDUAR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
222 | BANKURA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
223 | BIRBHUM |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
224 | COOCHBEHAR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
225 | DAKSHIN DINAJPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
226 | DARJEELING |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
227 | HOOGHLY |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
228 | HOWRAH |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
229 | JALPAIGURI |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
230 | JHARGRAM |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
231 | KALIMPONG |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
232 | MALDAH |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
233 | MURSHIDABAD |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
234 | NADIA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
235 | NORTH 24 PARGANAS |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
236 | PASCHIM BARDHAMAN |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
237 | PASCHIM MEDINIPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
238 | PURBA BARDHAMAN |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
239 | PURBA MEDINIPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
240 | PURULIA |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
241 | SOUTH 24 PARGANAS |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
242 | UTTAR DINAJPUR |  | Barasat Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Formal work order for Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Basirhat Sub-District Water Testing Laboratory in North 24 Parganas district under Barasat Division,Public Health Engineering Dte. | Assistant Engineer |  | ORD/000958/2024-2025 | 348/BD | 31/01/2025 | 31/10/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 53.65 | 0 | 0 | 0
243 | ALIPURDUAR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
244 | BANKURA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
245 | BIRBHUM |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
246 | COOCHBEHAR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
247 | DAKSHIN DINAJPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
248 | DARJEELING |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
249 | HOOGHLY |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
250 | HOWRAH |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
251 | JALPAIGURI |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
252 | JHARGRAM |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
253 | KALIMPONG |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
254 | MALDAH |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
255 | MURSHIDABAD |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
256 | NADIA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
257 | NORTH 24 PARGANAS |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
258 | PASCHIM BARDHAMAN |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
259 | PASCHIM MEDINIPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
260 | PURBA BARDHAMAN |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
261 | PURBA MEDINIPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
262 | PURULIA |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
263 | SOUTH 24 PARGANAS |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
264 | UTTAR DINAJPUR |  | Nadia Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Procurement, Installation, Training & 6 months operation of Double Beam Atomic Absorption Spectrophotometer including all necessary hardware & prerequisites for arsenic analysis in ppb level with 3 years Annual Maintenance of the system after expiry of warranty period and supply installation and operational training of ultrapura water generation system in a single package for Nadia District Water Testing Laboratory under Nadia Division, Public Health Engineering Dte. | Assistant Engineer |  | ORD/000066/2025-2026 | 2380/ND | 22/05/2025 | 16/02/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 53.65 | 0 | 0 | 0
265 | ALIPURDUAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
266 | BANKURA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
267 | BIRBHUM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
268 | COOCHBEHAR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
269 | DAKSHIN DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
270 | DARJEELING |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
271 | HOOGHLY |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
272 | HOWRAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
273 | JALPAIGURI |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
274 | JHARGRAM |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
275 | KALIMPONG |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
276 | MALDAH |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
277 | MURSHIDABAD |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
278 | NADIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
279 | NORTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
280 | PASCHIM BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
281 | PASCHIM MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
282 | PURBA BARDHAMAN |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
283 | PURBA MEDINIPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
284 | PURULIA |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
285 | SOUTH 24 PARGANAS |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
286 | UTTAR DINAJPUR |  | Raiganj Division | Up-gradation of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/11926 | Support-WQMSP | Making Distribution wiring and allied work in connection with Up-gradation of PHED managed laboratories related to water quality monitoring and surveillance activity under JJM for Hemtabad Sub-District Laboratory in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000566/2022-2023 | 1028/RD/PHE | 31/03/2023 | 30/04/2023 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 0.98 | 0 | 0 | 100
Total | [13 empty] | 10567.96 | 621.16 | 5.88