## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
2 | BANKURA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
3 | BIRBHUM |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
4 | COOCHBEHAR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
6 | DARJEELING |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
7 | HOOGHLY |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
8 | HOWRAH |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
9 | JALPAIGURI |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
10 | JHARGRAM |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
11 | KALIMPONG |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
12 | MALDAH |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
13 | MURSHIDABAD |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
14 | NADIA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
15 | NORTH 24 PARGANAS |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
18 | PURBA BARDHAMAN |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
19 | PURBA MEDINIPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
20 | PURULIA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
22 | UTTAR DINAJPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Procurement of 4 nos. On-site Mobile Analysis Systems (OMAS) equipped with consumables, reagents, smart phones with preloaded water quality app synchronized with PHED water quality dashboard in different water testing laboratories as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. |  | Junior Engineer | ORD/000668/2022-2023 | 4801/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 54.68 | 32.36 | 59.18 | 0
23 | ALIPURDUAR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
24 | BANKURA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
25 | BIRBHUM |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
26 | COOCHBEHAR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
27 | DAKSHIN DINAJPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
28 | DARJEELING |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
29 | HOOGHLY |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
30 | HOWRAH |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
31 | JALPAIGURI |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
32 | JHARGRAM |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
33 | KALIMPONG |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
34 | MALDAH |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
35 | MURSHIDABAD |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
36 | NADIA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
37 | NORTH 24 PARGANAS |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
38 | PASCHIM BARDHAMAN |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
39 | PASCHIM MEDINIPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
40 | PURBA BARDHAMAN |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
41 | PURBA MEDINIPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
42 | PURULIA |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
43 | SOUTH 24 PARGANAS |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
44 | UTTAR DINAJPUR |  | Resource | Water Ouality Monitoring through On-site Mobile Analysis System (OMAS testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State and Arsenic & Iron Removal Plants (AIRPs) in four Arsenic affected districts viz Maldah, Mu | SM/11928 | Support-WQMSP | Water Quality Monitoring through On-site Mobile Analysis System (OMAS) testing in Untouched Habitations, Schools, Anganwadis, Health Facilities throughout the State related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 716/RS | 28/02/2023 | 29/06/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 334.31 | 263.36 | 78.78 | 86
Total | [13 empty] | 8557.92 | 6505.87 | 76.02