## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
2 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
3 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
4 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
6 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
7 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
8 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
9 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
10 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
11 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
12 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
13 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
14 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
15 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
18 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
19 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
20 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
22 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
23 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
24 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
25 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
26 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
27 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
28 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
29 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
30 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
31 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
32 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
33 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
34 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
35 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
36 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
37 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
38 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
39 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
40 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
41 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
42 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
43 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
44 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
45 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
46 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
47 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
48 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
49 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
50 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
51 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
52 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
53 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
54 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
55 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
56 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
57 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
58 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
59 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
60 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
61 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
62 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
63 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
64 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
65 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
66 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
67 | ALIPURDUAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
68 | BANKURA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
69 | BIRBHUM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
70 | COOCHBEHAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
71 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
72 | DARJEELING |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
73 | HOOGHLY |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
74 | HOWRAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
75 | JALPAIGURI |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
76 | JHARGRAM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
77 | KALIMPONG |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
78 | MALDAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
79 | MURSHIDABAD |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
80 | NADIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
81 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
82 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
83 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
84 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
85 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
86 | PURULIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
87 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
88 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
89 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
90 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
91 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
92 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
93 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
94 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
95 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
96 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
97 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
98 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
99 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
100 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
101 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
102 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
103 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
104 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
105 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
106 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
107 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
108 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
109 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
110 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
111 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
112 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
113 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
114 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
115 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
116 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
117 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
118 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
119 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
120 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
121 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
122 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
123 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
124 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
125 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
126 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
127 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
128 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
129 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
130 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
131 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
132 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
133 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
134 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
135 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
136 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
137 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
138 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
139 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
140 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
141 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
142 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
143 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
144 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
145 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
146 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
147 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
148 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
149 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
150 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
151 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
152 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
153 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
154 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
155 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
156 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
157 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
158 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
159 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
160 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
161 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
162 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
163 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
164 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
165 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
166 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
167 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
168 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
169 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
170 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
171 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
172 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
173 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
174 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
175 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
176 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
177 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
178 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
179 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
180 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
181 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
182 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
183 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
184 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
185 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
186 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
187 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
188 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
189 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
190 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
191 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
192 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
193 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
194 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
195 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
196 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
197 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
198 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
199 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
200 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
201 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
202 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
203 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
204 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
205 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
206 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
207 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
208 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
209 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
210 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
211 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
212 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
213 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
214 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
215 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
216 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
217 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
218 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
219 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
220 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
221 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
222 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
223 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
224 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
225 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
226 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
227 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
228 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
229 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
230 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
231 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
232 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
233 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
234 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
235 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
236 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
237 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
238 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
239 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
240 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
241 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
242 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
243 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
244 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
245 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
246 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
247 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
248 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
249 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
250 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
251 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
252 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
253 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
254 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
255 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
256 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
257 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
258 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
259 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
260 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
261 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
262 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
263 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
264 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
265 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
266 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
267 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
268 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
269 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
270 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
271 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
272 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
273 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
274 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
275 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
276 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
277 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
278 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
279 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
280 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
281 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
282 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
283 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
284 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
285 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
286 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
287 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
288 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
289 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
290 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
291 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
292 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
293 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
294 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
295 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
296 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
297 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
298 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
299 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
300 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
301 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
302 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
303 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
304 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
305 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
306 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
307 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
308 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
309 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
310 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
311 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
312 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
313 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
314 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
315 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
316 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
317 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
318 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
319 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
320 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
321 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
322 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
323 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
324 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
325 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
326 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
327 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
328 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
329 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
330 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
331 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
332 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
333 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
334 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
335 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
336 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
337 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
338 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
339 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
340 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
341 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
342 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
343 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
344 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
345 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
346 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
347 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
348 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
349 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
350 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
351 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
352 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
353 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
354 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
355 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
356 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
357 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
358 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
359 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
360 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
361 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
362 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
363 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
364 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
365 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
366 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
367 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
368 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
369 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
370 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
371 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
372 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
373 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
374 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
375 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
376 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
377 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
378 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
379 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
380 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
381 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
382 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
383 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
384 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
385 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
386 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
387 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
388 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
389 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
390 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
391 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
392 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
393 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
394 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
395 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
396 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
397 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
398 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
399 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
400 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
401 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
402 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
403 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
404 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
405 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
406 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
407 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
408 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
409 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
410 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
411 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
412 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
413 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
414 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
415 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
416 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
417 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
418 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
419 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
420 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
421 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
422 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
423 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
424 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
425 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
426 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
427 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
428 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
429 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
430 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
431 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
432 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
433 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
434 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
435 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
436 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
437 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
438 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
439 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
440 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
441 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
442 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
443 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
444 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
445 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
446 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
447 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
448 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
449 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
450 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
451 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
452 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
453 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
454 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
455 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
456 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
457 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
458 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
459 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
460 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
461 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
462 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
463 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
464 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
465 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
466 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
467 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
468 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
469 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
470 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
471 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
472 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
473 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
474 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
475 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
476 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
477 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
478 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
479 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
480 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
481 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
482 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
483 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
484 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
485 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
486 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
487 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
488 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
489 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
490 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
491 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
492 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
493 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
494 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
495 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
496 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
497 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
498 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
499 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
500 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
501 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
502 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
503 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
504 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
505 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
506 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
507 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
508 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
509 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
510 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
511 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
512 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
513 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
514 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
515 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
516 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
517 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
518 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
519 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
520 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
521 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
522 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
523 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
524 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
525 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
526 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
527 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
528 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
529 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
530 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
531 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
532 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
533 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
534 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
535 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
536 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
537 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
538 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
539 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
540 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
541 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
542 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
543 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
544 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
545 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
546 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
547 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
548 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
549 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
550 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
551 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
552 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
553 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
554 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
555 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
556 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
557 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
558 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
559 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
560 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
561 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
562 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
563 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
564 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
565 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
566 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
567 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
568 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
569 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
570 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
571 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
572 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
573 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
574 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
575 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
576 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
577 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
578 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
579 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
580 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
581 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
582 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
583 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
584 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
585 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
586 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
587 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
588 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
589 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
590 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
591 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
592 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
593 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
594 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
595 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
596 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
597 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
598 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
599 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
600 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
601 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
602 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
603 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
604 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
605 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
606 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
607 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
608 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
609 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
610 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
611 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
612 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
613 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
614 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
615 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
616 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
617 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
618 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
619 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
620 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
621 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
622 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
623 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
624 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
625 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
626 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
627 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
628 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
629 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
630 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
631 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
632 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
633 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
634 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
635 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
636 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
637 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
638 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
639 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
640 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
641 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
642 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
643 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
644 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
645 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
646 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
647 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
648 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
649 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
650 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
651 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
652 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
653 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
654 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
655 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
656 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
657 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
658 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
659 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
660 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
661 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
662 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
663 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
664 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
665 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
666 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
667 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
668 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
669 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
670 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
671 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
672 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
673 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
674 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
675 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
676 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
677 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
678 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
679 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
680 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
681 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
682 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
683 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
684 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
685 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
686 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
687 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
688 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
689 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
690 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
691 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
692 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
693 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
694 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
695 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
696 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
697 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
698 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
699 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
700 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
701 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
702 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
703 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
704 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
Total | [13 empty] | 13464.05 | 9063.82 | 67.32