## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
2 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
3 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
4 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
5 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
6 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
7 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
8 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
9 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
10 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
11 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
12 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
13 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
14 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
15 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
16 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
17 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
18 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
19 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
20 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
21 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
22 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
23 | ALIPURDUAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
24 | BANKURA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
25 | BIRBHUM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
26 | COOCHBEHAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
27 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
28 | DARJEELING |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
29 | HOOGHLY |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
30 | HOWRAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
31 | JALPAIGURI |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
32 | JHARGRAM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
33 | KALIMPONG |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
34 | MALDAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
35 | MURSHIDABAD |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
36 | NADIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
37 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
38 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
39 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
40 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
41 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
42 | PURULIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
43 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
44 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
45 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
46 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
47 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
48 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
49 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
50 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
51 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
52 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
53 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
54 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
55 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
56 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
57 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
58 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
59 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
60 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
61 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
62 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
63 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
64 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
65 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
66 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
67 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
68 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
69 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
70 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
71 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
72 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
73 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
74 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
75 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
76 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
77 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
78 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
79 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
80 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
81 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
82 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
83 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
84 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
85 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
86 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
87 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
88 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
89 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
90 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
91 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
92 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
93 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
94 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
95 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
96 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
97 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
98 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
99 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
100 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
101 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
102 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
103 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
104 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
105 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
106 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
107 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
108 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
109 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
110 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
111 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
112 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
113 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
114 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
115 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
116 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
117 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
118 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
119 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
120 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
121 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
122 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
123 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
124 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
125 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
126 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
127 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
128 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
129 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
130 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
131 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
132 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
133 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
134 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
135 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
136 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
137 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
138 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
139 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
140 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
141 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
142 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
143 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
144 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
145 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
146 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
147 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
148 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
149 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
150 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
151 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
152 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
153 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
154 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
155 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
156 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
157 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
158 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
159 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
160 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
161 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
162 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
163 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
164 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
165 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
166 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
167 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
168 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
169 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
170 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
171 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
172 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
173 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
174 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
175 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
176 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
177 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
178 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
179 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
180 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
181 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
182 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
183 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
184 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
185 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
186 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
187 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
188 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
189 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
190 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
191 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
192 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
193 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
194 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
195 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
196 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
197 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
198 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
199 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
200 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
201 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
202 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
203 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
204 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
205 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
206 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
207 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
208 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
209 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
210 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
211 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
212 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
213 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
214 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
215 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
216 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
217 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
218 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
219 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
220 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
221 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
222 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
223 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
224 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
225 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
226 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
227 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
228 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
229 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
230 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
231 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
232 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
233 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
234 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
235 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
236 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
237 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
238 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
239 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
240 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
241 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
242 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
243 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
244 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
245 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
246 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
247 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
248 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
249 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
250 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
251 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
252 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
253 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
254 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
255 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
256 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
257 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
258 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
259 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
260 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
261 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
262 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
263 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
264 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
265 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
266 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
267 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
268 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
270 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
271 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
272 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
273 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
274 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
275 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
276 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
277 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
278 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
284 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
287 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
288 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
289 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
290 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
291 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
292 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
293 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
294 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
295 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
296 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
297 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
298 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
299 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
300 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
301 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
302 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
303 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
304 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
305 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
306 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
307 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
308 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
309 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
310 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
311 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
312 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
313 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
314 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
315 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
316 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
317 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
318 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
319 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
320 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
321 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
322 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
323 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
324 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
325 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
326 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
327 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
328 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
329 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
330 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
331 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
332 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
333 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
334 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
335 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
336 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
337 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
338 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
339 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
340 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
341 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
342 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
343 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
344 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
345 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
346 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
347 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
348 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
349 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
350 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
351 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
352 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
353 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
354 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
355 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
356 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
357 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
358 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
359 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
360 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
361 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
362 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
363 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
364 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
365 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
366 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
367 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
368 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
369 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
370 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
371 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
372 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
373 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
374 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
375 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
376 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
377 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
378 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
379 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
380 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
381 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
382 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
383 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
384 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
385 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
386 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
387 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
388 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
389 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
390 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
391 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
392 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
393 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
394 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
395 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
396 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
397 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
398 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
399 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
400 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
401 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
402 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
403 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
404 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
405 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
406 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
407 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
408 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
409 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
410 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
411 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
412 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
413 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
414 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
415 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
416 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
417 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
418 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
419 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
420 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
421 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
422 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
423 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
424 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
425 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
426 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
427 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
428 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
429 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
430 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
431 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
432 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
433 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
434 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
435 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
436 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
437 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
438 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
439 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
440 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
441 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
442 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
443 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
444 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
445 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
446 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
447 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
448 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
449 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
450 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
451 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
452 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
453 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
454 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
455 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
456 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
457 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
458 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
459 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
460 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
461 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
462 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 407-D/PR | 28/06/2024 | 28/09/2024 | MILAN MAHATO | 0.97 | 0 | 0 | 100
463 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
464 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
465 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
466 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
467 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
468 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
469 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
470 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
471 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
472 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
473 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
474 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
475 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
476 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
477 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
478 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
479 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
480 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
481 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
482 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
483 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
484 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 407-B/PR | 28/06/2024 | 28/09/2024 | TAPAN MAHATO | 0.97 | 0 | 0 | 100
485 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
486 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
487 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
488 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
489 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
490 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
491 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
492 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
493 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
494 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
495 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
496 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
497 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
498 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
499 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
500 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
501 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
502 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
503 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
504 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
505 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
506 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
507 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
508 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
509 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
510 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
511 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
512 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
513 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
514 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
515 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
516 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
517 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
518 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
519 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
520 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
521 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
522 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
523 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
524 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
525 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
526 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
527 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
528 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Dubra Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.04.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/004489/2023-2024 | 207/A/PR | 22/03/2024 | 22/06/2024 | UTSAV AGENCY | 0.65 | 0 | 0 | 100
529 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
530 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
531 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
532 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
533 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
534 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
535 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
536 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
537 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
538 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
539 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
540 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
541 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
542 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
543 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
544 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
545 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
546 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
547 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
548 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
549 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
550 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 30 /06/2024) | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 265/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
551 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
552 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
553 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
554 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
555 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
556 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
557 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
558 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
559 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
560 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
561 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
562 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
563 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
564 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
565 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
566 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
567 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
568 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
569 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
570 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
571 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
572 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001428/2024-2025 | 407-A/PR | 28/06/2024 | 28/09/2024 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 100
573 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
574 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
575 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
576 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
577 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
578 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
579 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
580 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
581 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
582 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
583 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
584 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
585 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
586 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
587 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
588 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
589 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
590 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
591 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
592 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
593 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
594 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. (July to Sep 2024) | Assistant Engineer |  | ORD/001430/2024-2025 | 407-C/PR | 28/06/2024 | 28/09/2024 | BABLU MAHATO | 0.97 | 0 | 0 | 100
595 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
596 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
597 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
598 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
599 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
600 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
601 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
602 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
603 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
604 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
605 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
606 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
607 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
608 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
609 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
610 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
611 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
612 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
613 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
614 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
615 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
616 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001425/2024-2025 | 406-B-PR | 28/06/2024 | 28/09/2024 | CHANDAN MONDAL | 0.77 | 0 | 0 | 100
617 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
618 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
619 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
620 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
621 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
622 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
623 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
624 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
625 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
626 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
627 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
628 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
629 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
630 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
631 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
632 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
633 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
634 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
635 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
636 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
637 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
638 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000265/2024-2025 | 407/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
639 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
640 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
641 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
642 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
643 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
644 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
645 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
646 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
647 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
648 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
649 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
650 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
651 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
652 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
653 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
654 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
655 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
656 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
657 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
658 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
659 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
660 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2024 to 30.06.2025) |  | Junior Engineer | ORD/000264/2024-2025 | 406/PR | 28/06/2024 | 28/06/2025 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
661 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
662 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
663 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
664 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
665 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
666 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
667 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
668 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
669 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
670 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
671 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
672 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
673 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
674 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
675 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
676 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
677 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
678 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
679 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
680 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
681 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
682 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
683 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
684 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
685 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
686 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
687 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
688 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
689 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
690 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
691 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
692 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
693 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
694 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
695 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
696 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
697 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
698 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
699 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
700 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
701 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
702 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
703 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
704 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 07/04/2026 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 100
Total | [13 empty] | 13464.05 | 9063.82 | 67.32