## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
2 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
3 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
4 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
6 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
7 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
8 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
9 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
10 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
11 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
12 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
13 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
14 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
15 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
18 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
19 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
20 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
22 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 44 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000175/2022-2023 | 3047/RS | 31/05/2022 | 29/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 288.13 | 288.13 | 100 | 0
23 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
24 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
25 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
26 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
27 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
28 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
29 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
30 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
31 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
32 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
33 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
34 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
35 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
36 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
37 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
38 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
39 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
40 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
41 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
42 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
43 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
44 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
45 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
46 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
47 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
48 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
49 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
50 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
51 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
52 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
53 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
54 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
55 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
56 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
57 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
58 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
59 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
60 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
61 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
62 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
63 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
64 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
65 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
66 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
67 | ALIPURDUAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
68 | BANKURA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
69 | BIRBHUM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
70 | COOCHBEHAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
71 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
72 | DARJEELING |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
73 | HOOGHLY |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
74 | HOWRAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
75 | JALPAIGURI |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
76 | JHARGRAM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
77 | KALIMPONG |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
78 | MALDAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
79 | MURSHIDABAD |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
80 | NADIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
81 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
82 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
83 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
84 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
85 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
86 | PURULIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
87 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
88 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
89 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
90 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
91 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
92 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
93 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
94 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
95 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
96 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
97 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
98 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
99 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
100 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
101 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
102 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
103 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
104 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
105 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
106 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
107 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
108 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
109 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
110 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
111 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
112 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
113 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
114 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
115 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
116 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
117 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
118 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
119 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
120 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
121 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
122 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
123 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
124 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
125 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
126 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
127 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
128 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
129 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
130 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
131 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
132 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
133 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
134 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
135 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
136 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
137 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
138 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
139 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
140 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
141 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
142 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
143 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
144 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
145 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
146 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
147 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
148 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
149 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
150 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
151 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
152 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
153 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
154 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Engagement of consultancy service provider for various documentation along with supply, installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of 12 Sub-district Water Testing Laboratories throughout the State under PHE Department, Govt. of West Bengal |  | Junior Engineer | ORD/000704/2022-2023 | 5631/RS | 20/10/2022 | 18/01/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 78.57 | 78.57 | 100 | 0
155 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
156 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
157 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
158 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
159 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
160 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
161 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
162 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
163 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
164 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
165 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
166 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
167 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
168 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
169 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
170 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
171 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
172 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
173 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
174 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
175 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
176 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
177 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
178 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
179 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
180 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
181 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
182 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
183 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
184 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
185 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
186 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
187 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
188 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
189 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
190 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
191 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
192 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
193 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
194 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
195 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
196 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
197 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
198 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
199 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
200 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
201 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
202 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
203 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
204 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
205 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
206 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
207 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
208 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
209 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
210 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
211 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
212 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
213 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
214 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
215 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
216 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
217 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
218 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
219 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
220 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
221 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
222 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
223 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
224 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
225 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
226 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
227 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
228 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
229 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
230 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
231 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
232 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
233 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
234 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
235 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
236 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
237 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
238 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
239 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
240 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
241 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
242 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0 | 0 | 100
243 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
244 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
245 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
246 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
247 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
248 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
249 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
250 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
251 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
252 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
253 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
254 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
255 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
256 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
257 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
258 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
259 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
260 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
261 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
262 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
263 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
264 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
265 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
266 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
267 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
268 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
269 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
270 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
271 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
272 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
273 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
274 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
275 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
276 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
277 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
278 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
279 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
280 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
281 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
282 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
283 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
284 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
285 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
286 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0 | 0 | 100
287 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
288 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
289 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
290 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
291 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
292 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
293 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
294 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
295 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
296 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
297 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
298 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
299 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
300 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
301 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
302 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
303 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
304 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
305 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
306 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
307 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
308 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 0 | 0 | 50
309 | ALIPURDUAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
310 | BANKURA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
311 | BIRBHUM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
312 | COOCHBEHAR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
313 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
314 | DARJEELING |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
315 | HOOGHLY |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
316 | HOWRAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
317 | JALPAIGURI |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
318 | JHARGRAM |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
319 | KALIMPONG |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
320 | MALDAH |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
321 | MURSHIDABAD |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
322 | NADIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
323 | NORTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
324 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
325 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
326 | PURBA BARDHAMAN |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
327 | PURBA MEDINIPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
328 | PURULIA |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
329 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
330 | UTTAR DINAJPUR |  | Resource | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person supervision of process of continuation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratories of the State of West Bengal under PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 2859/RS | 14/11/2024 | 12/07/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 59.72 | 0 | 0 | 90
331 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
332 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
333 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
334 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
335 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
336 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
337 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
338 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
339 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
340 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
341 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
342 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
343 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
344 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
345 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
346 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
347 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
348 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
349 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
350 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
351 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
352 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
353 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
354 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
355 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
356 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
357 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
358 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
359 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
360 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
361 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
362 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
363 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
364 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
365 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
366 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
367 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
368 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
369 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
370 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
371 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
372 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
373 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
374 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
375 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
376 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
377 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
378 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
379 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
380 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
381 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
382 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
383 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
384 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
385 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
386 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
387 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
388 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
389 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
390 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
391 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
392 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
393 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
394 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
395 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
396 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | Assistant Engineer | Junior Engineer | ORD/001736/2023-2024 | 635/PR | 28/12/2023 | 28/04/2024 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
397 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
398 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
399 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
400 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
401 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
402 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
403 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
404 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
405 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
406 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
407 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
408 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
409 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
410 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
411 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
412 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
413 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
414 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
415 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
416 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
417 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
418 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001764/2023-2024 | 1887/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
419 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
420 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
421 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
422 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
423 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
424 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
425 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
426 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
427 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
428 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
429 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
430 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
431 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
432 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
433 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
434 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
435 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
436 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
437 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
438 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
439 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
440 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus, Ranchi Road under Purulia Division, PHE Dte. (w.e.f.01.01.2024 to 30.06.2024). | Assistant Engineer | Junior Engineer | ORD/001761/2023-2024 | 1888/PD | 29/12/2023 | 29/06/2024 | ARUNALOY SCIENTIFIC HOUSE | 5.62 | 0 | 0 | 100
441 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
442 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
443 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
444 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
445 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
446 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
447 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
448 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
449 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
450 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
451 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
452 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
453 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
454 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
455 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
456 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
457 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
458 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
459 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
460 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
461 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
462 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | Assistant Engineer | Junior Engineer | ORD/004487/2023-2024 | 645/PR | 29/12/2023 | 29/04/2024 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
463 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
464 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
465 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
466 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
467 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
468 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
469 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
470 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
471 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
472 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
473 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
474 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
475 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
476 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
477 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
478 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
479 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
480 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
481 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
482 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
483 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
484 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000192/2024-2025 | 339/JRWS | 20/09/2024 | 05/10/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
485 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
486 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
487 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
488 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
489 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
490 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
491 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
492 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
493 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
494 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
495 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
496 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
497 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
498 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
499 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
500 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
501 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
502 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
503 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
504 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
505 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
506 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 266/A/PR | 26/04/2024 | 26/06/2024 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
Total | [13 empty] | 13212.63 | 8440.44 | 63.88