## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
2 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
3 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
4 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
5 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
6 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
7 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
8 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
9 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
10 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
11 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
12 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
13 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
14 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
15 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
16 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
17 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
18 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
19 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
20 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
21 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
22 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.01 | Assistant Engineer |  | ORD/000584/2022-2023 | 371/PR | 04/08/2022 | 19/08/2022 | MS LAXMI ENTERPRISE | 2.96 | 2.96 | 100 | 0
23 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
24 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
25 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
26 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
27 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
28 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
29 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
30 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
31 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
32 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
33 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
34 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
35 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
36 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
37 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
38 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
39 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
40 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
41 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
42 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
43 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
44 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Jabala Agrani tarun Club under NGO Laboratory under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 95/PR | 11/03/2022 | 09/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 4.85 | 100 | 0
45 | ALIPURDUAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
46 | BANKURA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
47 | BIRBHUM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
48 | COOCHBEHAR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
49 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
50 | DARJEELING |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
51 | HOOGHLY |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
52 | HOWRAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
53 | JALPAIGURI |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
54 | JHARGRAM |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
55 | KALIMPONG |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
56 | MALDAH |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
57 | MURSHIDABAD |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
58 | NADIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
59 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
60 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
61 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
62 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
63 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
64 | PURULIA |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
65 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
66 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Chandrakona Municipality Sub-District Water Testing Laboratory under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000178/2021-2022 | 498/AE/GSD | 30/07/2021 | 30/10/2021 | UTSAV AGENCY | 4.82 | 4.82 | 100 | 100
67 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
68 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
69 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
70 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
71 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
72 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
73 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
74 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
75 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
76 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
77 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
78 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
79 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
80 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
81 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
82 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
83 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
84 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
85 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
86 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
87 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
88 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Renovation of Joypur Sub Distict Laboratoty for NABL Accrediation (Part-A) SL NO.04 | Assistant Engineer |  | ORD/000099/2021-2022 | 307/PR | 05/08/2021 | 01/02/2022 | INJAMAMUL HAQUE MONDAL | 4.83 | 1.91 | 39.59 | 0
89 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
90 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
91 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
92 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
93 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
94 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
95 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
96 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
97 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
98 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
99 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
100 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
101 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
102 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
103 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
104 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
105 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
106 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
107 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
108 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
109 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
110 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply and installation of Instrument related to NABL Recognisation of Sub District Water Testing Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission SL NO.02 | Assistant Engineer |  | ORD/000585/2022-2023 | 372/PR | 04/08/2022 | 19/08/2022 | ARUNALOY SCIENTIFIC HOUSE | 2.41 | 2.41 | 100 | 0
111 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
112 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
113 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
114 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
115 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
116 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
117 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
118 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
119 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
120 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
121 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
122 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
123 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
124 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
125 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
126 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
127 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
128 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
129 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
130 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
131 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
132 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the NGO Managed Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000443/2023-2024 | 414/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
133 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
134 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
135 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
136 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
137 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
138 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
139 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
140 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
141 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
142 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
143 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
144 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
145 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
146 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
147 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
148 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
149 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
150 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
151 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
152 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
153 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
154 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Lalgarh sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000439/2023-2024 | 410/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
155 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
156 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
157 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
158 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
159 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
160 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
161 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
162 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
163 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
164 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
165 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
166 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
167 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
168 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
169 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
170 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
171 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
172 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
173 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
174 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
175 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
176 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Calibration and other chemicals required related to smooth functioning of NGO managed Laboratory, under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000446/2023-2024 | 409/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
177 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
178 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
179 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
180 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
181 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
182 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
183 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
184 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
185 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
186 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
187 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
188 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
189 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
190 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
191 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
192 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
193 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
194 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
195 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
196 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
197 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
198 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Belpahari sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000440/2023-2024 | 411/JRWS | 09/02/2024 | 24/02/2024 | A R CONSTRUCTION | 0.78 | 0.78 | 100 | 100
199 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
200 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
201 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
202 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
203 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
204 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
205 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
206 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
207 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
208 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
209 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
210 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
211 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
212 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
213 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
214 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
215 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
216 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
217 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
218 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
219 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
220 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gidhni sub- Dist.Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000441/2023-2024 | 412/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
221 | ALIPURDUAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
222 | BANKURA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
223 | BIRBHUM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
224 | COOCHBEHAR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
225 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
226 | DARJEELING |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
227 | HOOGHLY |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
228 | HOWRAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
229 | JALPAIGURI |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
230 | JHARGRAM |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
231 | KALIMPONG |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
232 | MALDAH |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
233 | MURSHIDABAD |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
234 | NADIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
235 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
236 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
237 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
238 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
239 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
240 | PURULIA |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
241 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
242 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Procurement of Chemicals & Consumables, Glassware, Plasticware etc. required for smooth running of the Gopiballavpur sub- Dist Laboratories for the year 2023- 2024 in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000447/2023-2024 | 413/JRWS | 09/02/2024 | 24/02/2024 | UTSAV AGENCY | 0.92 | 0.92 | 100 | 100
243 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
244 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
245 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
246 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
247 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
248 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
249 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
250 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
251 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
252 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
253 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
254 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
255 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
256 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
257 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
258 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
259 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
260 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
261 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
262 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
263 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
264 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of 17 nos laboratories Bagmundi Sub-District Laboratory, Jhalda Water Treatment Plant Sub-District Laboratory, Jhalda-1 Sub- District Laboratory, Sirkabad Sub-District Laboratory, Balarampur Water Treatment Plant Sub- District Laboratory, Barabazar Sub-District Laboratory, Hura Sub-District Laboratory,, Raghunathpur Water Treatment Plant Sub-District Laboratory, Kashipur Sub-District Laboratory, Raghunathpur Sub-District Laboratory, Bundwan Sub-District Laboratory, Manbazar-II Sub-District Laboratory, Joypur Sub-District Laboratory, Purulia District Laboratory, Cheliyama Sub- District Laboratory, Santuri Sub-District Laboratory, Dubra Sub-District Laboratory of RWS Purulia Sub-Division under Purulia Division, PHE Dte. (For 12 months) and will be supplied (50%, 30% & 20%) in three phase as per instruction of EIC. | Assistant Engineer | Junior Engineer | ORD/001128/2024-2025 | 25/PD | 07/01/2025 | 06/02/2025 | UTSAV AGENCY | 134.35 | 23.07 | 17.17 | 50
265 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
266 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
267 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
268 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
270 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
271 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
272 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
273 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
274 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
275 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
276 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
277 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
278 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
284 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Purulia-I block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) |  | Junior Engineer | ORD/001433/2024-2025 | 407-F/PR | 28/06/2024 | 28/09/2024 | SUBAL MAHATO | 0.97 | 0 | 0 | 0
287 | ALIPURDUAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
288 | BANKURA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
289 | BIRBHUM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
290 | COOCHBEHAR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
291 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
292 | DARJEELING |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
293 | HOOGHLY |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
294 | HOWRAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
295 | JALPAIGURI |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
296 | JHARGRAM |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
297 | KALIMPONG |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
298 | MALDAH |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
299 | MURSHIDABAD |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
300 | NADIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
301 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
302 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
303 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
304 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
305 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
306 | PURULIA |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
307 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
308 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & goods in connection with NABL Recognition of 76 Sub District Laboratories Jointly Managed by PHED & various NGOs related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/10761 | Support-WQMSP | Continuation work order for Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( July to Sep 2024) | Assistant Engineer | Junior Engineer | ORD/001424/2024-2025 | 406-A/PR | 28/06/2024 | 28/09/2024 | DIPAK MANDAL | 0.96 | 0 | 0 | 100
Total | [13 empty] | 3551.41 | 996.5 | 28.06