## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
2 | BANKURA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
3 | BIRBHUM |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
4 | COOCHBEHAR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
6 | DARJEELING |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
7 | HOOGHLY |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
8 | HOWRAH |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
9 | JALPAIGURI |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
10 | JHARGRAM |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
11 | KALIMPONG |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
12 | MALDAH |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
13 | MURSHIDABAD |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
14 | NADIA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
15 | NORTH 24 PARGANAS |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
18 | PURBA BARDHAMAN |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
19 | PURBA MEDINIPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
20 | PURULIA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
22 | UTTAR DINAJPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department |  | Junior Engineer | ORD/000174/2022-2023 | 3019/RS | 30/05/2022 | 30/05/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 47.35 | 36.75 | 77.61 | 0
23 | ALIPURDUAR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
24 | BANKURA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
25 | BIRBHUM |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
26 | COOCHBEHAR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
27 | DAKSHIN DINAJPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
28 | DARJEELING |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
29 | HOOGHLY |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
30 | HOWRAH |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
31 | JALPAIGURI |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
32 | JHARGRAM |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
33 | KALIMPONG |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
34 | MALDAH |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
35 | MURSHIDABAD |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
36 | NADIA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
37 | NORTH 24 PARGANAS |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
38 | PASCHIM BARDHAMAN |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
39 | PASCHIM MEDINIPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
40 | PURBA BARDHAMAN |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
41 | PURBA MEDINIPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
42 | PURULIA |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
43 | SOUTH 24 PARGANAS |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
44 | UTTAR DINAJPUR |  | Resource | Operation, Maintenance, Upgradation and Management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water quality Dashboard related to Water Quality Monitoring & Surveillance Programme under Jal Jeeva | SM/10763 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
Total | [13 empty] | 1976.81 | 808.45 | 40.9