## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
2 | BANKURA |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
3 | BIRBHUM |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
4 | COOCHBEHAR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
5 | DAKSHIN DINAJPUR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
6 | DARJEELING |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
7 | HOOGHLY |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
8 | HOWRAH |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
9 | JALPAIGURI |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
10 | JHARGRAM |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
11 | KALIMPONG |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
12 | MALDAH |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
13 | MURSHIDABAD |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
14 | NADIA |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
15 | NORTH 24 PARGANAS |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
16 | PASCHIM BARDHAMAN |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
17 | PASCHIM MEDINIPUR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
18 | PURBA BARDHAMAN |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
19 | PURBA MEDINIPUR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
20 | PURULIA |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
21 | SOUTH 24 PARGANAS |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
22 | UTTAR DINAJPUR |  | Resource | Procurement of Digital Residual Chlorine Kit for Monitoring of Piped Water Supply Schemes Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/11209 | Support-WQMSP | Procurement of Digital smart Onsite Residual Chlorine Kit compatible with Smart UI based mobile application for transfer of data without human intervention through wireless networks for online Data transfer including water quality results from field to existing State Water Quality Dashboard for better Water Quality monitoring & surveillance of Piped Water Supply Schemes and Capacity building of resource personnel for the operation, maintenance and data transfer using the same |  | Junior Engineer | ORD/000672/2022-2023 | 4802/RS | 26/08/2022 | 26/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 61.84 | 60.72 | 98.19 | 97
Total | [13 empty] | 1360.52 | 1335.94 | 98.19