## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
2 | BANKURA |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
3 | BIRBHUM |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
4 | COOCHBEHAR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
6 | DARJEELING |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
7 | HOOGHLY |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
8 | HOWRAH |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
9 | JALPAIGURI |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
10 | JHARGRAM |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
11 | KALIMPONG |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
12 | MALDAH |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
13 | MURSHIDABAD |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
14 | NADIA |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
15 | NORTH 24 PARGANAS |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
18 | PURBA BARDHAMAN |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
19 | PURBA MEDINIPUR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
20 | PURULIA |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
22 | UTTAR DINAJPUR |  | Resource | Designing & layout preparation of various kinds of maps related to Drinking water supply coverage t District / Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking | SM/12348 | Support-MIS | Designing & layout preparation of various kinds of maps related to Drinking Water Supply coverage at District/ Block/ Scheme level, various water quality parameters using available disease outbreak data correlating with bacteriological quality of drinking water sources, preparation of thematic maps throughout the state in both Raster and Vector formats along with hosting in the existing Web GIS platform of official website of PHED Dept. Govt. of West Bengal |  | Junior Engineer | ORD/000733/2022-2023 | 5744/RS | 07/11/2022 | 07/11/2023 | HORIZEN | 93.92 | 93.77 | 99.84 | 0
Total | [13 empty] | 2066.34 | 2062.97 | 99.84