## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
2 | BANKURA |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
3 | BIRBHUM |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
4 | COOCHBEHAR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
5 | DAKSHIN DINAJPUR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
6 | DARJEELING |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
7 | HOOGHLY |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
8 | HOWRAH |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
9 | JALPAIGURI |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
10 | JHARGRAM |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
11 | KALIMPONG |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
12 | MALDAH |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
13 | MURSHIDABAD |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
14 | NADIA |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
15 | NORTH 24 PARGANAS |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
16 | PASCHIM BARDHAMAN |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
17 | PASCHIM MEDINIPUR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
18 | PURBA BARDHAMAN |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
19 | PURBA MEDINIPUR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
20 | PURULIA |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
21 | SOUTH 24 PARGANAS |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
22 | UTTAR DINAJPUR |  | Resource | Design and Development of an Integrated Monitoring System on Chlorine consumption in the Head work/Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supe | SM/12678 | Support-WQMSP | Design and Development of an Integrated Monitoring System focusing on Chlorine consumption in the Head work/ Tube well sites of various Piped Water Supply Schemes with other relevant developmental indicators for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000751/2022-2023 | 6410/RS | 23/12/2022 | 23/12/2023 | HORIZEN | 74.29 | 59.91 | 80.65 | 90
Total | [13 empty] | 1634.29 | 1317.98 | 80.65