## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
2 | BANKURA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
3 | BIRBHUM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
4 | COOCHBEHAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
5 | DAKSHIN DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
6 | DARJEELING |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
7 | HOOGHLY |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
8 | HOWRAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
9 | JALPAIGURI |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
10 | JHARGRAM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
11 | KALIMPONG |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
12 | MALDAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
13 | MURSHIDABAD |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
14 | NADIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
15 | NORTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
16 | PASCHIM BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
17 | PASCHIM MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
18 | PURBA BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
19 | PURBA MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
20 | PURULIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
21 | SOUTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
22 | UTTAR DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West Bengal |  |  | ORD/000795/2022-2023 | 416/RS | 31/01/2023 | 31/01/2024 | HORIZEN | 83.55 | 9.13 | 10.93 | 11
23 | ALIPURDUAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
24 | BANKURA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
25 | BIRBHUM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
26 | COOCHBEHAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
27 | DAKSHIN DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
28 | DARJEELING |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
29 | HOOGHLY |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
30 | HOWRAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
31 | JALPAIGURI |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
32 | JHARGRAM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
33 | KALIMPONG |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
34 | MALDAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
35 | MURSHIDABAD |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
36 | NADIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
37 | NORTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
38 | PASCHIM BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
39 | PASCHIM MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
40 | PURBA BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
41 | PURBA MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
42 | PURULIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
43 | SOUTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
44 | UTTAR DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 44.38 | 83.66 | 35
45 | ALIPURDUAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
46 | BANKURA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
47 | BIRBHUM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
48 | COOCHBEHAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
49 | DAKSHIN DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
50 | DARJEELING |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
51 | HOOGHLY |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
52 | HOWRAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
53 | JALPAIGURI |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
54 | JHARGRAM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
55 | KALIMPONG |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
56 | MALDAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
57 | MURSHIDABAD |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
58 | NADIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
59 | NORTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
60 | PASCHIM BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
61 | PASCHIM MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
62 | PURBA BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
63 | PURBA MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
64 | PURULIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
65 | SOUTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
66 | UTTAR DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Comprehensive Proposal for Digital Transformation and Monitoring of Mega Schemes under PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 452/RS | 28/02/2025 | 28/02/2026 | HORIZEN | 70.1 | 0 | 0 | 18
67 | ALIPURDUAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
68 | BANKURA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
69 | BIRBHUM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
70 | COOCHBEHAR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
71 | DAKSHIN DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
72 | DARJEELING |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
73 | HOOGHLY |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
74 | HOWRAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
75 | JALPAIGURI |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
76 | JHARGRAM |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
77 | KALIMPONG |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
78 | MALDAH |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
79 | MURSHIDABAD |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
80 | NADIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
81 | NORTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
82 | PASCHIM BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
83 | PASCHIM MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
84 | PURBA BARDHAMAN |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
85 | PURBA MEDINIPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
86 | PURULIA |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
87 | SOUTH 24 PARGANAS |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
88 | UTTAR DINAJPUR |  | Resource | Design and Development of a Separate Module on Water Quality in WB-JJM Dashboards under Login and Public View encompassing all sorts of relevant information for establishing a Decision Support System under the supervision of PHE Department, Govt. of West | SM/13483 | Support-MIS | Upkeepment and Management of WB-JJM Applications and Dashboards through suitable Data Integration, Visualization and Customized Data Analysis | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 303/RS | 06/02/2025 | 09/04/2025 | HORIZEN | 36.59 | 31.01 | 84.75 | 85
Total | [13 empty] | 5352.51 | 1859.49 | 34.74