## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
2 | BANKURA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
3 | BIRBHUM |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
4 | COOCHBEHAR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
6 | DARJEELING |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
7 | HOOGHLY |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
8 | HOWRAH |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
9 | JALPAIGURI |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
10 | JHARGRAM |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
11 | KALIMPONG |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
12 | MALDAH |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
14 | NADIA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
20 | PURULIA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Transfer of Fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK), OCTOBER 2023 |  |  | BILL/00834/2023-2024 | 341-MSD/23-24 | 17/10/2023 | 17/10/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20.86 | 0 | 0 | 0
23 | ALIPURDUAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
24 | BANKURA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
25 | BIRBHUM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
26 | COOCHBEHAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
27 | DAKSHIN DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
28 | DARJEELING |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
29 | HOOGHLY |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
30 | HOWRAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
31 | JALPAIGURI |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
32 | JHARGRAM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
33 | KALIMPONG |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
34 | MALDAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
35 | MURSHIDABAD |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
36 | NADIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
39 | PASCHIM MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
42 | PURULIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
44 | UTTAR DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION EDUCATION & COMMUNICATION |  |  | BILL/01039/2023-2024 |  | 13/12/2023 | 13/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
45 | ALIPURDUAR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
46 | BANKURA |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
47 | BIRBHUM |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
48 | COOCHBEHAR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
50 | DARJEELING |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
51 | HOOGHLY |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
52 | HOWRAH |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
53 | JALPAIGURI |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
54 | JHARGRAM |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
55 | KALIMPONG |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
56 | MALDAH |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
57 | MURSHIDABAD |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
58 | NADIA |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
64 | PURULIA |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | Bankura Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Implementation of mass awareness generation and sensitization program at various of the district |  |  | BILL/02247/2023-2024 | FHTC/11 | 23/11/2023 | 23/11/2023 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 44 | 0 | 0 | 0
67 | ALIPURDUAR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
68 | BANKURA |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
69 | BIRBHUM |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
70 | COOCHBEHAR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
71 | DAKSHIN DINAJPUR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
72 | DARJEELING |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
73 | HOOGHLY |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
74 | HOWRAH |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
75 | JALPAIGURI |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
76 | JHARGRAM |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
77 | KALIMPONG |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
78 | MALDAH |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
79 | MURSHIDABAD |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
80 | NADIA |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
81 | NORTH 24 PARGANAS |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
82 | PASCHIM BARDHAMAN |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
83 | PASCHIM MEDINIPUR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
84 | PURBA BARDHAMAN |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
85 | PURBA MEDINIPUR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
86 | PURULIA |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
87 | SOUTH 24 PARGANAS |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
88 | UTTAR DINAJPUR |  | Birbhum Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities |  |  | BILL/00470/2023-2024 | BP-2023-24-233 | 18/10/2023 | 18/10/2023 | BZP TOTAL SANITATION CAMPAIGNTANCAL | 38 | 0 | 0 | 0
89 | ALIPURDUAR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
90 | BANKURA |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
91 | BIRBHUM |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
92 | COOCHBEHAR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
93 | DAKSHIN DINAJPUR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
94 | DARJEELING |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
95 | HOOGHLY |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
96 | HOWRAH |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
97 | JALPAIGURI |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
98 | JHARGRAM |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
99 | KALIMPONG |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
100 | MALDAH |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
101 | MURSHIDABAD |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
102 | NADIA |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
103 | NORTH 24 PARGANAS |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
104 | PASCHIM BARDHAMAN |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
105 | PASCHIM MEDINIPUR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
106 | PURBA BARDHAMAN |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
107 | PURBA MEDINIPUR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
108 | PURULIA |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
109 | SOUTH 24 PARGANAS |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
110 | UTTAR DINAJPUR |  | Balurghat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme (WQMSP). |  |  | BILL/00277/2023-2024 | BP-2023-24-161 | 13/10/2023 | 13/10/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 16 | 0 | 0 | 0
111 | ALIPURDUAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
112 | BANKURA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
113 | BIRBHUM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
114 | COOCHBEHAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
115 | DAKSHIN DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
116 | DARJEELING |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
117 | HOOGHLY |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
118 | HOWRAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
119 | JALPAIGURI |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
120 | JHARGRAM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
121 | KALIMPONG |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
122 | MALDAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
123 | MURSHIDABAD |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
124 | NADIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
125 | NORTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
126 | PASCHIM BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
128 | PURBA BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
129 | PURBA MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
130 | PURULIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
131 | SOUTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
132 | UTTAR DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | BILL FOR INFORMATION , EDUCATION & COMMUNICATION |  |  | BILL/01040/2023-2024 | 433/PFMS | 14/12/2023 | 14/12/2023 | SECRETARY, NADIA ZILLA PARISHAD | 36 | 0 | 0 | 0
133 | ALIPURDUAR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
134 | BANKURA |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
135 | BIRBHUM |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
136 | COOCHBEHAR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
137 | DAKSHIN DINAJPUR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
138 | DARJEELING |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
139 | HOOGHLY |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
140 | HOWRAH |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
141 | JALPAIGURI |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
142 | JHARGRAM |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
143 | KALIMPONG |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
144 | MALDAH |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
145 | MURSHIDABAD |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
146 | NADIA |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
147 | NORTH 24 PARGANAS |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
148 | PASCHIM BARDHAMAN |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
149 | PASCHIM MEDINIPUR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
150 | PURBA BARDHAMAN |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
151 | PURBA MEDINIPUR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
152 | PURULIA |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
153 | SOUTH 24 PARGANAS |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
154 | UTTAR DINAJPUR |  | Burdwan Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC Activities of JJM. |  |  | BILL/01123/2023-2024 | 1075/JJM | 14/12/2023 | 14/12/2023 | PURBA BARDHAMAN ZILLA PARISHAD | 46 | 0 | 0 | 0
155 | ALIPURDUAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
156 | BANKURA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
157 | BIRBHUM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
158 | COOCHBEHAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
159 | DAKSHIN DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
160 | DARJEELING |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
161 | HOOGHLY |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
162 | HOWRAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
163 | JALPAIGURI |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
164 | JHARGRAM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
165 | KALIMPONG |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
166 | MALDAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
167 | MURSHIDABAD |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
168 | NADIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
169 | NORTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
170 | PASCHIM BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
171 | PASCHIM MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
172 | PURBA BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
173 | PURBA MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
174 | PURULIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
175 | SOUTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
176 | UTTAR DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Allotment of funds towards IEC Activities |  |  | BILL/00805/2023-2024 | BP-2023-24-457 | 03/11/2023 | 03/11/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 28 | 0 | 0 | 0
177 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
178 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
179 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
180 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
181 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
182 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
183 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
184 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
185 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
186 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
187 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
188 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
189 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
190 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
191 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
192 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
193 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
194 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
195 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
196 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
197 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
198 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Gosaba and Canning -I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000522/2024-2025 | 2749/AD | 26/06/2024 | 26/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.55 | 0 | 0 | 0
199 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
200 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
201 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
202 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
203 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
204 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
205 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
206 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
207 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
208 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
209 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
210 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
211 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
212 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
213 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
214 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
215 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
216 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
217 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
218 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
219 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
220 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Basanti and Canning -II block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000523/2024-2025 | 2792/AD | 01/07/2024 | 31/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
221 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
222 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
223 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
224 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
225 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
226 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
227 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
228 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
229 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
230 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
231 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
232 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
233 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
234 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
235 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
236 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
237 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
238 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
239 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
240 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
241 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
242 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Jamboni Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000165/2024-2025 | 163/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
243 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
244 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
245 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
246 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
247 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
248 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
249 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
250 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
251 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
252 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
253 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
254 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
255 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
256 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
257 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
258 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
259 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
260 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
261 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
262 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
263 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
264 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000167/2024-2025 | 165/JRWS | 27/06/2024 | 27/07/2024 | S.R. ENTERPRISE | 0.98 | 0 | 0 | 0
265 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
266 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
267 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
268 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
269 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
270 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
271 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
272 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
273 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
274 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
275 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
276 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
277 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
278 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
279 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
280 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
281 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
282 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
283 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
284 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
285 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
286 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Jhargram Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000163/2024-2025 | 161/JRWS | 27/06/2024 | 27/07/2024 | SUJOY RANJAN BHOWMICK | 0.98 | 0 | 0 | 0
287 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
288 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
289 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
290 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
291 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
292 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
293 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
294 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
295 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
296 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
297 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
298 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
299 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
300 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
301 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
302 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
303 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
304 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
305 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
306 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
307 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
308 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sagar and Kakdwip block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000520/2024-2025 | 2737/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.24 | 0 | 0 | 0
309 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
310 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
311 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
312 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
313 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
314 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
315 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
316 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
317 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
318 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
319 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
320 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
321 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
322 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
323 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
324 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
325 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
326 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
327 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
328 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
329 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
330 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Patharpratima and Namkhana block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000521/2024-2025 | 2738/AD | 25/06/2024 | 25/07/2024 | HALDAH EASTERN DEVELOPMENT SOCIETY | 3.4 | 0 | 0 | 0
331 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
332 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
333 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
334 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
335 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
336 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
337 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
338 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
339 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
340 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
341 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
342 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
343 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
344 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
345 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
346 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
347 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
348 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
349 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
350 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
351 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
352 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Sankrail Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000166/2024-2025 | 164/JRWS | 27/06/2024 | 27/07/2024 | ENVOTECH INFRA SOLUTION | 0.98 | 0 | 0 | 0
353 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
354 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
355 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
356 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
357 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
358 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
359 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
360 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
361 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
362 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
363 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
364 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
365 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
366 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
367 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
368 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
369 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
370 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
371 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
372 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
373 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
374 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Nayagram Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000164/2024-2025 | 162/JRWS | 27/06/2024 | 27/07/2024 | MAHAVIR SAMPARK PVT. LTD. | 0.98 | 0 | 0 | 0
375 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
376 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
377 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
378 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
379 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
380 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
381 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
382 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
383 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
384 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
385 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
386 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
387 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
388 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
389 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
390 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
391 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
392 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
393 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
394 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
395 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
396 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Gopiballavpur-I Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000168/2024-2025 | 166/JRWS | 27/06/2024 | 27/07/2024 | JAY BABA LOKNATH ENTERPRISE | 0.98 | 0 | 0 | 0
397 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
398 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
399 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
400 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
401 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
402 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
403 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
404 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
405 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
406 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
407 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
408 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
409 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
410 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
411 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
412 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
413 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
414 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
415 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
416 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
417 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
418 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation Binpur-II Block (for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000169/2024-2025 | 171/JRWS | 28/06/2024 | 28/07/2024 | NARGISH ENTERPRISE | 0.98 | 0 | 0 | 0
419 | ALIPURDUAR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
420 | BANKURA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
421 | BIRBHUM |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
422 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
423 | DAKSHIN DINAJPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
424 | DARJEELING |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
425 | HOOGHLY |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
426 | HOWRAH |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
427 | JALPAIGURI |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
428 | JHARGRAM |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
429 | KALIMPONG |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
430 | MALDAH |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
431 | MURSHIDABAD |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
432 | NADIA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
433 | NORTH 24 PARGANAS |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
434 | PASCHIM BARDHAMAN |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
435 | PASCHIM MEDINIPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
436 | PURBA BARDHAMAN |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
437 | PURBA MEDINIPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
438 | PURULIA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
439 | SOUTH 24 PARGANAS |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
440 | UTTAR DINAJPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Providing necessary logistic support and all other necessary arrangements required for 2O DAYS RASH MELA 2022 in co ordination with SWSM | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000407/2022-2023 | 1160/CD | 07/11/2022 | 27/11/2022 | BIJOY ROY | 6.25 | 1.65 | 26.42 | 100
441 | ALIPURDUAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
442 | BANKURA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
443 | BIRBHUM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
444 | COOCHBEHAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
445 | DAKSHIN DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
446 | DARJEELING |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
447 | HOOGHLY |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
448 | HOWRAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
449 | JALPAIGURI |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
450 | JHARGRAM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
451 | KALIMPONG |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
452 | MALDAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
453 | MURSHIDABAD |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
454 | NADIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
455 | NORTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
456 | PASCHIM BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
457 | PASCHIM MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
458 | PURBA BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
459 | PURBA MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
460 | PURULIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
461 | SOUTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
462 | UTTAR DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-B) | AE HQ |  | ORD/000225/2023-2024 | 2802/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.61 | 100
463 | ALIPURDUAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
464 | BANKURA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
465 | BIRBHUM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
466 | COOCHBEHAR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
467 | DAKSHIN DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
468 | DARJEELING |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
469 | HOOGHLY |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
470 | HOWRAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
471 | JALPAIGURI |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
472 | JHARGRAM |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
473 | KALIMPONG |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
474 | MALDAH |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
475 | MURSHIDABAD |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
476 | NADIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
477 | NORTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
478 | PASCHIM BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
479 | PASCHIM MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
480 | PURBA BARDHAMAN |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
481 | PURBA MEDINIPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
482 | PURULIA |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
483 | SOUTH 24 PARGANAS |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
484 | UTTAR DINAJPUR |  | Howrah Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-A) | AE HQ |  | ORD/000224/2023-2024 | 2801/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.96 | 99.74 | 100
485 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
486 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
487 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
488 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
489 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
490 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
491 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
492 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
493 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
494 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
495 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
496 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
497 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
498 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
499 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
500 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
501 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
502 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
503 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
504 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
505 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
506 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00210/2024-2025 | BP-2024-25-146 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
507 | ALIPURDUAR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
508 | BANKURA |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
509 | BIRBHUM |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
510 | COOCHBEHAR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
511 | DAKSHIN DINAJPUR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
512 | DARJEELING |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
513 | HOOGHLY |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
514 | HOWRAH |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
515 | JALPAIGURI |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
516 | JHARGRAM |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
517 | KALIMPONG |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
518 | MALDAH |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
519 | MURSHIDABAD |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
520 | NADIA |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
521 | NORTH 24 PARGANAS |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
522 | PASCHIM BARDHAMAN |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
523 | PASCHIM MEDINIPUR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
524 | PURBA BARDHAMAN |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
525 | PURBA MEDINIPUR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
526 | PURULIA |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
527 | SOUTH 24 PARGANAS |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
528 | UTTAR DINAJPUR |  | Siliguri W/S Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Commucion (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal Jeevan Mission (JJM) Water Quality Monitoring and Survillance Programme (WQMSP) |  |  | BILL/00508/2023-2024 | BP-2023-24-168 | 16/02/2024 | 16/02/2024 | DISTRICT MAGISTRATE, DARJEELING | 18 | 0 | 0 | 0
529 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
530 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
531 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
532 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
533 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
534 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
535 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
536 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
537 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
538 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
539 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
540 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
541 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
542 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
543 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
544 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
545 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
546 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
547 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
548 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
549 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
550 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | SUPPORT ACTIVITY FUND FOR IEC ACTIVITY |  |  | BILL/01204/2023-2024 | BP-2023-24-327 | 08/03/2024 | 08/03/2024 | JAL SHAKTI ABHIYAN | 18 | 0 | 0 | 0
551 | ALIPURDUAR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
552 | BANKURA |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
553 | BIRBHUM |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
554 | COOCHBEHAR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
555 | DAKSHIN DINAJPUR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
556 | DARJEELING |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
557 | HOOGHLY |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
558 | HOWRAH |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
559 | JALPAIGURI |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
560 | JHARGRAM |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
561 | KALIMPONG |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
562 | MALDAH |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
563 | MURSHIDABAD |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
564 | NADIA |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
565 | NORTH 24 PARGANAS |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
566 | PASCHIM BARDHAMAN |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
567 | PASCHIM MEDINIPUR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
568 | PURBA BARDHAMAN |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
569 | PURBA MEDINIPUR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
570 | PURULIA |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
571 | SOUTH 24 PARGANAS |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
572 | UTTAR DINAJPUR |  | Tamluk Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme |  |  | BILL/00956/2024-2025 | BP-2024-25-403 | 13/09/2024 | 13/09/2024 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 50 | 0 | 0 | 0
573 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
574 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
575 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
576 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
577 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
578 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
579 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
580 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
581 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
582 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
583 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
584 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
585 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
586 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
587 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
588 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
589 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
590 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
591 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
592 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
593 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
594 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00212/2024-2025 | BP-2024-25-147 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.04 | 0 | 0 | 0
595 | ALIPURDUAR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
596 | BANKURA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
597 | BIRBHUM |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
598 | COOCHBEHAR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
599 | DAKSHIN DINAJPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
600 | DARJEELING |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
601 | HOOGHLY |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
602 | HOWRAH |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
603 | JALPAIGURI |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
604 | JHARGRAM |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
605 | KALIMPONG |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
606 | MALDAH |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
607 | MURSHIDABAD |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
608 | NADIA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
609 | NORTH 24 PARGANAS |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
610 | PASCHIM BARDHAMAN |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
611 | PASCHIM MEDINIPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
612 | PURBA BARDHAMAN |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
613 | PURBA MEDINIPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
614 | PURULIA |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
615 | SOUTH 24 PARGANAS |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
616 | UTTAR DINAJPUR |  | Coochbehar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Development fund committee |  |  | BILL/02095/2023-2024 | BP-1401 | 31/03/2024 | 31/03/2024 | DEVELOPMENT FUND | 24 | 0 | 0 | 0
617 | ALIPURDUAR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
618 | BANKURA |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
619 | BIRBHUM |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
620 | COOCHBEHAR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
621 | DAKSHIN DINAJPUR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
622 | DARJEELING |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
623 | HOOGHLY |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
624 | HOWRAH |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
625 | JALPAIGURI |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
626 | JHARGRAM |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
627 | KALIMPONG |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
628 | MALDAH |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
629 | MURSHIDABAD |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
630 | NADIA |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
631 | NORTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
632 | PASCHIM BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
633 | PASCHIM MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
634 | PURBA BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
635 | PURBA MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
636 | PURULIA |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
637 | SOUTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
638 | UTTAR DINAJPUR |  | Barasat Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Executive Engineer, Barasat Division, PHE. Dte. Vide Memo No.-19918 -19951/WORKS/MISC/000006/2021, Date-10-10-2023 Chief Engineer (HQ) transfer of fund for IEC Activity under Jal Jeevan Mission Programme in favour of North 24Pgs. |  |  | BILL/03871/2023-2024 | BP-2023-24-774 | 19/03/2024 | 19/03/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 44 | 0 | 0 | 0
639 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
640 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
641 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
642 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
643 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
644 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
645 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
646 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
647 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
648 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
649 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
650 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
651 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
652 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
653 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
654 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
655 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
656 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
657 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
658 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
659 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
660 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) |  |  | BILL/00976/2023-2024 | BP-2023-24-247 | 10/10/2023 | 10/10/2023 | PGE 2018 DM AND DPEO JHARGRAM | 16 | 0 | 0 | 0
661 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
662 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
663 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
664 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
665 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
666 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
667 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
668 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
669 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
670 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
671 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
672 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
673 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
674 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
675 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
676 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
677 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
678 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
679 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
680 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
681 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
682 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00214/2024-2025 | BP-2024-25-141 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
683 | ALIPURDUAR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
684 | BANKURA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
685 | BIRBHUM |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
686 | COOCHBEHAR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
687 | DAKSHIN DINAJPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
688 | DARJEELING |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
689 | HOOGHLY |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
690 | HOWRAH |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
691 | JALPAIGURI |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
692 | JHARGRAM |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
693 | KALIMPONG |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
694 | MALDAH |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
695 | MURSHIDABAD |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
696 | NADIA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
697 | NORTH 24 PARGANAS |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
698 | PASCHIM BARDHAMAN |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
699 | PASCHIM MEDINIPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
700 | PURBA BARDHAMAN |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
701 | PURBA MEDINIPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
702 | PURULIA |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
703 | SOUTH 24 PARGANAS |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
704 | UTTAR DINAJPUR |  | Murshidabad Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | TRANSFER OF FUND FOR ASHA IN CONNECTION WITH WQ TESTING OF DRINKING WATER SAMPLE USING FTK |  |  | BILL/00705/2024-2025 | 249-MSD/2024-25 | 29/07/2024 | 29/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 31.14 | 0 | 0 | 0
705 | ALIPURDUAR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
706 | BANKURA |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
707 | BIRBHUM |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
708 | COOCHBEHAR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
709 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
710 | DARJEELING |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
711 | HOOGHLY |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
712 | HOWRAH |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
713 | JALPAIGURI |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
714 | JHARGRAM |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
715 | KALIMPONG |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
716 | MALDAH |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
717 | MURSHIDABAD |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
718 | NADIA |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
719 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
720 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
721 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
722 | PURBA BARDHAMAN |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
723 | PURBA MEDINIPUR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
724 | PURULIA |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
725 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
726 | UTTAR DINAJPUR |  | Jalpaiguri Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | payment to CMOH(ASHA) |  |  | BILL/01191/2023-2024 | BP-2023-24-601 | 16/01/2024 | 16/01/2024 | FC &CAO JALPAIGURI ZILLA PARISHAD | 18 | 0 | 0 | 0
727 | ALIPURDUAR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
728 | BANKURA |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
729 | BIRBHUM |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
730 | COOCHBEHAR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
731 | DAKSHIN DINAJPUR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
732 | DARJEELING |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
733 | HOOGHLY |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
734 | HOWRAH |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
735 | JALPAIGURI |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
736 | JHARGRAM |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
737 | KALIMPONG |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
738 | MALDAH |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
739 | MURSHIDABAD |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
740 | NADIA |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
741 | NORTH 24 PARGANAS |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
742 | PASCHIM BARDHAMAN |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
743 | PASCHIM MEDINIPUR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
744 | PURBA BARDHAMAN |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
745 | PURBA MEDINIPUR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
746 | PURULIA |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
747 | SOUTH 24 PARGANAS |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
748 | UTTAR DINAJPUR |  | Purulia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Funds towards IEC activities. |  |  | BILL/00387/2024-2025 | BP-2024-25-192 | 23/06/2024 | 23/06/2024 | DISTRICT MAGISTRATE | 40 | 0 | 0 | 0
749 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
750 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
751 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
752 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
753 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
754 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
755 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
756 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
757 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
758 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
759 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
760 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
761 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
762 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
763 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
764 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
765 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
766 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
767 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
768 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
769 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
770 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Karnajora PHE office premises on 20.02.2024 |  |  | BILL/00211/2024-2025 | BP-2024-25-148 | 26/07/2024 | 26/07/2024 | SANDIP SARKAR | 0.09 | 0 | 0 | 0
771 | ALIPURDUAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
772 | BANKURA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
773 | BIRBHUM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
774 | COOCHBEHAR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
775 | DAKSHIN DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
776 | DARJEELING |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
777 | HOOGHLY |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
778 | HOWRAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
779 | JALPAIGURI |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
780 | JHARGRAM |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
781 | KALIMPONG |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
782 | MALDAH |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
783 | MURSHIDABAD |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
784 | NADIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
785 | NORTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
786 | PASCHIM BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
787 | PASCHIM MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
788 | PURBA BARDHAMAN |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
789 | PURBA MEDINIPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
790 | PURULIA |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
791 | SOUTH 24 PARGANAS |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
792 | UTTAR DINAJPUR |  | Raiganj Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Arrangement of refreshment for participants for the training program of valve/IEP operators under Raiganj Division and pump operators under Malda Mechanical Division PHE Dte. at Itahar Sub District Lab premises on 20.02.2024 |  |  | BILL/00213/2024-2025 | BP-2024-25-140 | 26/07/2024 | 26/07/2024 | SUBHASIS MAJUMDER | 0.06 | 0 | 0 | 0
793 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
794 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
795 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
796 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
797 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
798 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
799 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
800 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
801 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
802 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
803 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
804 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
805 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
806 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
807 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
808 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
809 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
810 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
811 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
812 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
813 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
814 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) (GO2223009362PH, 04/11/2022, SM/13540 ) |  |  | BILL/02585/2023-2024 | BP-2023-24-741 | 29/11/2023 | 29/11/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 58 | 0 | 0 | 0
815 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
816 | BANKURA |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
817 | BIRBHUM |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
818 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
819 | DAKSHIN DINAJPUR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
820 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
821 | HOOGHLY |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
822 | HOWRAH |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
823 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
824 | JHARGRAM |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
825 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
826 | MALDAH |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
827 | MURSHIDABAD |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
828 | NADIA |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
829 | NORTH 24 PARGANAS |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
830 | PASCHIM BARDHAMAN |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
831 | PASCHIM MEDINIPUR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
832 | PURBA BARDHAMAN |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
833 | PURBA MEDINIPUR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
834 | PURULIA |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
835 | SOUTH 24 PARGANAS |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
836 | UTTAR DINAJPUR |  | Neorakhola W/S & Mtc.Div. | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
837 | ALIPURDUAR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
838 | BANKURA |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
839 | BIRBHUM |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
840 | COOCHBEHAR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
841 | DAKSHIN DINAJPUR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
842 | DARJEELING |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
843 | HOOGHLY |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
844 | HOWRAH |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
845 | JALPAIGURI |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
846 | JHARGRAM |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
847 | KALIMPONG |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
848 | MALDAH |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
849 | MURSHIDABAD |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
850 | NADIA |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
851 | NORTH 24 PARGANAS |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
852 | PASCHIM BARDHAMAN |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
853 | PASCHIM MEDINIPUR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
854 | PURBA BARDHAMAN |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
855 | PURBA MEDINIPUR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
856 | PURULIA |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
857 | SOUTH 24 PARGANAS |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
858 | UTTAR DINAJPUR |  | Alipurduar Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme 2433/DPHE-12/38/2023-MONT.CELL-DPHE DT:09/10/2023 |  |  | BILL/00603/2023-2024 | 384/23-24/PFMS | 29/02/2024 | 29/02/2024 | ALIPURDUAR ZILLA PARISHAD | 12 | 0 | 0 | 0
859 | ALIPURDUAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
860 | BANKURA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
861 | BIRBHUM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
862 | COOCHBEHAR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
863 | DAKSHIN DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
864 | DARJEELING |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
865 | HOOGHLY |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
866 | HOWRAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
867 | JALPAIGURI |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
868 | JHARGRAM |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
869 | KALIMPONG |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
870 | MALDAH |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
871 | MURSHIDABAD |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
872 | NADIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
873 | NORTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
874 | PASCHIM BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
875 | PASCHIM MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
876 | PURBA BARDHAMAN |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
877 | PURBA MEDINIPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
878 | PURULIA |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
879 | SOUTH 24 PARGANAS |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
880 | UTTAR DINAJPUR |  | Nadia Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Conceptulization, Design and Wall painting of 7 nos Arsenic affected Block (Haringhata, Chakdaha, Kalyani, Krishnagar-II, Nakashipara, Kaliganj, Nabadwip) having surface piped water supply scheme in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000086/2021-2022 | 2740/ND | 09/07/2021 | 09/03/2022 | DEBNATH BROTHERS | 24.9 | 24.84 | 99.77 | 100
881 | ALIPURDUAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
882 | BANKURA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
883 | BIRBHUM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
884 | COOCHBEHAR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
885 | DAKSHIN DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
886 | DARJEELING |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
887 | HOOGHLY |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
888 | HOWRAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
889 | JALPAIGURI |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
890 | JHARGRAM |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
891 | KALIMPONG |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
892 | MALDAH |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
893 | MURSHIDABAD |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
894 | NADIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
895 | NORTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
896 | PASCHIM BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
897 | PASCHIM MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
898 | PURBA BARDHAMAN |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
899 | PURBA MEDINIPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
900 | PURULIA |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
901 | SOUTH 24 PARGANAS |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
902 | UTTAR DINAJPUR |  | Jhargram Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | IEC activity (i.e wall writing/ flex/ banner/ leafleting) for legal provision, damage and illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation Binpur-I Block( for 15 village) of Jhargram District. (Phase-II) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000162/2024-2025 | 160/JRWS | 27/06/2024 | 27/07/2024 | SAMIR PATRA | 0.98 | 0 | 0 | 100
903 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
904 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
905 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
906 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
907 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
908 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
909 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
910 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
911 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
912 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
913 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
914 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
915 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
916 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
917 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
918 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
919 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
920 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
921 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
922 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
923 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
924 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Kalikatala (Zone-I), Kalikatala (Zone-II), Kuler Khonj, Par Kalugachi, Baintala, Khun Khali (Part-I), Khun Khali (Part-II), Khun Khali (Part-III), Khun Khali (Part-IV), Tambuldaha (Part-I), Tambuldaha (Part-II), Chelikati & Bibir Abad and Khagra. (For 13 (Thirteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000968/2024-2025 | 1181/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.13 | 0 | 0 | 100
925 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
926 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
927 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
928 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
929 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
930 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
931 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
932 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
933 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
934 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
935 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
936 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
937 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
938 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
939 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
940 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
941 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
942 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
943 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
944 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
945 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
946 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amlamethi, Sambhunagar, Choto Mollakhali (Zone-I), Bijoynagar, Luxbagan, Puinjali, Lahiripur, Pathankhali (Zone - I), Pathankhali (Zone - II), Pathankhali (Zone - III), Gosaba (Zone - I), Gosaba (Zone - II), Gosaba (Zone - III), Kumirmari (Zone- I) & Kumirmari (Zone-II) (For 15 (Fifteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000969/2024-2025 | 1182/CSD | 24/10/2024 | 13/11/2024 | A.P. CONSTRUCTION | 4.38 | 0 | 0 | 100
947 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
948 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
949 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
950 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
951 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
952 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
953 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
954 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
955 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
956 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
957 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
958 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
959 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
960 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
961 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
962 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
963 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
964 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
965 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
966 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
967 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
968 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
969 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
970 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
971 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
972 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
973 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
974 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
975 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
976 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
977 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
978 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
979 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
980 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
981 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
982 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
983 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
984 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
985 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
986 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
987 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
988 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
989 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
990 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Basanti) Name of PWSS :- Parbatipur, Lot No. 126, Ananda Abad, Goranbose, Bharatgarh, Basanti (Zone-III), Jyotishpur, Harekrishnapur, Hironmoypur, Ramchandrakhali (Zone-I & II), Dhuri, Tilkumar (Zone-I, II & III), Chunakhali (Zone-I), Chunakhali (Zone-II), Kumarkhali, Charabidya Abad, Narayantala, Phulmalancha & Chatrakhali (Zone-I) (For 19 (Nineteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000972/2024-2025 | 1196/CSD | 28/10/2024 | 17/11/2024 | A.P. CONSTRUCTION | 4.57 | 0 | 0 | 98
991 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
992 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
993 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
994 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
995 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
996 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
997 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
998 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
999 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1000 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1001 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1002 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1003 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1004 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1005 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1006 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1007 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1008 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1009 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1010 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1011 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1012 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Amtali (Zone - I), Amtali (Zone - II), Jelepara, Gopalkata, Kamakhyapur, Chimta (Zone - I), Chimta (Zone - II), Kamarpara, Bipradaspur & Battali (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000971/2024-2025 | 1184/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
1013 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1014 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1015 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1016 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1017 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1018 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1019 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1020 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1021 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1022 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1023 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1024 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1025 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1026 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1027 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1028 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1029 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1030 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1031 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1032 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1033 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1034 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS - Bhaleya, Kalaria (Zone-IA), Kalaria (Zone-IB), Kalaria (Zone-IIA), Kalaria (Zone-IIB), Devis Abad, Duttababur Abad, Bayarsing, Narayangar (Part -B), Narayangar, Bansra (Zone-I), Bansra (Zone-II), Dharmatala (Part-B) and Dharmatala. (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000965/2024-2025 | 1177/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 3.37 | 0 | 0 | 0
1035 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1036 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1037 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1038 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1039 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1040 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1041 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1042 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1043 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1044 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1045 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1046 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1047 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1048 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1049 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1050 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1051 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1052 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1053 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1054 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1055 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1056 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 0
1057 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1058 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1059 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1060 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1061 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1062 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1063 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1064 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1065 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1066 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1067 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1068 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1069 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1070 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1071 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1072 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1073 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1074 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1075 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1076 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1077 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1078 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Atharabeki, Iswaripur, Deuli (Zone-I), Deuli (Zone-II), Singheswar, Kalugachhi, Jibantala (Zone-I), Jibantala (Zone-II), Mallikkati, Makhaltala, Narayanpur, Srinagar, Nagartala (Zone - I), Nagartala (Zone - II), Netra, Daharani, Matherdighi R.O. (Zone - A, B, C & D), Matherdighi (Zone-I), Matherdighi (Zone-II) and Matherdighi (Zone-III) (For 20 (Twenty) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000966/2024-2025 | 1178/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 4.81 | 0 | 0 | 99
1079 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1080 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1081 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1082 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1083 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1084 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1085 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1086 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1087 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1088 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1089 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1090 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1091 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1092 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1093 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1094 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1095 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1096 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1097 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1098 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1099 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1100 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-II) Name of PWSS :- Gangacheri, Homrapolta, Moukhali-Kumarkhali (Zone - I), Moukhali-Kumarkhali (Zone - II), Moukhali-Kumarkhali (Zone - III), Moukhali-Kumarkhali (Zone - IV), Moukhali-Kumarkhali (Zone - V), Moukhali-Kumarkhali (Zone - VI), Moukhali-Kumarkhali (Zone - VII), Moukhali-Kumarkhali (Zone - VIII), Moukhali-Kumarkhali (Zone - IX), Moukhali-Kumarkhali (Zone - X), Moukhali-Kumarkhali (Zone - XI) and Moukhali-Kumarkhali (Zone - XII) (For 14 (Fourteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000967/2024-2025 | 1179/CSD | 24/10/2024 | 13/11/2024 | M/S. MIHIR KUMAR NASKAR | 3.37 | 0 | 0 | 100
1101 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1102 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1103 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1104 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1105 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1106 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1107 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1108 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1109 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1110 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1111 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1112 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1113 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1114 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1115 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1116 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1117 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1118 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1119 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1120 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1121 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1122 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Battali PWSS, Bipradaspur PWSS, Gopalkata PWSS, Kamarpara PWSS, Kamakhyapur PWSS, Jelepara PWSS, Luxbagan PWSS, Sadhupur (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000046/2025-2026 | 526/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1123 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1124 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1125 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1126 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1127 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1128 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1129 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1130 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1131 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1132 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1133 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1134 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1135 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1136 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1137 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1138 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1139 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1140 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1141 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1142 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1143 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1144 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Pathankhali (Zone - I) PWSS, Pathankhali (Zone - II) PWSS, Pathankhali (Zone - III)PWSS, Gosaba (Zone - I) PWSS & Gosaba (Zone - III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000045/2025-2026 | 525/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1145 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1146 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1147 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1148 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1149 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1150 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1151 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1152 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1153 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1154 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1155 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1156 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1157 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1158 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1159 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1160 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1161 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1162 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1163 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1164 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1165 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1166 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Purba Radhanagar (Zone-I, II & III) PWSS and Choto Mollakhali (Zone-I, II & III) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000052/2025-2026 | 531/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1167 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1168 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1169 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1170 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1171 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1172 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1173 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1174 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1175 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1176 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1177 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1178 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1179 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1180 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1181 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1182 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1183 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1184 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1185 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1186 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1187 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1188 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Shambhunagar PWSS, Lahiripur PWSS, Sadhupur (Zone-I & II) PWSS, Luxbagan PWSS, Harishpur (Zone-I & II) PWSS, Choto Mollakhali (Zone-I, II & III) PWSS, Gosaba Pond Base & Balance PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000053/2025-2026 | 532/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1189 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1190 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1191 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1192 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1193 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1194 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1195 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1196 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1197 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1198 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1199 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1200 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1201 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1202 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1203 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1204 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1205 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1206 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1207 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1208 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1209 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1210 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Budhkhali PWSS, Dharmatala PWSS, Duttababur Abad PWSS, Moukhali PWSS & Dakshin Rendokhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000054/2025-2026 | 533/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1211 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1212 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1213 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1214 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1215 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1216 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1217 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1218 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1219 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1220 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1221 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1222 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1223 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1224 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1225 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1226 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1227 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1228 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1229 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1230 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1231 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1232 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Matherdighi (Zone - A, B, C & D) PWSS, Narayanpur PWSS, Srinagar PWSS, Jibantala (Zone-I & II) PWSS, Homrapolta PWSS, Makhaltala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000217/2025-2026 | 655/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1233 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1234 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1235 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1236 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1237 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1238 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1239 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1240 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1241 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1242 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1243 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1244 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1245 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1246 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1247 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1248 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1249 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1250 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1251 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1252 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1253 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1254 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Lot No. 126 (Zone-I & II) PWSS, Parbatipur PWSS, Basanti (Zone-VII) PWSS, Basanti (Zone-VIII) PWSS and Basanti (Zone-IX) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000220/2025-2026 | 758/CSD | 02/06/2025 | 02/07/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 0
1255 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1256 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1257 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1258 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1259 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1260 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1261 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1262 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1263 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1264 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1265 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1266 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1267 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1268 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1269 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1270 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1271 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1272 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1273 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1274 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1275 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1276 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Kalugachhi PWSS, Mallikati PWSS, Deuli (Zone-I & II) PWSS, Nagartala (Zone - I & II) PWSS, Netra PWSS, Kaluakhali Mukherjeepara PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000213/2025-2026 | 651/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 100
1277 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1278 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1279 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1280 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1281 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1282 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1283 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1284 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1285 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1286 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1287 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1288 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1289 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1290 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1291 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1292 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1293 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1294 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1295 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1296 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1297 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1298 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Bibir Abad PWSS, Matherdighi (Zone-I, II & III), Kalikatala (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000215/2025-2026 | 653/CSD | 26/05/2025 | 25/06/2025 | GANGA TUBEWELL AND HARDWARE | 4.8 | 0 | 0 | 95
1299 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1300 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1301 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1302 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1303 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1304 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1305 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1306 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1307 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1308 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1309 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1310 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1311 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1312 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1313 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1314 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1315 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1316 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1317 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1318 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1319 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1320 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Basanti (Zone-I) PWSS, Basanti (Zone-II) PWSS, Basanti (Zone-III) PWSS, Basanti (Zone-IV) PWSS, Basanti (Zone-V) PWSS, Basanti (Zone-VI) PWSS and Lot No. 126 (Zone-I & II) PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000219/2025-2026 | 657/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1321 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1322 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1323 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1324 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1325 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1326 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1327 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1328 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1329 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1330 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1331 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1332 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1333 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1334 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1335 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1336 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1337 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1338 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1339 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1340 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1341 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1342 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Chatrakhali (Zone-I, II & III) PWSS, Chunakhali (Zone-I & II) PWSS and Char Baidyarabad PWSS. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000224/2025-2026 | 659/CSD | 26/05/2025 | 25/06/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 98
1343 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1344 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1345 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1346 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1347 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1348 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1349 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1350 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1351 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1352 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1353 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1354 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1355 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1356 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1357 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1358 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1359 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1360 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1361 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1362 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1363 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1364 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Dharmatala (Part-B) PWSS, Bhaleya PWSS, Kalaria (Zone-IA, IB) PWSS & Kalaria (Zone-IIA, IIB) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000057/2025-2026 | 536/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1365 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1366 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1367 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1368 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1369 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1370 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1371 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1372 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1373 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1374 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1375 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1376 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1377 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1378 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1379 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1380 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1381 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1382 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1383 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1384 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1385 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1386 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Dakshin Rendokhali PWSS, Taldi (Zone-I & II) PWSS & Devis Abad PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000058/2025-2026 | 537/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 100
1387 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1388 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1389 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1390 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1391 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1392 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1393 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1394 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1395 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1396 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1397 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1398 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1399 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1400 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1401 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1402 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1403 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1404 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1405 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1406 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1407 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1408 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Moukhali-Kumarkhali (Part - I to XII) PWSS, Khun Khali (Part-I to IV) PWSS, Tambuldaha (Part-I & II), Par Kalugachi PWSS & Baintala PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD | ORD/000214/2025-2026 | 652/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 100
1409 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1410 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1411 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1412 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1413 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1414 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1415 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1416 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1417 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1418 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1419 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1420 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1421 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1422 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1423 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1424 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1425 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1426 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1427 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1428 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1429 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1430 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Sonakhali (Zone-I) PWSS, Sonakhali (Zone-III) PWSS, Harbhangi PWSS, Kanthalberia PWSS, Bhangankhali PWSS and Phulmalancha PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2025-2026 | 658/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1431 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1432 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1433 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1434 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1435 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1436 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1437 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1438 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1439 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1440 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1441 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1442 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1443 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1444 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1445 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1446 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1447 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1448 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1449 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1450 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1451 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1452 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Char Baidyarabad PWSS, Kumarkhali PWSS, Dhuri PWSS, Tilkumar (Zone-I, II & III) PWSS and Sonakhali (Zone-IV) PWSS & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000225/2025-2026 | 660/CSD | 26/05/2025 | 25/06/2025 | A.P. CONSTRUCTION | 4.79 | 0 | 0 | 98
1453 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1454 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1455 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1456 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1457 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1458 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1459 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1460 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1461 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1462 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1463 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1464 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1465 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1466 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1467 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1468 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1469 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1470 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1471 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1472 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1473 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1474 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Uttar Angadberia PWSS, Bansra (Zone-I & II) PWSS & Banibadabelekhali PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000055/2025-2026 | 534/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 100
1475 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1476 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1477 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1478 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1479 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1480 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1481 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1482 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1483 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1484 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1485 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1486 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1487 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1488 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1489 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1490 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1491 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1492 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1493 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1494 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1495 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1496 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Nagartala (Zone - I & II) PWSS, Atharabeki PWSS, Atharabeki (Part-B) PWSS, Daharani PWSS, Iswaripur PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000216/2025-2026 | 654/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.8 | 0 | 0 | 98
1497 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1498 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1499 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1500 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1501 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1502 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1503 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1504 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1505 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1506 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1507 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1508 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1509 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1510 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1511 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1512 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1513 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1514 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1515 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1516 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1517 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1518 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name - Canning-II Name of PWSS :- Iswaripur PWSS, Kalugachi PWSS, Kuler Khonj PWSS, Khagra PWSS, Singheswar PWSS, Gangacheri PWSS, Moukhali-Kumarkhali (Old) (Zone - I & II) & Balance PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000218/2025-2026 | 656/CSD | 26/05/2025 | 25/06/2025 | M/S. MIHIR KUMAR NASKAR | 4.79 | 0 | 0 | 98
1519 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1520 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1521 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1522 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1523 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1524 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1525 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1526 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1527 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1528 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1529 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1530 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1531 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1532 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1533 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1534 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1535 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1536 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1537 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1538 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1539 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1540 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Bijoynagar PWSS & Gosaba (Zone-II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 528/CSD | 29/04/2025 | 29/05/2025 | SURYA ENTERPRISE | 4.65 | 0 | 0 | 100
1541 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1542 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1543 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1544 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1545 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1546 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1547 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1548 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1549 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1550 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1551 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1552 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1553 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1554 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1555 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1556 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1557 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1558 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1559 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1560 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1561 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1562 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Harishpur (Zone-I & II) PWSS, Lahiripur PWSS, Kachukhali PWSS & Sudhansupur PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000047/2025-2026 | 527/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1563 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1564 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1565 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1566 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1567 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1568 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1569 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1570 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1571 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1572 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1573 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1574 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1575 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1576 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1577 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1578 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1579 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1580 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1581 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1582 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1583 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1584 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Satjelia (Zone-I, II & III) PWSS, Sadhupur (Zone-I & II) PWSS & Amlamethi PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000049/2025-2026 | 529/CSD | 29/04/2025 | 29/05/2025 | A.P. CONSTRUCTION | 4.65 | 0 | 0 | 100
1585 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1586 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1587 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1588 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1589 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1590 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1591 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1592 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1593 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1594 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1595 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1596 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1597 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1598 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1599 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1600 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1601 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1602 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1603 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1604 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1605 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1606 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Gosaba Name of PWSS :- Chimta (Zone-I & II) PWSS, Amtali (Zone-I & II) PWSS & Kumirmari (Zone-I & II) PWSS. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000051/2025-2026 | 530/CSD | 29/04/2025 | 29/05/2025 | S.P. CONSTRUCTION (I) | 4.65 | 0 | 0 | 100
1607 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1608 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1609 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1610 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1611 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1612 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1613 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1614 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1615 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1616 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1617 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1618 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1619 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1620 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1621 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1622 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1623 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1624 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1625 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1626 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1627 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1628 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Narayangar PWSS, Adhia PWSS, Adhia (Part-B) PWSS, Narayangar (Part -B) PWSS, Bayarsing PWSS, Kalaria (Zone-IB) PWSS & Daria PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2025-2026 | 535/CSD | 29/04/2025 | 29/05/2025 | GANGA TUBEWELL AND HARDWARE | 4.78 | 0 | 0 | 98
1629 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1630 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1631 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1632 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1633 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1634 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1635 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1636 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1637 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1638 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1639 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1640 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1641 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1642 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1643 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1644 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1645 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1646 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1647 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1648 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1649 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1650 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Godkhali RO Plant, Harekrishnapur PWSS, Jyotishpur PWSS, Bharatgarh PWSS Hironmoypur PWSS and Goranbose PWSS | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000221/2025-2026 | 759/CSD | 02/06/2025 | 02/07/2025 | S.P. CONSTRUCTION (I) | 4.79 | 0 | 0 | 100
1651 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1652 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1653 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1654 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1655 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1656 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1657 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1658 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1659 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1660 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1661 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1662 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1663 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1664 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1665 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1666 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1667 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1668 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1669 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1670 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1671 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1672 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Basanti Name of PWSS :- Goranbose PWSS, Ananda Abad PWSS, Ramchandrakhali (Zone-I & II) PWSS, Sonakhali (Zone-II) PWSS and Narayantala PWSS | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000222/2025-2026 | 760/CSD | 02/06/2025 | 02/07/2025 | SURYA ENTERPRISE | 4.79 | 0 | 0 | 0
1673 | ALIPURDUAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1674 | BANKURA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1675 | BIRBHUM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1676 | COOCHBEHAR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1677 | DAKSHIN DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1678 | DARJEELING |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1679 | HOOGHLY |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1680 | HOWRAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1681 | JALPAIGURI |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1682 | JHARGRAM |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1683 | KALIMPONG |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1684 | MALDAH |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1685 | MURSHIDABAD |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1686 | NADIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1687 | NORTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1688 | PASCHIM BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1689 | PASCHIM MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1690 | PURBA BARDHAMAN |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1691 | PURBA MEDINIPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1692 | PURULIA |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1693 | SOUTH 24 PARGANAS |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
1694 | UTTAR DINAJPUR |  | Alipore Division | Information Education Communication (IEC) and Training/Capacity Building Activities with special emphasis on Water Quality under Jal jeevan Mission (JJM) Water Quality Monitoring and Surveillance Programme ( WQMSP) | SM/13540 | Support-WQMSP | Erection of Land Sign Board at different PWSS under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) Block Name :- Canning-I Name of PWSS - Canning (Zone-I, II & III) PWSS, Kalaria (IA, IB, IIA & IIB) PWSS, Taldi (Zone-I & II) PWSS & Balance PWSS (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000059/2025-2026 | 538/CSD | 29/04/2025 | 29/05/2025 | M/S. MIHIR KUMAR NASKAR | 4.78 | 0 | 0 | 0
Total | [13 empty] | 18161.63 | 624.88 | 3.44