## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
2 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
3 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
4 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
6 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
7 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
8 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
9 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
10 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
11 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
12 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
13 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
14 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
20 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Tiffin Allowances for plumbing, fitting and Electrician Training at different ITI colleges under Alipurduar District |  |  | ORD/000541/2022-2023 | 288/RWS | 27/02/2023 | 14/03/2023 | DIPAK DAS | 0.79 | 0 | 0 | 0
23 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
24 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
25 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
26 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
27 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
28 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
29 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
30 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
31 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
32 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
33 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
34 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
35 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
36 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
37 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
38 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
39 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
40 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
41 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
42 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
43 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
44 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Amta-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000711/2022-2023 | 2996/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.47 | 49.34 | 0
45 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
46 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
47 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
48 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
49 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
50 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
51 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
52 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
53 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
54 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
55 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
56 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
57 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
58 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
59 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
60 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
61 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
62 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
63 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
64 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
65 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
66 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000712/2022-2023 | 2997/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.66 | 69.05 | 0
67 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
68 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
69 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
70 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
71 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
72 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
73 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
74 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
75 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
76 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
77 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
78 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
79 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
80 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
81 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
82 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
83 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
84 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
85 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
86 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
87 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
88 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan - II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000714/2022-2023 | 2999/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.56 | 57.86 | 0
89 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
90 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
91 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
92 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
93 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
94 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
95 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
96 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
97 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
98 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
99 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
100 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
101 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
102 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
103 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
104 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
105 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
106 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
107 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
108 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
109 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
110 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Garchumuk Picnic Spot) | AE/Ulu |  | ORD/000743/2022-2023 | 615/HD | 16/02/2023 | 18/03/2023 | PRADIP KUMAR JATI | 7.86 | 7.86 | 100 | 0
111 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
112 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
113 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
114 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
115 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
116 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
117 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
118 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
119 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
120 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
121 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
122 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
123 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
124 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
125 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
126 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
127 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
128 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
129 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
130 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
131 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
132 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - I) | AE HQ |  | ORD/000716/2022-2023 | 3001/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
133 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
134 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
135 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
136 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
137 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
138 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
139 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
140 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
141 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
142 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
143 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
144 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
145 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
146 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
147 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
148 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
149 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
150 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
151 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
152 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
153 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
154 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000717/2022-2023 | 3002/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
155 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
156 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
157 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
158 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
159 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
160 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
161 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
162 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
163 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
164 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
165 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
166 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
167 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
168 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
169 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
170 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
171 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
172 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
173 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
174 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
175 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
176 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Shyampur-II Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. (Phase - II) | AE HQ |  | ORD/000718/2022-2023 | 3003/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.56 | 57.86 | 0
177 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
178 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
179 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
180 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
181 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
182 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
183 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
184 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
185 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
186 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
187 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
188 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
189 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
190 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
191 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
192 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
193 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
194 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
195 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
196 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
197 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
198 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Udaynarayanpur Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000719/2022-2023 | 3004/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.58 | 60.49 | 0
199 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
200 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
201 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
202 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
203 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
204 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
205 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
206 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
207 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
208 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
209 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
210 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
211 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
212 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
213 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
214 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
215 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
216 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
217 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
218 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
219 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
220 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supply of potable water by movable water Tankers to the Picnic Tourists including performing of IEC activities at different Tourists spots like Garchumuk (58Gate), Gadiara and Shibganj of Shyampur-I Block of Uluberia Sub Division under Howrah Division, PHE Dte. (for Shibgachi & Gadiara Picnic Spot) | AE/Ulu |  | ORD/000742/2022-2023 | 614/HD | 16/02/2023 | 18/03/2023 | S.M. CONSTRUCTION | 7.82 | 7.82 | 100 | 100
221 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
222 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
223 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
224 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
225 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
226 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
227 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
228 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
229 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
230 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
231 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
232 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
233 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
234 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
235 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
236 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
237 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
238 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
239 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
240 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
241 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
242 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Uluberia-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000713/2022-2023 | 2998/HD | 30/12/2022 | 09/01/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.46 | 48 | 0
243 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
244 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
245 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
246 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
247 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
248 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
249 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
250 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
251 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
252 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
253 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
254 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
255 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
256 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
257 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
258 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
259 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
260 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
261 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
262 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
263 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
264 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Conducting Skill Development Training Programme under "Jal Jeevan Mission" for Bagnan-I Block of Howrah District in collaboration with Howrah Division, PHE Dte. & ITI Howrah Homes, TET & SD Deptt. | AE HQ |  | ORD/000715/2022-2023 | 3000/HD | 30/12/2022 | 09/01/2023 | COMMERCIAL AND MECHANICAL WINGS | 0.96 | 0.49 | 51.31 | 0
265 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
266 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
267 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
268 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
269 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
270 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
271 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
272 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
273 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
274 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
275 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
276 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
277 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
278 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
279 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
280 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
281 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
282 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
283 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
284 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
285 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
286 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for theTufanganj Block, held at Tufanganj ITI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000728/2022-2023 | 1524/CD(A) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.74 | 0.7 | 94.68 | 100
287 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
288 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
289 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
290 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
291 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
292 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
293 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
294 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
295 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
296 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
297 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
298 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
299 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
300 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
301 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
302 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
303 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
304 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
305 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
306 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
307 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
308 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-II, held at PHE Office Building. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000729/2022-2023 | 1524/CD(B) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.85 | 0.81 | 95.36 | 100
309 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
310 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
311 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
312 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
313 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
314 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
315 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
316 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
317 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
318 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
319 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
320 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
321 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
322 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
323 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
324 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
325 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
326 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
327 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
328 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
329 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
330 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 19TH Jangal Mahal Utsav 2023 at Chuapara play ground , under Kalchini Block , Alipurduar. | HQ-A.E |  | ORD/000572/2022-2023 | 3633/ALD | 31/03/2023 | 30/04/2023 | ANIK BHATTACHARJEE | 0.96 | 0.96 | 100 | 0
331 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
332 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
333 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
334 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
335 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
336 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
337 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
338 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
339 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
340 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
341 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
342 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
343 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
344 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
345 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
346 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
347 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
348 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
349 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
350 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
351 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
352 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the delegates present in the Meeting of Honble CM, GoWB at Panchla Netaji Club ground, including supplying fitting & fixing of standy display board along DN lane of NH-6 I.e, from Panchla to Ankurhati check post of Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000904/2022-2023 | 476/HD | 08/02/2023 | 18/02/2023 | ADITYA HAZRA | 11.64 | 11.63 | 99.91 | 0
353 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
354 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
355 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
356 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
357 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
358 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
359 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
360 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
361 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
362 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
363 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
364 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
365 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
366 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
367 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
368 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
369 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
370 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
371 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
372 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
373 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
374 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Supplying fitting and fixing different hording or Standi Display Board along the NH-6 from Ankurhati Checkpost to Panchla by the side of up lane in connection with hon¿ble CM¿s visit on 09/02/2023 under Howrah District under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000905/2022-2023 | 474/HD | 08/02/2023 | 18/02/2023 | SHOUMMYODIP & CO. | 10.63 | 10.63 | 100 | 0
375 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
376 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
377 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
378 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
379 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
380 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
381 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
382 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
383 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
384 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
385 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
386 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
387 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
388 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
389 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
390 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
391 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
392 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
393 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
394 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
395 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
396 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement under Alipurduar- I Block for IEC/ Awarness generation activities , Alipurduar Division P.H.E Dte. | Alipurduar RWS,HQ-A.E | RWS Kumargram Block | ORD/000013/2023-2024 | 163/ALD | 26/04/2023 | 28/04/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.41 | 0 | 0 | 0
397 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
398 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
399 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
400 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
401 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
402 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
403 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
404 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
405 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
406 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
407 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
408 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
409 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
410 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
411 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
412 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
413 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
414 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
415 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
416 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
417 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
418 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Construction of Temporary Toilets and making arrangement for distribution of Drinking water to the Beneficeries as well as for Drivers / Officials for the Meeting of Honble CM,GOWB at Ma Tara Parking, KC Service Station & NDR, Howrah District under Under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000903/2022-2023 | 475/HD | 08/02/2023 | 18/02/2023 | SKI ENTERPRISE | 6.83 | 6.83 | 100 | 0
419 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
420 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
421 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
422 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
423 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
424 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
425 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
426 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
427 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
428 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
429 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
430 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
431 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
432 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
433 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
434 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
435 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
436 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
437 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
438 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
439 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
440 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying of different types for smooth running of official work under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000308/2023-2024 | 136/MTB | 21/06/2023 | 24/06/2023 | ELECTRO SERVICES PVT.LTD | 0.39 | 0 | 0 | 0
441 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
442 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
443 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
444 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
445 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
446 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
447 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
448 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
449 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
450 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
451 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
452 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
453 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
454 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
455 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
456 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
457 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
458 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
459 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
460 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
461 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
462 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2022 to June 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001196/2021-2022 | 4011/MURD | 23/12/2021 | 23/06/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
463 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
464 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
465 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
466 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
467 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
468 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
469 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
470 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
471 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
472 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
473 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
474 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
475 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
476 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
477 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
478 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
479 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
480 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
481 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
482 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
483 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
484 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Mass awareness programme through wall painting by dissemination of awareness generation IEC messages regarding FHTC and water conservation,save water,safe water and water quality etc. other water related issues at 13 no. GPs (Pratapaditya,Madhusudanpur,Netaji ,Rabindra,Bapuji,Srinagar G.P under Kakdwip Block & Dhaspara Sumatinagar-I,Dhaspara Sumatinagar-II,Dhablat,Kamalpur Rudranagar,Gangasagar,Muriganga-II, Ramkarchar G.P under Sagar Block) in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. Govt. of West Bengal (PART-A) | Assistant Engineer, RWS |  | ORD/001427/2021-2022 | 807/RWS | 08/03/2022 | 22/04/2022 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 90
485 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
486 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
487 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
488 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
489 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
490 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
491 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
492 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
493 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
494 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
495 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
496 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
497 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
498 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
499 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
500 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
501 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
502 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
503 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
504 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
505 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
506 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Work Order for Procurement of consumable & reagents for 3nos Onsite Mobile Analysis System (3nos OMAS kit) foe testing of Public drinking water sources under Howrah Division, PHE Dte. | AE HQ |  | ORD/000179/2022-2023 | 1416/HD | 08/07/2022 | 23/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 0.37 | 7.6 | 0
507 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
508 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
509 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
510 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
511 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
512 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
513 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
514 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
515 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
516 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
517 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
518 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
519 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
520 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
521 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
522 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
523 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
524 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
525 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
526 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
527 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
528 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e.July 2022 to Dec 2022 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000279/2022-2023 | 1549/MURD | 15/06/2022 | 15/12/2022 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
529 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
530 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
531 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
532 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
533 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
534 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
535 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
536 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
537 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
538 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
539 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
540 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
541 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
542 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
543 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
544 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
545 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
546 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
547 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
548 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
549 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
550 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. January 2023 to June 2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000647/2022-2023 | 3320/MURD | 14/12/2022 | 14/06/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
551 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
552 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
553 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
554 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
555 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
556 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
557 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
558 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
559 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
560 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
561 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
562 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
563 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
564 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
565 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
566 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
567 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
568 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
569 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
570 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
571 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
572 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) |  | ORD/000533/2022-2023 | 294/HQ | 21/09/2022 | 16/02/2023 | DARSHAN COMMUNICATION | 4.97 | 4.97 | 100 | 0
573 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
574 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
575 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
576 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
577 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
578 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
579 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
580 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
581 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
582 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
583 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
584 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
585 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
586 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
587 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
588 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
589 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
590 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
591 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
592 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
593 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
594 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Necessary arrangement of training to DEO¿s on physical/financial modules of IMIS. | HQ-A.E |  | ORD/000411/2022-2023 | 2803/ALD | 10/01/2023 | 11/01/2023 | SREE MAA CONSTRUCTION | 0.96 | 0.96 | 100 | 0
595 | ALIPURDUAR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
596 | BANKURA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
597 | BIRBHUM |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
598 | COOCHBEHAR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
599 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
600 | DARJEELING |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
601 | HOOGHLY |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
602 | HOWRAH |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
603 | JALPAIGURI |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
604 | JHARGRAM |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
605 | KALIMPONG |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
606 | MALDAH |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
607 | MURSHIDABAD |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
608 | NADIA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
609 | NORTH 24 PARGANAS |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
610 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
611 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
612 | PURBA BARDHAMAN |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
613 | PURBA MEDINIPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
614 | PURULIA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
615 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
616 | UTTAR DINAJPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply of different sizes Bannars hoarding for Bangla Unnayaner Pathe in Printable format for different sizes under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000326/2022-2023 | 2457/JD | 22/12/2022 | 29/12/2022 | SWAPAN SAHA | 2.39 | 2.39 | 100 | 0
617 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
618 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
619 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
620 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
621 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
622 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
623 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
624 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
625 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
626 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
627 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
628 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
629 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
630 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
631 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
632 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
633 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
634 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
635 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
636 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
637 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
638 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking and Sanitary Water Supply arrangement for Dooars Utsab,2023 under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000408/2022-2023 | 2799/ALD | 10/01/2023 | 25/01/2023 | SREE MAA CONSTRUCTION | 4.36 | 4.36 | 100 | 0
639 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
640 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
641 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
642 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
643 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
644 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
645 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
646 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
647 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
648 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
649 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
650 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
651 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
652 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
653 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
654 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
655 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
656 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
657 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
658 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
659 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
660 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation work order for organizing 05 minutes sponsored programme through F.M. Radio, Murshidabad. Media plan Hundred For I48 days (one Forty Eight days) . | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000728/2022-2023 | 20/HQ | 08/02/2023 | 06/07/2023 | DARSHAN COMMUNICATION | 4.97 | 4.55 | 91.43 | 100
661 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
662 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
663 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
664 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
665 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
666 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
667 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
668 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
669 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
670 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
671 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
672 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
673 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
674 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
675 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
676 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
677 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
678 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
679 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
680 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
681 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
682 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Dinhata Block, held at Dinhata ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000730/2022-2023 | 1524/CD(C) | 20/01/2023 | 27/01/2023 | BIJOY ROY | 0.77 | 0 | 0 | 100
683 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
684 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
685 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
686 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
687 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
688 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
689 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
690 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
691 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
692 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
693 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
694 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
695 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
696 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
697 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
698 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
699 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
700 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
701 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
702 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
703 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
704 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Training for Skilling of manpower to generate employment opportunities and to support implementation of ¿Jal Jeevan Mission¿ for the Cooch Behar Block-I, held at Cooch Behar ITI. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000727/2022-2023 | 1464/CD | 09/01/2023 | 16/01/2023 | BIJOY ROY | 0.56 | 0.52 | 92.97 | 100
705 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
706 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
707 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
708 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
709 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
710 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
711 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
712 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
713 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
714 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
715 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
716 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
717 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
718 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
719 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
720 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
721 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
722 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
723 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
724 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
725 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
726 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and Operation of Stall of PHED in the 17th Dooars Utsab 2023 at ALipurduar Parade ground, Alipurduar. | Alipurduar RWS |  | ORD/000409/2022-2023 | 2800/ALD | 10/01/2023 | 25/01/2023 | ANIK BHATTACHARJEE | 4.85 | 4.66 | 96.17 | 0
727 | ALIPURDUAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
728 | BANKURA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
729 | BIRBHUM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
730 | COOCHBEHAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
731 | DAKSHIN DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
732 | DARJEELING |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
733 | HOOGHLY |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
734 | HOWRAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
735 | JALPAIGURI |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
736 | JHARGRAM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
737 | KALIMPONG |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
738 | MALDAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
739 | MURSHIDABAD |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
740 | NADIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
741 | NORTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
742 | PASCHIM BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
743 | PASCHIM MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
744 | PURBA BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
745 | PURBA MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
746 | PURULIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
747 | SOUTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
748 | UTTAR DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Chanchal-I, Chanchal-II, Harischandrapur-II, Ratua-I and Manikchak Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Sumit Kumar Ghosh, Assistant Engineer | Junior Engineer,Mr. Tilok Roy, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000001/2023-2024 | 08/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.69 | 0.62 | 89.18 | 0
749 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
750 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
751 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
752 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
753 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
754 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
755 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
756 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
757 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
758 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
759 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
760 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
761 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
762 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
763 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
764 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
765 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
766 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
767 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
768 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
769 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
770 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Water supply arrangement in connection with the IEC/ Awarness generation activities under Kumargram Block , Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division |  | ORD/000012/2023-2024 | 162/ALD | 26/04/2023 | 28/04/2023 | SREE MAA CONSTRUCTION | 0.58 | 0 | 0 | 100
771 | ALIPURDUAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
772 | BANKURA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
773 | BIRBHUM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
774 | COOCHBEHAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
775 | DAKSHIN DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
776 | DARJEELING |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
777 | HOOGHLY |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
778 | HOWRAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
779 | JALPAIGURI |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
780 | JHARGRAM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
781 | KALIMPONG |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
782 | MALDAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
783 | MURSHIDABAD |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
784 | NADIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
785 | NORTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
786 | PASCHIM BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
787 | PASCHIM MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
788 | PURBA BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
789 | PURBA MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
790 | PURULIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
791 | SOUTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
792 | UTTAR DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Kaliachak-III Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer |  | ORD/000003/2023-2024 | 10/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.59 | 0.44 | 74.32 | 0
793 | ALIPURDUAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
794 | BANKURA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
795 | BIRBHUM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
796 | COOCHBEHAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
797 | DAKSHIN DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
798 | DARJEELING |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
799 | HOOGHLY |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
800 | HOWRAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
801 | JALPAIGURI |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
802 | JHARGRAM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
803 | KALIMPONG |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
804 | MALDAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
805 | MURSHIDABAD |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
806 | NADIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
807 | NORTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
808 | PASCHIM BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
809 | PASCHIM MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
810 | PURBA BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
811 | PURBA MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
812 | PURULIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
813 | SOUTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
814 | UTTAR DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of English Bazar Dev. Block under RWS Malda Sub-Division in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000002/2023-2024 | 09/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.89 | 0.7 | 79.27 | 0
815 | ALIPURDUAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
816 | BANKURA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
817 | BIRBHUM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
818 | COOCHBEHAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
819 | DAKSHIN DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
820 | DARJEELING |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
821 | HOOGHLY |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
822 | HOWRAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
823 | JALPAIGURI |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
824 | JHARGRAM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
825 | KALIMPONG |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
826 | MALDAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
827 | MURSHIDABAD |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
828 | NADIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
829 | NORTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
830 | PASCHIM BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
831 | PASCHIM MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
832 | PURBA BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
833 | PURBA MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
834 | PURULIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
835 | SOUTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
836 | UTTAR DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of Swajal Gram Sign Board at Different Pin-pointed Sites of Bamongola, Habibpur and Old Malda Dev. Block under RWS Malda Sub-Division in the district of Malda | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000004/2023-2024 | 11/RWS | 06/04/2023 | 20/04/2023 | M/S AYUSH BUILDERS | 0.79 | 0.7 | 89.18 | 0
837 | ALIPURDUAR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
838 | BANKURA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
839 | BIRBHUM |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
840 | COOCHBEHAR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
841 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
842 | DARJEELING |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
843 | HOOGHLY |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
844 | HOWRAH |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
845 | JALPAIGURI |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
846 | JHARGRAM |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
847 | KALIMPONG |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
848 | MALDAH |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
849 | MURSHIDABAD |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
850 | NADIA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
851 | NORTH 24 PARGANAS |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
852 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
853 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
854 | PURBA BARDHAMAN |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
855 | PURBA MEDINIPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
856 | PURULIA |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
857 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
858 | UTTAR DINAJPUR |  | Jalpaiguri Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000113/2023-2024 | 448/JD. | 08/06/2023 | 15/06/2023 | J.M. CONSTRUCTION | 6.05 | 6.03 | 99.7 | 100
859 | ALIPURDUAR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
860 | BANKURA |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
861 | BIRBHUM |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
862 | COOCHBEHAR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
863 | DAKSHIN DINAJPUR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
864 | DARJEELING |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
865 | HOOGHLY |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
866 | HOWRAH |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
867 | JALPAIGURI |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
868 | JHARGRAM |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
869 | KALIMPONG |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
870 | MALDAH |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
871 | MURSHIDABAD |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
872 | NADIA |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
873 | NORTH 24 PARGANAS |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
874 | PASCHIM BARDHAMAN |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
875 | PASCHIM MEDINIPUR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
876 | PURBA BARDHAMAN |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
877 | PURBA MEDINIPUR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
878 | PURULIA |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
879 | SOUTH 24 PARGANAS |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
880 | UTTAR DINAJPUR |  | Raiganj Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00114/2022-2023 | BP-2022-23-287 | 01/02/2023 | 01/02/2023 | JAL SHAKTI ABHIYAN | 33.2 | 0 | 0 | 0
881 | ALIPURDUAR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
882 | BANKURA |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
883 | BIRBHUM |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
884 | COOCHBEHAR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
885 | DAKSHIN DINAJPUR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
886 | DARJEELING |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
887 | HOOGHLY |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
888 | HOWRAH |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
889 | JALPAIGURI |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
890 | JHARGRAM |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
891 | KALIMPONG |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
892 | MALDAH |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
893 | MURSHIDABAD |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
894 | NADIA |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
895 | NORTH 24 PARGANAS |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
896 | PASCHIM BARDHAMAN |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
897 | PASCHIM MEDINIPUR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
898 | PURBA BARDHAMAN |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
899 | PURBA MEDINIPUR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
900 | PURULIA |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
901 | SOUTH 24 PARGANAS |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
902 | UTTAR DINAJPUR |  | Jhargram Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00214/2022-2023 | BP-2022-23-173 | 10/03/2023 | 10/03/2023 | PGE 2018 DM AND DPEO JHARGRAM | 23.6 | 0 | 0 | 0
903 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
904 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
905 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
906 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
907 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
908 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
909 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
910 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
911 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
912 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
913 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
914 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
915 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
916 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
917 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
918 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
919 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
920 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
921 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
922 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
923 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
924 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/01226/2022-2023 | BP-2022-23-800 | 24/02/2023 | 24/02/2023 | EXECUTIVE ENGINEER, ALIPUR DIVN. | 48.8 | 0 | 0 | 0
925 | ALIPURDUAR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
926 | BANKURA |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
927 | BIRBHUM |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
928 | COOCHBEHAR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
929 | DAKSHIN DINAJPUR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
930 | DARJEELING |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
931 | HOOGHLY |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
932 | HOWRAH |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
933 | JALPAIGURI |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
934 | JHARGRAM |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
935 | KALIMPONG |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
936 | MALDAH |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
937 | MURSHIDABAD |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
938 | NADIA |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
939 | NORTH 24 PARGANAS |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
940 | PASCHIM BARDHAMAN |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
941 | PASCHIM MEDINIPUR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
942 | PURBA BARDHAMAN |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
943 | PURBA MEDINIPUR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
944 | PURULIA |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
945 | SOUTH 24 PARGANAS |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
946 | UTTAR DINAJPUR |  | Burdwan Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and Rural development department, under Jal Jeevan Mission. |  |  | BILL/00557/2022-2023 | 1187/JJM | 14/03/2023 | 14/03/2023 | ELECTION PERSONNEL PAYMENT OF PURBA BARDHAMAN | 58.8 | 0 | 0 | 0
947 | ALIPURDUAR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
948 | BANKURA |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
949 | BIRBHUM |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
950 | COOCHBEHAR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
951 | DAKSHIN DINAJPUR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
952 | DARJEELING |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
953 | HOOGHLY |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
954 | HOWRAH |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
955 | JALPAIGURI |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
956 | JHARGRAM |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
957 | KALIMPONG |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
958 | MALDAH |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
959 | MURSHIDABAD |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
960 | NADIA |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
961 | NORTH 24 PARGANAS |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
962 | PASCHIM BARDHAMAN |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
963 | PASCHIM MEDINIPUR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
964 | PURBA BARDHAMAN |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
965 | PURBA MEDINIPUR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
966 | PURULIA |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
967 | SOUTH 24 PARGANAS |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
968 | UTTAR DINAJPUR |  | Nadia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/AWARENESS GENERATION ACTIVITIES THROUGH WALL PAINTING AND MIKING IN THE VILLAGE HAVING HOUSE CONNECTION THROUGH PWS IN COLLABORATION WITH PANCHYAT AND RURAL DEVELOPMENT DEPARTMENT , GOVT. OF WEST BENGAL UNDER JJM SUPPORT ACTIVITIES. |  |  | BILL/00743/2022-2023 | 444/PFMS | 04/03/2023 | 04/03/2023 | OTHERS | 67.2 | 0 | 0 | 0
969 | ALIPURDUAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
970 | BANKURA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
971 | BIRBHUM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
972 | COOCHBEHAR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
973 | DAKSHIN DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
974 | DARJEELING |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
975 | HOOGHLY |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
976 | HOWRAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
977 | JALPAIGURI |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
978 | JHARGRAM |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
979 | KALIMPONG |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
980 | MALDAH |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
981 | MURSHIDABAD |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
982 | NADIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
983 | NORTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
984 | PASCHIM BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
985 | PASCHIM MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
986 | PURBA BARDHAMAN |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
987 | PURBA MEDINIPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
988 | PURULIA |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
989 | SOUTH 24 PARGANAS |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
990 | UTTAR DINAJPUR |  | Coochbehar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC ACTIVITIES EXPENSES UNDER COB DIVISION, PHED |  |  | BILL/00621/2022-2023 | BP-680-2022-23 | 13/02/2023 | 13/02/2023 | MS DISTRICT MAZISTRATE COOCHBEHAR | 32 | 0 | 0 | 0
991 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
992 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
993 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
994 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
995 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
996 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
997 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
998 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
999 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1000 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1001 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1002 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1003 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1004 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1005 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1006 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1007 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1008 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1009 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1010 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1011 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1012 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC Actiivty |  |  | BILL/00134/2023-2024 | 81/23-24/PFMS | 04/07/2023 | 04/07/2023 | DISTRICT MAGISTRATE | 22.4 | 0 | 0 | 0
1013 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1014 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1015 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1016 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1017 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1018 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1019 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1020 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1021 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1022 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1023 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1024 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1025 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1026 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1027 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1028 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1029 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1030 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1031 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1032 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1033 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1034 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00308/2022-2023 | 506-MSD/22-23 | 13/01/2023 | 13/01/2023 | SPECIAL LAND AQUISITION OFFICER | 59.2 | 0 | 0 | 0
1035 | ALIPURDUAR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1036 | BANKURA |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1037 | BIRBHUM |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1038 | COOCHBEHAR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1039 | DAKSHIN DINAJPUR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1040 | DARJEELING |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1041 | HOOGHLY |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1042 | HOWRAH |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1043 | JALPAIGURI |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1044 | JHARGRAM |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1045 | KALIMPONG |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1046 | MALDAH |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1047 | MURSHIDABAD |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1048 | NADIA |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1049 | NORTH 24 PARGANAS |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1050 | PASCHIM BARDHAMAN |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1051 | PASCHIM MEDINIPUR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1052 | PURBA BARDHAMAN |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1053 | PURBA MEDINIPUR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1054 | PURULIA |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1055 | SOUTH 24 PARGANAS |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1056 | UTTAR DINAJPUR |  | Birbhum Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/ Awareness generation activities through wall painting and miking in the village having house connection through PWS in collaboration with panchayat and rural development Dept under Jal Jeevan Mission Support Activities |  |  | BILL/00259/2022-2023 | BP-2022-23-441 | 13/01/2023 | 13/01/2023 | BIRBHUM ZILLA PARISHAD. | 34.4 | 0 | 0 | 0
1057 | ALIPURDUAR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1058 | BANKURA |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1059 | BIRBHUM |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1060 | COOCHBEHAR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1061 | DAKSHIN DINAJPUR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1062 | DARJEELING |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1063 | HOOGHLY |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1064 | HOWRAH |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1065 | JALPAIGURI |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1066 | JHARGRAM |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1067 | KALIMPONG |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1068 | MALDAH |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1069 | MURSHIDABAD |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1070 | NADIA |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1071 | NORTH 24 PARGANAS |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1072 | PASCHIM BARDHAMAN |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1073 | PASCHIM MEDINIPUR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1074 | PURBA BARDHAMAN |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1075 | PURBA MEDINIPUR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1076 | PURULIA |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1077 | SOUTH 24 PARGANAS |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1078 | UTTAR DINAJPUR |  | Balurghat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities through Wall Painting & Miking in vollaboratio with P&RD Department, Govt. of West Bengal. |  |  | BILL/00108/2022-2023 | BP-2022-23-183 | 13/01/2023 | 13/01/2023 | DISTRICT MAGISTRATE, DAKSHIN DINAJPUR. | 18.8 | 0 | 0 | 0
1079 | ALIPURDUAR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1080 | BANKURA |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1081 | BIRBHUM |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1082 | COOCHBEHAR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1083 | DAKSHIN DINAJPUR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1084 | DARJEELING |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1085 | HOOGHLY |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1086 | HOWRAH |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1087 | JALPAIGURI |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1088 | JHARGRAM |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1089 | KALIMPONG |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1090 | MALDAH |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1091 | MURSHIDABAD |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1092 | NADIA |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1093 | NORTH 24 PARGANAS |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1094 | PASCHIM BARDHAMAN |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1095 | PASCHIM MEDINIPUR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1096 | PURBA BARDHAMAN |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1097 | PURBA MEDINIPUR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1098 | PURULIA |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1099 | SOUTH 24 PARGANAS |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1100 | UTTAR DINAJPUR |  | Bankura Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fund Transfer for IEC activities through wall Painting & Milking in collaboration with P&RD Department, Govt of West Bengal |  |  | BILL/01204/2022-2023 | FHTC/10 | 10/03/2023 | 10/03/2023 | COOKED MID DAY MEAL PROGRAMME BANKURA | 48.4 | 0 | 0 | 0
1101 | ALIPURDUAR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1102 | BANKURA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1103 | BIRBHUM |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1104 | COOCHBEHAR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1105 | DAKSHIN DINAJPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1106 | DARJEELING |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1107 | HOOGHLY |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1108 | HOWRAH |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1109 | JALPAIGURI |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1110 | JHARGRAM |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1111 | KALIMPONG |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1112 | MALDAH |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1113 | MURSHIDABAD |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1114 | NADIA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1115 | NORTH 24 PARGANAS |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1116 | PASCHIM BARDHAMAN |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1117 | PASCHIM MEDINIPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1118 | PURBA BARDHAMAN |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1119 | PURBA MEDINIPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1120 | PURULIA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1121 | SOUTH 24 PARGANAS |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1122 | UTTAR DINAJPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | VCH/003008/2022-2023 | BP-2022-23-588 | 10/03/2023 | 10/03/2023 | HOOGHLY ZILLA PARISHAD | 44.4 | 0 | 0 | 0
1123 | ALIPURDUAR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1124 | BANKURA |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1125 | BIRBHUM |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1126 | COOCHBEHAR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1127 | DAKSHIN DINAJPUR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1128 | DARJEELING |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1129 | HOOGHLY |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1130 | HOWRAH |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1131 | JALPAIGURI |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1132 | JHARGRAM |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1133 | KALIMPONG |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1134 | MALDAH |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1135 | MURSHIDABAD |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1136 | NADIA |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1137 | NORTH 24 PARGANAS |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1138 | PASCHIM BARDHAMAN |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1139 | PASCHIM MEDINIPUR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1140 | PURBA BARDHAMAN |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1141 | PURBA MEDINIPUR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1142 | PURULIA |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1143 | SOUTH 24 PARGANAS |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1144 | UTTAR DINAJPUR |  | Midnapore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Rastiya Swasthya Bima. |  |  | BILL/00749/2022-2023 | BP-2022-23-501 | 01/02/2023 | 01/02/2023 | DISTRICT MAGISTRATE, PASCHIM MEDINIPUR | 46.8 | 0 | 0 | 0
1145 | ALIPURDUAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1146 | BANKURA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1147 | BIRBHUM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1148 | COOCHBEHAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1149 | DAKSHIN DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1150 | DARJEELING |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1151 | HOOGHLY |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1152 | HOWRAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1153 | JALPAIGURI |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1154 | JHARGRAM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1155 | KALIMPONG |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1156 | MALDAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1157 | MURSHIDABAD |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1158 | NADIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1159 | NORTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1160 | PASCHIM BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1161 | PASCHIM MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1162 | PURBA BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1163 | PURBA MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1164 | PURULIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1165 | SOUTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1166 | UTTAR DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00294/2022-2023 | BP-2022-23-671 | 06/02/2023 | 06/02/2023 | DISTRICT MAGISTRATE, PURBA MEDINIPUR. | 46 | 0 | 0 | 0
1167 | ALIPURDUAR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1168 | BANKURA |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1169 | BIRBHUM |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1170 | COOCHBEHAR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1171 | DAKSHIN DINAJPUR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1172 | DARJEELING |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1173 | HOOGHLY |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1174 | HOWRAH |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1175 | JALPAIGURI |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1176 | JHARGRAM |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1177 | KALIMPONG |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1178 | MALDAH |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1179 | MURSHIDABAD |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1180 | NADIA |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1181 | NORTH 24 PARGANAS |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1182 | PASCHIM BARDHAMAN |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1183 | PASCHIM MEDINIPUR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1184 | PURBA BARDHAMAN |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1185 | PURBA MEDINIPUR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1186 | PURULIA |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1187 | SOUTH 24 PARGANAS |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1188 | UTTAR DINAJPUR |  | Siliguri W/S Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awarness generation Activities through Wall painting and Miking in the village having house connection through PWSS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities. |  |  | BILL/00120/2022-2023 | BP-2022-23-140 | 13/03/2023 | 13/03/2023 | DISTRICT MAGISTRATE, DARJEELING | 12.4 | 0 | 0 | 0
1189 | ALIPURDUAR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1190 | BANKURA |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1191 | BIRBHUM |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1192 | COOCHBEHAR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1193 | DAKSHIN DINAJPUR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1194 | DARJEELING |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1195 | HOOGHLY |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1196 | HOWRAH |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1197 | JALPAIGURI |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1198 | JHARGRAM |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1199 | KALIMPONG |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1200 | MALDAH |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1201 | MURSHIDABAD |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1202 | NADIA |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1203 | NORTH 24 PARGANAS |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1204 | PASCHIM BARDHAMAN |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1205 | PASCHIM MEDINIPUR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1206 | PURBA BARDHAMAN |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1207 | PURBA MEDINIPUR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1208 | PURULIA |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1209 | SOUTH 24 PARGANAS |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1210 | UTTAR DINAJPUR |  | Purulia Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Purulia in connection with IEC Activities Fund for awareness programme. |  |  | BILL/00406/2022-2023 | BP-2022-23-785 | 23/03/2023 | 23/03/2023 | DISTRICT MAGISTRATE | 22.8 | 0 | 0 | 0
1211 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1212 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1213 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1214 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1215 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1216 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1217 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1218 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1219 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1220 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1221 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1222 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1223 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1224 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1225 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1226 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1227 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1228 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1229 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1230 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1231 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1232 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Bandana Art |  |  | BILL/00250/2023-2024 | BP-2023-24-50 | 31/05/2023 | 31/05/2023 | BANDANA ART | 0.86 | 0 | 0 | 0
1233 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1234 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1235 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1236 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1237 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1238 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1239 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1240 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1241 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1242 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1243 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1244 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1245 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1246 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1247 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1248 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1249 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1250 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1251 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1252 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1253 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1254 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities |  |  | BILL/00723/2023-2024 | BP-2023-24-366 | 12/10/2023 | 12/10/2023 | DISTRICT PANCHAYAT & RURAL DEV. OFFICER, HOWRAH | 24.77 | 0 | 0 | 0
1255 | ALIPURDUAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1256 | BANKURA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1257 | BIRBHUM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1258 | COOCHBEHAR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1259 | DAKSHIN DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1260 | DARJEELING |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1261 | HOOGHLY |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1262 | HOWRAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1263 | JALPAIGURI |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1264 | JHARGRAM |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1265 | KALIMPONG |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1266 | MALDAH |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1267 | MURSHIDABAD |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1268 | NADIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1269 | NORTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1270 | PASCHIM BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1271 | PASCHIM MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1272 | PURBA BARDHAMAN |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1273 | PURBA MEDINIPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1274 | PURULIA |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1275 | SOUTH 24 PARGANAS |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1276 | UTTAR DINAJPUR |  | Malda Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activety |  |  | BILL/00338/2022-2023 | BP-2022-23-156 | 31/01/2023 | 31/01/2023 | ADDITIONAL DISTRIEL MAGISTRATE MALDA A.E.O.M.Z.P.M | 47.2 | 0 | 0 | 0
1277 | ALIPURDUAR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1278 | BANKURA |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1279 | BIRBHUM |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1280 | COOCHBEHAR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1281 | DAKSHIN DINAJPUR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1282 | DARJEELING |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1283 | HOOGHLY |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1284 | HOWRAH |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1285 | JALPAIGURI |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1286 | JHARGRAM |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1287 | KALIMPONG |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1288 | MALDAH |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1289 | MURSHIDABAD |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1290 | NADIA |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1291 | NORTH 24 PARGANAS |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1292 | PASCHIM BARDHAMAN |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1293 | PASCHIM MEDINIPUR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1294 | PURBA BARDHAMAN |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1295 | PURBA MEDINIPUR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1296 | PURULIA |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1297 | SOUTH 24 PARGANAS |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1298 | UTTAR DINAJPUR |  | Barasat Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC |  |  |  | BILL/00295/2023-2024 | BP-2023-24-6 | 19/04/2023 | 19/04/2023 | PGS DISASTER RISK MANAGEMENT PROGARA. | 52.8 | 0 | 0 | 0
1299 | ALIPURDUAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1300 | BANKURA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1301 | BIRBHUM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1302 | COOCHBEHAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1303 | DAKSHIN DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1304 | DARJEELING |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1305 | HOOGHLY |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1306 | HOWRAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1307 | JALPAIGURI |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1308 | JHARGRAM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1309 | KALIMPONG |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1310 | MALDAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1311 | MURSHIDABAD |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1312 | NADIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1313 | NORTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1314 | PASCHIM BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1315 | PASCHIM MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1316 | PURBA BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1317 | PURBA MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1318 | PURULIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1319 | SOUTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1320 | UTTAR DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 34 villages within Tamluk Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000271/2023-2024 | 548/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 6.55 | 6.26 | 95.53 | 0
1321 | ALIPURDUAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1322 | BANKURA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1323 | BIRBHUM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1324 | COOCHBEHAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1325 | DAKSHIN DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1326 | DARJEELING |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1327 | HOOGHLY |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1328 | HOWRAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1329 | JALPAIGURI |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1330 | JHARGRAM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1331 | KALIMPONG |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1332 | MALDAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1333 | MURSHIDABAD |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1334 | NADIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1335 | NORTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1336 | PASCHIM BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1337 | PASCHIM MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1338 | PURBA BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1339 | PURBA MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1340 | PURULIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1341 | SOUTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1342 | UTTAR DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 18 villages within Digha and Haldia Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000269/2023-2024 | 547/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 3.48 | 2.55 | 73.16 | 0
1343 | ALIPURDUAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1344 | BANKURA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1345 | BIRBHUM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1346 | COOCHBEHAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1347 | DAKSHIN DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1348 | DARJEELING |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1349 | HOOGHLY |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1350 | HOWRAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1351 | JALPAIGURI |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1352 | JHARGRAM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1353 | KALIMPONG |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1354 | MALDAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1355 | MURSHIDABAD |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1356 | NADIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1357 | NORTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1358 | PASCHIM BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1359 | PASCHIM MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1360 | PURBA BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1361 | PURBA MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1362 | PURULIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1363 | SOUTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1364 | UTTAR DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 06 villages of Nandigram and Lakshya-I GP within Haldia Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000273/2023-2024 | 549/TD | 12/05/2023 | 01/06/2023 | SUDIP MANNA | 0.95 | 0.81 | 85.14 | 0
1365 | ALIPURDUAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1366 | BANKURA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1367 | BIRBHUM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1368 | COOCHBEHAR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1369 | DAKSHIN DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1370 | DARJEELING |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1371 | HOOGHLY |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1372 | HOWRAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1373 | JALPAIGURI |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1374 | JHARGRAM |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1375 | KALIMPONG |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1376 | MALDAH |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1377 | MURSHIDABAD |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1378 | NADIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1379 | NORTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1380 | PASCHIM BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1381 | PASCHIM MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1382 | PURBA BARDHAMAN |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1383 | PURBA MEDINIPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1384 | PURULIA |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1385 | SOUTH 24 PARGANAS |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1386 | UTTAR DINAJPUR |  | Tamluk Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Fixing of Swajal Gram Display Board at 38 villages within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000274/2023-2024 | 550/TD | 12/05/2023 | 11/06/2023 | MISHRA ENTERPRISE | 7.35 | 7.23 | 98.41 | 0
1387 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1388 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1389 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1390 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1391 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1392 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1393 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1394 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1395 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1396 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1397 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1398 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1399 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1400 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1401 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1402 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1403 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1404 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1405 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1406 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1407 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1408 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Lalpur G.P-01 no, Sankarpur G.P-01 no) under Mathurapur-I Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-E) |  |  | ORD/000599/2023-2024 | 292/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.68 | 0.68 | 100 | 45
1409 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1410 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1411 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1412 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1413 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1414 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1415 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1416 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1417 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1418 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1419 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1420 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1421 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1422 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1423 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1424 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1425 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1426 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1427 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1428 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1429 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1430 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Baruipur and Joynagar-I block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000505/2024-2025 | 2677/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.74 | 0 | 0 | 0
1431 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1432 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1433 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1434 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1435 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1436 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1437 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1438 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1439 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1440 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1441 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1442 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1443 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1444 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1445 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1446 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1447 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1448 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1449 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1450 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1451 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1452 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Sonarpur, Bhangar-I and Mandirbazar under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000507/2024-2025 | 2678/AD | 22/06/2024 | 22/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 4.59 | 0 | 0 | 0
1453 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1454 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1455 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1456 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1457 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1458 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1459 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1460 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1461 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1462 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1463 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1464 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1465 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1466 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1467 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1468 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1469 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1470 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1471 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1472 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1473 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1474 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Wall writing of IEC messages along with logo pictures etc. of multiple colour as will be supplied by the PHE Dte. on smooth wall surface at Budge Budge -I Budge -II & Thakurpur Mahestala Block under Alipore Division, PHE Dte. | Assistant Engineer,HQ-II | Junior Engineer-2 | ORD/000504/2024-2025 | 2647/AD | 21/06/2024 | 21/07/2024 | HARISCHANDRAPUR PALLY UNNAYAN SAMITY | 3.21 | 0 | 0 | 0
1475 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1476 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1477 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1478 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1479 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1480 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1481 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1482 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1483 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1484 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1485 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1486 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1487 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1488 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1489 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1490 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1491 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1492 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1493 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1494 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1495 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1496 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000504/2022-2023 | 3366/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.49 | 0.49 | 99.99 | 100
1497 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1498 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1499 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1500 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1501 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1502 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1503 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1504 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1505 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1506 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1507 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1508 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1509 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1510 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1511 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1512 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1513 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1514 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1515 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1516 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1517 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1518 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply , Fitting and Fixing of sign boards in different schemes under Alipurduar Division , P.H.E Dte. ( Part - A) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000506/2022-2023 | 3365/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.95 | 0.94 | 99.78 | 100
1519 | ALIPURDUAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1520 | BANKURA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1521 | BIRBHUM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1522 | COOCHBEHAR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1523 | DAKSHIN DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1524 | DARJEELING |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1525 | HOOGHLY |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1526 | HOWRAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1527 | JALPAIGURI |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1528 | JHARGRAM |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1529 | KALIMPONG |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1530 | MALDAH |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1531 | MURSHIDABAD |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1532 | NADIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1533 | NORTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1534 | PASCHIM BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1535 | PASCHIM MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1536 | PURBA BARDHAMAN |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1537 | PURBA MEDINIPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1538 | PURULIA |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1539 | SOUTH 24 PARGANAS |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1540 | UTTAR DINAJPUR |  | Murshidabad Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Continuation Order for Broadcast of 15 minutes sponsored programme through All India Radio, Murshidabad. Media Plan For 26 (Twenty Six) Weeks i.e. July2023 to Dec2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000262/2023-2024 | 1697/MURD | 28/06/2023 | 28/12/2023 | NAYA SANYOG | 1.34 | 1.34 | 100 | 100
1541 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1542 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1543 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1544 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1545 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1546 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1547 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1548 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1549 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1550 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1551 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1552 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1553 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1554 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1555 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1556 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1557 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1558 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1559 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1560 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1561 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1562 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-02 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) |  |  | ORD/000596/2023-2024 | 288/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1563 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1564 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1565 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1566 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1567 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1568 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1569 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1570 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1571 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1572 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1573 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1574 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1575 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1576 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1577 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1578 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1579 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1580 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1581 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1582 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1583 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1584 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Kalatalahat GP-01 no, Khorda G.P-01 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) |  |  | ORD/000597/2023-2024 | 289/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 95
1585 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1586 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1587 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1588 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1589 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1590 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1591 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1592 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1593 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1594 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1595 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1596 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1597 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1598 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1599 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1600 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1601 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1602 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1603 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1604 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1605 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1606 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Khorda G.P-02 no) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-D) |  |  | ORD/000598/2023-2024 | 291/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.67 | 0.67 | 100 | 95
1607 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1608 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1609 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1610 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1611 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1612 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1613 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1614 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1615 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1616 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1617 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1618 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1619 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1620 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1621 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1622 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1623 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1624 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1625 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1626 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1627 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1628 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 01(One) no. display board related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bally-I G.P-01 no) under Gosaba Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-F) |  |  | ORD/000600/2023-2024 | 293/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.35 | 0.35 | 100 | 80
1629 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1630 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1631 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1632 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1633 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1634 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1635 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1636 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1637 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1638 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1639 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1640 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1641 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1642 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1643 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1644 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1645 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1646 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1647 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1648 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1649 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1650 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Erection of 02(Two) nos. display boards related to Swajal Gram on a permanent structure at the entry point of each Swajal Gram or any other prominent places at (Bhadura Haridas G.P-01 no, Kalatalahat G.P-01 no.) under Diamond Harbour-II Dev. Block in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) |  |  | ORD/000594/2023-2024 | 287/RWS | 01/08/2023 | 08/08/2023 | M & M GRAPHICS | 0.66 | 0.66 | 100 | 90
1651 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1652 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1653 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1654 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1655 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1656 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1657 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1658 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1659 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1660 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1661 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1662 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1663 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1664 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1665 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1666 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1667 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1668 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1669 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1670 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1671 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1672 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction of Typical Swajal Gram Display Board for different schemes under Howrah Division, PHE Dte (Part-C) | AE HQ |  | ORD/000226/2023-2024 | 2817/HD | 03/08/2023 | 18/08/2023 | ABONTICA ENTERPRISE | 0.96 | 0.95 | 98.43 | 100
1673 | ALIPURDUAR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1674 | BANKURA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1675 | BIRBHUM |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1676 | COOCHBEHAR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1677 | DAKSHIN DINAJPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1678 | DARJEELING |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1679 | HOOGHLY |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1680 | HOWRAH |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1681 | JALPAIGURI |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1682 | JHARGRAM |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1683 | KALIMPONG |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1684 | MALDAH |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1685 | MURSHIDABAD |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1686 | NADIA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1687 | NORTH 24 PARGANAS |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1688 | PASCHIM BARDHAMAN |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1689 | PASCHIM MEDINIPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1690 | PURBA BARDHAMAN |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1691 | PURBA MEDINIPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1692 | PURULIA |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1693 | SOUTH 24 PARGANAS |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1694 | UTTAR DINAJPUR |  | Hooghly Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000531/2023-2024 | 3053/HUG | 11/10/2023 | 11/04/2024 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 22.16 | 40.13 | 74
1695 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1696 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1697 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1698 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1699 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1700 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1701 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1702 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1703 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1704 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1705 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1706 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1707 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1708 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1709 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1710 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1711 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1712 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1713 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1714 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1715 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1716 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Construction and operation of stall of PHED in the 18th Dooars Utsav 2023 at Alipurduar Parade Ground , Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000362/2023-2024 | 2849/ALD | 22/12/2023 | 24/12/2023 | M/S SARKAR & CO | 5.76 | 5.69 | 98.78 | 100
1717 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1718 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1719 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1720 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1721 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1722 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1723 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1724 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1725 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1726 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1727 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1728 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1729 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1730 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1731 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1732 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1733 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1734 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1735 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1736 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1737 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1738 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000363/2023-2024 | 2850/ALD | 22/12/2023 | 24/12/2023 | SATYABRATA BHATTACHERJEE | 5.94 | 5.67 | 95.51 | 100
1739 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1740 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1741 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1742 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1743 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1744 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1745 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1746 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1747 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1748 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1749 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1750 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1751 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1752 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1753 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1754 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1755 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1756 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1757 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1758 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1759 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1760 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Extension of Drinking Water Supply and sanitary arrangement for 18th Dooars Utsav, 2023 at Parade Ground Alipurduar. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000373/2023-2024 | 70/ALD | 08/01/2024 | 10/01/2024 | M/S SARKAR & CO | 2.56 | 1.6 | 62.53 | 100
1761 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1762 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1763 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1764 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1765 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1766 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1767 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1768 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1769 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1770 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1771 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1772 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1773 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1774 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1775 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1776 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1777 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1778 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1779 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1780 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1781 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1782 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board ( 7NOS) at different PWSS under Garopara, Rajabhatkhawa, Latabari GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000374/2023-2024 | 71/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.85 | 0.85 | 100 | 100
1783 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1784 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1785 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1786 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1787 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1788 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1789 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1790 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1791 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1792 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1793 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1794 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1795 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1796 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1797 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1798 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1799 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1800 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1801 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1802 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1803 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1804 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (6 NOS) at different PWSS under Mendabari & Chuapara GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000376/2023-2024 | 73/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.73 | 0.73 | 100 | 100
1805 | ALIPURDUAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1806 | BANKURA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1807 | BIRBHUM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1808 | COOCHBEHAR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1809 | DAKSHIN DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1810 | DARJEELING |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1811 | HOOGHLY |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1812 | HOWRAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1813 | JALPAIGURI |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1814 | JHARGRAM |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1815 | KALIMPONG |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1816 | MALDAH |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1817 | MURSHIDABAD |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1818 | NADIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1819 | NORTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1820 | PASCHIM BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1821 | PASCHIM MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1822 | PURBA BARDHAMAN |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1823 | PURBA MEDINIPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1824 | PURULIA |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1825 | SOUTH 24 PARGANAS |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1826 | UTTAR DINAJPUR |  | Alipurduar Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | Supply & Installation of sign board (5 NOS) at different PWSS under Malangi & Kalchini GP under Kalchini Block Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000375/2023-2024 | 72/ALD | 08/01/2024 | 07/02/2024 | M/S SARKAR & CO | 0.61 | 0.61 | 100 | 100
1827 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1828 | BANKURA |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1829 | BIRBHUM |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1830 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1831 | DAKSHIN DINAJPUR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1832 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1833 | HOOGHLY |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1834 | HOWRAH |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1835 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1836 | JHARGRAM |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1837 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1838 | MALDAH |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1839 | MURSHIDABAD |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1840 | NADIA |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1841 | NORTH 24 PARGANAS |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1842 | PASCHIM BARDHAMAN |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1843 | PASCHIM MEDINIPUR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1844 | PURBA BARDHAMAN |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1845 | PURBA MEDINIPUR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1846 | PURULIA |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1847 | SOUTH 24 PARGANAS |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1848 | UTTAR DINAJPUR |  | Neorakhola W/S & Mtc.Div. | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | DISTRICT MAGISTRATE payment |  |  | BILL/00846/2023-2024 | BP-2023-24-449 | 20/01/2024 | 20/01/2024 | DISTRICT MAGISTRATE KALIMPONG DISTRICT | 12.8 | 0 | 0 | 0
1849 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1850 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1851 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1852 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1853 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1854 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1855 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1856 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1857 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1858 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1859 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1860 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1861 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1862 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1863 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1864 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1865 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1866 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1867 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1868 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1869 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1870 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00400/2024-2025 | BP-2024-25-244 | 06/08/2024 | 06/08/2024 | AMTA BOI O SANSKRITI MELA SAMITY | 0.3 | 0 | 0 | 0
1871 | ALIPURDUAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1872 | BANKURA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1873 | BIRBHUM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1874 | COOCHBEHAR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1875 | DAKSHIN DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1876 | DARJEELING |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1877 | HOOGHLY |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1878 | HOWRAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1879 | JALPAIGURI |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1880 | JHARGRAM |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1881 | KALIMPONG |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1882 | MALDAH |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1883 | MURSHIDABAD |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1884 | NADIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1885 | NORTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1886 | PASCHIM BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1887 | PASCHIM MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1888 | PURBA BARDHAMAN |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1889 | PURBA MEDINIPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1890 | PURULIA |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1891 | SOUTH 24 PARGANAS |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1892 | UTTAR DINAJPUR |  | Alipore Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | To charges of making 1000sq.ft. of PHE pavilion with super structure false ceiling, chair, table including electricity charges in the 27th Sundarban Kristi Mela o Loko Sanskriti Utsab, Organized by Kultali Milan Tirtha Society. |  |  | BILL/02744/2023-2024 |  | 09/02/2024 | 09/02/2024 | SUNDARBAN KRISTI MELA O LOKO SANSKRITI UTSAB KULTALI MILON TIRTHA SOCIETY | 12 | 0 | 0 | 0
1893 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1894 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1895 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1896 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1897 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1898 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1899 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1900 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1901 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1902 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1903 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1904 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1905 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1906 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1907 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1908 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1909 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1910 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1911 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1912 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1913 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1914 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00399/2024-2025 | BP-2024-25-240 | 06/08/2024 | 06/08/2024 | RAYBHAGINI RANI BHABASHANKARI SMIRITI RAKSHYA SAMITY | 0.4 | 0 | 0 | 0
1915 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1916 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1917 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1918 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1919 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1920 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1921 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1922 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1923 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1924 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1925 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1926 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1927 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1928 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1929 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1930 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1931 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1932 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1933 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1934 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1935 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1936 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00397/2024-2025 | BP-2024-25-238 | 06/08/2024 | 06/08/2024 | AMTA SAMRITI UTSAV COMMITTEE | 1.5 | 0 | 0 | 0
1937 | ALIPURDUAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1938 | BANKURA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1939 | BIRBHUM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1940 | COOCHBEHAR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1941 | DAKSHIN DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1942 | DARJEELING |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1943 | HOOGHLY |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1944 | HOWRAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1945 | JALPAIGURI |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1946 | JHARGRAM |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1947 | KALIMPONG |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1948 | MALDAH |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1949 | MURSHIDABAD |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1950 | NADIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1951 | NORTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1952 | PASCHIM BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1953 | PASCHIM MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1954 | PURBA BARDHAMAN |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1955 | PURBA MEDINIPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1956 | PURULIA |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1957 | SOUTH 24 PARGANAS |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
1958 | UTTAR DINAJPUR |  | Howrah Division | IEC/Awareness generation Activities through Wall painting and Miking in the village having house connection through PWS in collaboration with panchayat and Rural Development Department, Govt. of West Bengal under Jal Jeevan Mission Support Activities | SM/13541 | Support-IEC | IEC activities at different Rural PWSS and Book Fair Public gatherings etc to create Mass Awareness regarding judicious use of portable water through FHTC |  |  | BILL/00398/2024-2025 | BP-2024-25-239 | 06/08/2024 | 06/08/2024 | SARAT MELA CELEBRATION COMMITTEE | 0.35 | 0 | 0 | 0
Total | [13 empty] | 21706.3 | 3381.55 | 15.58