## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
2 | BANKURA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
3 | BIRBHUM |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
4 | COOCHBEHAR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
5 | DAKSHIN DINAJPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
6 | DARJEELING |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
7 | HOOGHLY |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
8 | HOWRAH |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
9 | JALPAIGURI |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
10 | JHARGRAM |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
11 | KALIMPONG |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
12 | MALDAH |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
14 | NADIA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
15 | NORTH 24 PARGANAS |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
16 | PASCHIM BARDHAMAN |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
17 | PASCHIM MEDINIPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
18 | PURBA BARDHAMAN |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
19 | PURBA MEDINIPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
20 | PURULIA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
21 | SOUTH 24 PARGANAS |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
22 | UTTAR DINAJPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition,Alteration & Modification of Civil Construction work at District Laboratory in Compliance with guideline of NABL Accredation under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/000741/2021-2022 | 2747/MURD | 03/09/2021 | 13/09/2021 | M H SUPPLIERS | 11.86 | 8.82 | 74.43 | 0
23 | ALIPURDUAR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
24 | BANKURA |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
25 | BIRBHUM |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
26 | COOCHBEHAR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
27 | DAKSHIN DINAJPUR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
28 | DARJEELING |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
29 | HOOGHLY |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
30 | HOWRAH |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
31 | JALPAIGURI |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
32 | JHARGRAM |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
33 | KALIMPONG |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
34 | MALDAH |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
35 | MURSHIDABAD |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
36 | NADIA |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
37 | NORTH 24 PARGANAS |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
38 | PASCHIM BARDHAMAN |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
39 | PASCHIM MEDINIPUR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
40 | PURBA BARDHAMAN |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
41 | PURBA MEDINIPUR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
42 | PURULIA |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
43 | SOUTH 24 PARGANAS |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
44 | UTTAR DINAJPUR |  | Tamluk Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Contai Sub-District Water Testing Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000047/2021-2022 | 246/TD | 24/06/2021 | 24/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 1.18 | 24.33 | 0
45 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
46 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
47 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
48 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
49 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
50 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
51 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
52 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
53 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
54 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
55 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
56 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
57 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
58 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
59 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
60 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
61 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
62 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
63 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
64 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
65 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
66 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Ahmedpur Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist:Birbhum. (Sl. No. - 01) | AE | JE1 | ORD/001152/2021-2022 | 387/BSSD | 10/12/2021 | 25/12/2021 | BISWARUP GHOSH | 0.8 | 0.75 | 93.58 | 100
67 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
68 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
69 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
70 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
71 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
72 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
73 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
74 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
75 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
76 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
77 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
78 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
79 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
80 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
81 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
82 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
83 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
84 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
85 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
86 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
87 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
88 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Proposed renovation for NABL recognition of Patelnagar Sub District Laboratory under Birbhum Division P.H.E. Dte. Dist: Birbhum. (Sl. No. - 02) | AE | Estimator | ORD/001195/2021-2022 | 354/BSSD | 27/10/2021 | 11/11/2021 | NEEL ENTERPRISE | 0.99 | 0.95 | 96.36 | 100
89 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
90 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
91 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
92 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
93 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
94 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
95 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
96 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
97 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
98 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
99 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
100 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
101 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
102 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
103 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
104 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
105 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
106 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
107 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
108 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
109 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
110 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Acceptance cum formal work order for Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Gazole Sub-District Water Testing Laboratory under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000005/2022-2023 | 1063/MD | 02/05/2022 | 17/05/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.19 | 4.19 | 100 | 0
111 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
112 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
113 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
114 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
115 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
116 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
117 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
118 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
119 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
120 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
121 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
122 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
123 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
124 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
125 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
126 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
127 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
128 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
129 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
130 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
131 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
132 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and glassware for the 15 (fifteen) nos. of water testing laboratories in the district of South 24 Parganas under Alipore Division, PHE Dte for the a period of 365 days. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000675/2022-2023 | 6179/AD | 01/11/2022 | 01/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.37 | 8.37 | 100 | 0
133 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
134 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
135 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
136 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
137 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
138 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
139 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
140 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
141 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
142 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
143 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
144 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
145 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
146 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
147 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
148 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
149 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
150 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
151 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
152 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
153 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
154 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist, One Laboratory Assistant and One Sampling Assistant for Gidhni Sub District lab.) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Lalgarh Sub-District Laboratory & (B) Gidhni Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer-III | ORD/000098/2022-2023 | 604/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 7.4 | 7.4 | 99.97 | 100
155 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
156 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
157 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
158 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
159 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
160 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
161 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
162 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
163 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
164 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
165 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
166 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
167 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
168 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
169 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
170 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
171 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
172 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
173 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
174 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
175 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
176 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory, Diamond Harbour Sub-District Water Testing Laboratory, Buita Sub-District Water Testing Laboratory, Canning Sub-District Water Testing Laboratory, Basanti Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-B) | Assistant Engineer, Canning sub division |  | ORD/001389/2022-2023 | 543/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
177 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
178 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
179 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
180 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
181 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
182 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
183 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
184 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
185 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
186 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
187 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
188 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
189 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
190 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
191 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
192 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
193 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
194 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
195 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
196 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
197 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
198 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (Kakdwip Sub-District Water Testing Laboratory, Sagar Mangal Sub-District Water Testing Laboratory, Bakkhali Sub-District Water Testing Laboratory, Ramganga Sub-District Water Testing Laboratory, Raidighi Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-C) | Assistant Engineer, Raidighi sub division |  | ORD/001390/2022-2023 | 544/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
199 | ALIPURDUAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
200 | BANKURA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
201 | BIRBHUM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
202 | COOCHBEHAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
203 | DAKSHIN DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
204 | DARJEELING |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
205 | HOOGHLY |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
206 | HOWRAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
207 | JALPAIGURI |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
208 | JHARGRAM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
209 | KALIMPONG |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
210 | MALDAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
211 | MURSHIDABAD |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
212 | NADIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
213 | NORTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
214 | PASCHIM BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
215 | PASCHIM MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
216 | PURBA BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
217 | PURBA MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
218 | PURULIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
219 | SOUTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
220 | UTTAR DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL Upgradation of Dist Lab in connection with safety shower & chemical instrument placement installation (PART A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2022-2023 | 732/CD | 27/08/2022 | 26/09/2022 | MS BIDYUT SARKAR | 9.72 | 9.45 | 97.15 | 0
221 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
222 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
223 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
224 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
225 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
226 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
227 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
228 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
229 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
230 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
231 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
232 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
233 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
234 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
235 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
236 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
237 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
238 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
239 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
240 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
241 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
242 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Gopiballavpur Sub-District Laboratory & (B) Belpahari Sub-District Laboratory within Jhargram Sub-Division under Jhargram Division, PHE Dte. [For the period of 12 (Twelve) months] (From 01.12.2022 to 30.11.2023) | Assistant Engineer |  | ORD/000099/2022-2023 | 605/JHD | 23/11/2022 | 23/11/2023 | CANVAS | 6.38 | 6.37 | 99.91 | 100
243 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
244 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
245 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
246 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
247 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
248 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
249 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
250 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
251 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
252 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
253 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
254 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
255 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
256 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
257 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
258 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
259 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
260 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
261 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
262 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
263 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
264 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Signboard updating for 05 nos. NABL Accredited/Recognized drinking water testing laboratories (South 24 Paraganas District Water Testing Laboratory, Amtala Sub-District Water Testing Laboratory, Baruipur WTP Sub-District Water Testing Laboratory, Dakshin Raipur Water Treatment Plant Laboratory,Ramkrishana Mission Lokasiksha Parishad, Narendrapur Sub-District Water Testing Laboratory) under South 24 Parganas District.(PART-A) | Assistant Engineer, RWS |  | ORD/001132/2022-2023 | 542/RWS | 01/11/2022 | 11/11/2022 | M & M GRAPHICS | 1 | 1 | 100 | 0
265 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
266 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
267 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
268 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
269 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
270 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
271 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
272 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
273 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
274 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
275 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
276 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
277 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
278 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
279 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
280 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
281 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
282 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
283 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
284 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
285 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
286 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Habibpur Sub District Laboratory and Bagula Sub District Laboratory at Ranaghat Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000425/2022-2023 | 224/Kly SD-I | 23/02/2023 | 25/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
287 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
288 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
289 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
290 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
291 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
292 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
293 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
294 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
295 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
296 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
297 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
298 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
299 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
300 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
301 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
302 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
303 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
304 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
305 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
306 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
307 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
308 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline at Krishnagar Sub District Laboratory and Krishnaganj Sub District Laboratory under Krishnagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000426/2022-2023 | 229/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.93 | 0.93 | 100 | 0
309 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
310 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
311 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
312 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
313 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
314 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
315 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
316 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
317 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
318 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
319 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
320 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
321 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
322 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
323 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
324 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
325 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
326 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
327 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
328 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
329 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
330 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments (Viz. pH Meter, Weight Box, Analytical balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & all digital indicator & any other measuring Instruments) at per NABL Guideline etc at Tehatta Sub District Laboratory at Tehatta Sub Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000427/2022-2023 | 232/Kly SD-I | 24/02/2023 | 26/03/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.6 | 0.6 | 100 | 0
331 | ALIPURDUAR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
332 | BANKURA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
333 | BIRBHUM |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
334 | COOCHBEHAR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
335 | DAKSHIN DINAJPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
336 | DARJEELING |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
337 | HOOGHLY |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
338 | HOWRAH |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
339 | JALPAIGURI |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
340 | JHARGRAM |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
341 | KALIMPONG |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
342 | MALDAH |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
343 | MURSHIDABAD |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
344 | NADIA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
345 | NORTH 24 PARGANAS |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
346 | PASCHIM BARDHAMAN |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
347 | PASCHIM MEDINIPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
348 | PURBA BARDHAMAN |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
349 | PURBA MEDINIPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
350 | PURULIA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
351 | SOUTH 24 PARGANAS |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
352 | UTTAR DINAJPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Silampur Sub District Laboratory, under Howrah Division PHE Dte. | AE HQ |  | ORD/000115/2023-2024 | 2207/HD | 12/06/2023 | 27/06/2023 | M/S LAXMI ENTERPRISE | 1.3 | 0 | 0 | 0
353 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
354 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
355 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
356 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
357 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
358 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
359 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
360 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
361 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
362 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
363 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
364 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
365 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
366 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
367 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
368 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
369 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
370 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
371 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
372 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
373 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
374 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Balupur WTP Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer |  | ORD/000559/2023-2024 | 3730/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
375 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
376 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
377 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
378 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
379 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
380 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
381 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
382 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
383 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
384 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
385 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
386 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
387 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
388 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
389 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
390 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
391 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
392 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
393 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
394 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
395 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
396 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Gazole Sub District Laboratoty under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000561/2023-2024 | 3732/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
397 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
398 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
399 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
400 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
401 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
402 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
403 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
404 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
405 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
406 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
407 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
408 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
409 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
410 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
411 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
412 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
413 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
414 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
415 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
416 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
417 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
418 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Bulbulchandi Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000560/2023-2024 | 3731/MD | 26/09/2023 | 26/10/2023 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
419 | ALIPURDUAR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
420 | BANKURA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
421 | BIRBHUM |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
422 | COOCHBEHAR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
423 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
424 | DARJEELING |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
425 | HOOGHLY |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
426 | HOWRAH |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
427 | JALPAIGURI |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
428 | JHARGRAM |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
429 | KALIMPONG |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
430 | MALDAH |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
431 | MURSHIDABAD |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
432 | NADIA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
433 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
434 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
435 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
436 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
437 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
438 | PURULIA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
439 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
440 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of Kashipur Sub District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer |  | ORD/000676/2023-2024 | 1360/PD | 13/09/2023 | 11/03/2024 | BOSE CONSTRUCTION | 19.42 | 0 | 0 | 0
441 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
442 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
443 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
444 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
445 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
446 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
447 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
448 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
449 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
450 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
451 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
452 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
453 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
454 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
455 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
456 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
457 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
458 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
459 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
460 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
461 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
462 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at JANGIPARA SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000637/2023-2024 | 379-HQ-HUG. | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
463 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
464 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
465 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
466 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
467 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
468 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
469 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
470 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
471 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
472 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
473 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
474 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
475 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
476 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
477 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
478 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
479 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
480 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
481 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
482 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
483 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
484 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at NETAJI MAHAVIDYALAYA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000635/2023-2024 | 377/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
485 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
486 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
487 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
488 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
489 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
490 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
491 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
492 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
493 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
494 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
495 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
496 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
497 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
498 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
499 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
500 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
501 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
502 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
503 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
504 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
505 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
506 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at HARIPAL SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000639/2023-2024 | 380/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
507 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
508 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
509 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
510 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
511 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
512 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
513 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
514 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
515 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
516 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
517 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
518 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
519 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
520 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
521 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
522 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
523 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
524 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
525 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
526 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
527 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
528 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at SERAMPORE SUB DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000636/2023-2024 | 378/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
529 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
530 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
531 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
532 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
533 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
534 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
535 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
536 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
537 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
538 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
539 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
540 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
541 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
542 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
543 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
544 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
545 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
546 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
547 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
548 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
549 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
550 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000640/2023-2024 | 382/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
551 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
552 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
553 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
554 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
555 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
556 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
557 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
558 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
559 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
560 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
561 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
562 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
563 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
564 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
565 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
566 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
567 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
568 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
569 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
570 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
571 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
572 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory at KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000642/2023-2024 | 383/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
573 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
574 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
575 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
576 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
577 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
578 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
579 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
580 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
581 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
582 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
583 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
584 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
585 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
586 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
587 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
588 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
589 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
590 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
591 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
592 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
593 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
594 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at AMARTYA RURAL WELFARE & RESEARCH CENTRE WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000641/2023-2024 | 381/HQ/HUG | 09/11/2023 | 19/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
595 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
596 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
597 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
598 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
599 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
600 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
601 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
602 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
603 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
604 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
605 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
606 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
607 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
608 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
609 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
610 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
611 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
612 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
613 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
614 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
615 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
616 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory at SARVIK VIVEKANANDA GRAM SEVA SANSTHA WATER TESTING LABORATORY under The Executive Engineer, Hooghly Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. | Assistant Engineer(HQ) |  | ORD/000643/2023-2024 | 384/HQ/HUG | 09/11/2023 | 19/11/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
617 | ALIPURDUAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
618 | BANKURA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
619 | BIRBHUM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
620 | COOCHBEHAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
621 | DAKSHIN DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
622 | DARJEELING |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
623 | HOOGHLY |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
624 | HOWRAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
625 | JALPAIGURI |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
626 | JHARGRAM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
627 | KALIMPONG |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
628 | MALDAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
629 | MURSHIDABAD |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
630 | NADIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
631 | NORTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
632 | PASCHIM BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
633 | PASCHIM MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
634 | PURBA BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
635 | PURBA MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
636 | PURULIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
637 | SOUTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
638 | UTTAR DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Execution of different works related to DISTRICT LAB KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000356/2023-2024 | 1340/CD | 24/11/2023 | 23/01/2024 | MS BIDYUT SARKAR | 8.75 | 0 | 0 | 0
639 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
640 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
641 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
642 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
643 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
644 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
645 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
646 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
647 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
648 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
649 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
650 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
651 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
652 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
653 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
654 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
655 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
656 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
657 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
658 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
659 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
660 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Hingalganj Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001673/2023-2024 | 1166/BST | 15/12/2023 | 14/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
661 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
662 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
663 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
664 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
665 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
666 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
667 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
668 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
669 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
670 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
671 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
672 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
673 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
674 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
675 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
676 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
677 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
678 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
679 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
680 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
681 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
682 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Youth Development Centre Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001675/2023-2024 | 1172/BST | 18/12/2023 | 17/03/2024 | LAB ANALYTICS | 0.9 | 0 | 0 | 0
683 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
684 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
685 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
686 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
687 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
688 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
689 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
690 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
691 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
692 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
693 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
694 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
695 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
696 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
697 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
698 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
699 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
700 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
701 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
702 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
703 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
704 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bithari Disha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001678/2023-2024 | 1197/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 100
705 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
706 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
707 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
708 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
709 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
710 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
711 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
712 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
713 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
714 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
715 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
716 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
717 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
718 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
719 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
720 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
721 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
722 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
723 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
724 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
725 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
726 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized West Bengal Comprehensive Area Development Corporation Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001674/2023-2024 | 1168/BST | 18/12/2023 | 17/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.9 | 0 | 0 | 0
727 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
728 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
729 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
730 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
731 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
732 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
733 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
734 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
735 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
736 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
737 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
738 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
739 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
740 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
741 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
742 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
743 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
744 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
745 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
746 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
747 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
748 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Pather Panchali Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001720/2023-2024 | 1198/BST | 29/12/2023 | 28/03/2024 | M/S LAXMI ENTERPRISE | 0.9 | 0 | 0 | 0
749 | ALIPURDUAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
750 | BANKURA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
751 | BIRBHUM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
752 | COOCHBEHAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
753 | DAKSHIN DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
754 | DARJEELING |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
755 | HOOGHLY |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
756 | HOWRAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
757 | JALPAIGURI |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
758 | JHARGRAM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
759 | KALIMPONG |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
760 | MALDAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
761 | MURSHIDABAD |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
762 | NADIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
763 | NORTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
764 | PASCHIM BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
765 | PASCHIM MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
766 | PURBA BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
767 | PURBA MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
768 | PURULIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
769 | SOUTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
770 | UTTAR DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD | Estimator | ORD/000297/2022-2023 | 537/RD/PHE | 22/02/2023 | 23/04/2023 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 14.33 | 13.46 | 93.9 | 100
771 | ALIPURDUAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
772 | BANKURA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
773 | BIRBHUM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
774 | COOCHBEHAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
775 | DAKSHIN DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
776 | DARJEELING |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
777 | HOOGHLY |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
778 | HOWRAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
779 | JALPAIGURI |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
780 | JHARGRAM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
781 | KALIMPONG |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
782 | MALDAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
783 | MURSHIDABAD |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
784 | NADIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
785 | NORTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
786 | PASCHIM BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
787 | PASCHIM MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
788 | PURBA BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
789 | PURBA MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
790 | PURULIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
791 | SOUTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
792 | UTTAR DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | Assistant Engineer RSD |  | ORD/000298/2022-2023 | 538/RD/PHE | 22/02/2023 | 23/04/2023 | UTSAV AGENCY UTSAVAGENCY@GMAIL.COM | 0.91 | 0.91 | 100 | 100
793 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
794 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
795 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
796 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
797 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
798 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
799 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
800 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
801 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
802 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
803 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
804 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
805 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
806 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
807 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
808 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
809 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
810 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
811 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
812 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
813 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
814 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 3rd Party to execute Calibration of Spectrophotometer, pH Meter, Turbiditymeter,Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, Measuring Cylinder of different volume, Thermometer & any other measuring instruments as per NABL traceability & conformity of North 24Parganas District Water Testing Laboratory under Barasat Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2022-2023 | 55/BST | 19/01/2023 | 19/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.55 | 0.55 | 100 | 100
815 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
816 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
817 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
818 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
819 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
820 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
821 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
822 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
823 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
824 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
825 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
826 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
827 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
828 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
829 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
830 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
831 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
832 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
833 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
834 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
835 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
836 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supplying,Fitting & Fixing vinyl printing on M.S steel plate for NABL Laboratory at Different place (10 Nos.) of Birbhum District within Birbhum Division, PHE Dte. | AE | JE | ORD/000618/2022-2023 | 183/BH | 30/01/2023 | 06/02/2023 | SOURAV MONDAL | 0.97 | 0.97 | 100.01 | 0
837 | ALIPURDUAR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
838 | BANKURA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
839 | BIRBHUM |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
840 | COOCHBEHAR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
841 | DAKSHIN DINAJPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
842 | DARJEELING |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
843 | HOOGHLY |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
844 | HOWRAH |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
845 | JALPAIGURI |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
846 | JHARGRAM |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
847 | KALIMPONG |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
848 | MALDAH |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
849 | MURSHIDABAD |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
850 | NADIA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
851 | NORTH 24 PARGANAS |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
852 | PASCHIM BARDHAMAN |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
853 | PASCHIM MEDINIPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
854 | PURBA BARDHAMAN |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
855 | PURBA MEDINIPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
856 | PURULIA |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
857 | SOUTH 24 PARGANAS |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
858 | UTTAR DINAJPUR |  | Murshidabad Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Addition, Alteration & Modification of Electrical works at District laboratory in compliance with guideline of NABL Accreditation under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000801/2022-2023 | 568/MURD | 28/02/2023 | 30/03/2023 | M H SUPPLIERS | 2.04 | 2.04 | 100 | 100
859 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
860 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
861 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
862 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
863 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
864 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
865 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
866 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
867 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
868 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
869 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
870 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
871 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
872 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
873 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
874 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
875 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
876 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
877 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
878 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
879 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
880 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Ghatal Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000154/2023-2024 | 218/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
881 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
882 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
883 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
884 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
885 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
886 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
887 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
888 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
889 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
890 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
891 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
892 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
893 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
894 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
895 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
896 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
897 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
898 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
899 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
900 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
901 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
902 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Chandrakona Municipality Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000155/2023-2024 | 219/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
903 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
904 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
905 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
906 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
907 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
908 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
909 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
910 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
911 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
912 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
913 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
914 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
915 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
916 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
917 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
918 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
919 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
920 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
921 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
922 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
923 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
924 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Garhbeta Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000156/2023-2024 | 225/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
925 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
926 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
927 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
928 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
929 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
930 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
931 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
932 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
933 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
934 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
935 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
936 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
937 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
938 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
939 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
940 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
941 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
942 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
943 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
944 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
945 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
946 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply delivery of Chemicals and other required items related to smooth functioning of NABL Recognition of Four (Belpahari, Gidhni, Gopiballavpur & Lalgarh) Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000101/2023-2024 | 166/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.53 | 0.53 | 100 | 100
947 | ALIPURDUAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
948 | BANKURA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
949 | BIRBHUM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
950 | COOCHBEHAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
951 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
952 | DARJEELING |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
953 | HOOGHLY |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
954 | HOWRAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
955 | JALPAIGURI |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
956 | JHARGRAM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
957 | KALIMPONG |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
958 | MALDAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
959 | MURSHIDABAD |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
960 | NADIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
961 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
962 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
963 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
964 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
965 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
966 | PURULIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
967 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
968 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of materials and calibration for Kalyani State Referral Laboratory (Prandhara, Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000115/2023-2024 | 310/AE-I/NAD-I | 28/07/2023 | 04/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
969 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
970 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
971 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
972 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
973 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
974 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
975 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
976 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
977 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
978 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
979 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
980 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
981 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
982 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
983 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
984 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
985 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
986 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
987 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
988 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
989 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
990 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Serbera Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000157/2023-2024 | 226/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
991 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
992 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
993 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
994 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
995 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
996 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
997 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
998 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
999 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1000 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1001 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1002 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1003 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1004 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1005 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1006 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1007 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1008 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1009 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1010 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1011 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1012 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000097/2023-2024 | 162/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1013 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1014 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1015 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1016 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1017 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1018 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1019 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1020 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1021 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1022 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1023 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1024 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1025 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1026 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1027 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1028 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1029 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1030 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1031 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1032 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1033 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1034 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2023-2024 | 163/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1035 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1036 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1037 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1038 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1039 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1040 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1041 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1042 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1043 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1044 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1045 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1046 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1047 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1048 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1049 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1050 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1051 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1052 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1053 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1054 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1055 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1056 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000099/2023-2024 | 164/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1057 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1058 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1059 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1060 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1061 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1062 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1063 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1064 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1065 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1066 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1067 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1068 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1069 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1070 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1071 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1072 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1073 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1074 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1075 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1076 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1077 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1078 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Belda Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000159/2023-2024 | 233/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1079 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1080 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1081 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1082 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1083 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1084 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1085 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1086 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1087 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1088 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1089 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1090 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1091 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1092 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1093 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1094 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1095 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1096 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1097 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1098 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1099 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1100 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Keshiary Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000160/2023-2024 | 234/RWS/MID | 06/06/2023 | 13/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1101 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1102 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1103 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1104 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1105 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1106 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1107 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1108 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1109 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1110 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1111 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1112 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1113 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1114 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1115 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1116 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1117 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1118 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1119 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1120 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1121 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1122 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Bhikni Nischintapur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000161/2023-2024 | 242/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1123 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1124 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1125 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1126 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1127 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1128 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1129 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1130 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1131 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1132 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1133 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1134 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1135 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1136 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1137 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1138 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1139 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1140 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1141 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1142 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1143 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1144 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer |  | ORD/000100/2023-2024 | 165/JRWS | 19/07/2023 | 03/08/2023 | ARUNALOY SCIENTIFIC HOUSE | 0.96 | 0.96 | 100 | 100
1145 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1146 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1147 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1148 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1149 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1150 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1151 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1152 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1153 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1154 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1155 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1156 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1157 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1158 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1159 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1160 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1161 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1162 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1163 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1164 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1165 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1166 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Kharagpur, Balichak, Gharal, C.K. Town & Garhbeta) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000162/2023-2024 | 243/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1167 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1168 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1169 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1170 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1171 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1172 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1173 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1174 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1175 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1176 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1177 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1178 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1179 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1180 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1181 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1182 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1183 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1184 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1185 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1186 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1187 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1188 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Five (Serbera, Dantan, Belda , Keshiary & Bhikni Nischintapur) Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000163/2023-2024 | 244/RWS/MID | 07/06/2023 | 14/06/2023 | UTSAV AGENCY | 0.66 | 0.66 | 100 | 100
1189 | ALIPURDUAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1190 | BANKURA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1191 | BIRBHUM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1192 | COOCHBEHAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1193 | DAKSHIN DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1194 | DARJEELING |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1195 | HOOGHLY |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1196 | HOWRAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1197 | JALPAIGURI |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1198 | JHARGRAM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1199 | KALIMPONG |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1200 | MALDAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1201 | MURSHIDABAD |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1202 | NADIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1203 | NORTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1204 | PASCHIM BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1205 | PASCHIM MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1206 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1207 | PURBA MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1208 | PURULIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1209 | SOUTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1210 | UTTAR DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Modification of Borshul Sub Dist. Laboratory for NABL accreditation by installing aluminium panel, aluminium door with glass and some other fitting work under Burdwan Division PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000408/2023-2024 | 422/AE/HQ | 02/08/2023 | 01/09/2023 | ANWESHA CONSTRUCTION | 0.57 | 0.56 | 98.07 | 100
1211 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1212 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1213 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1214 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1215 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1216 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1217 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1218 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1219 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1220 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1221 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1222 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1223 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1224 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1225 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1226 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1227 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1228 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1229 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1230 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1231 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1232 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Kharagpur Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000151/2023-2024 | 216/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1233 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1234 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1235 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1236 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1237 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1238 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1239 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1240 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1241 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1242 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1243 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1244 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1245 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1246 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1247 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1248 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1249 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1250 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1251 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1252 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1253 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1254 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of measuring instruments and other required items related to smooth functioning of NABL Accreditation of Medinipur District Water Testing Laboratory, under Midnapore Division PHE Dte. |  |  | ORD/000150/2023-2024 | 211/RWS/MID | 17/05/2023 | 16/06/2023 | UTSAV AGENCY | 0.54 | 0.52 | 96.76 | 100
1255 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1256 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1257 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1258 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1259 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1260 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1261 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1262 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1263 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1264 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1265 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1266 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1267 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1268 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1269 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1270 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1271 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1272 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1273 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1274 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1275 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1276 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Construction of Display Board at different District/Sub-District Water Testing Laboratory in different Blocks of Paschim Medinipur District under Midnapur Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2023-2024 | 379/RWS/MID | 17/07/2023 | 01/08/2023 | UTSAV AGENCY | 1.51 | 1.51 | 100 | 100
1277 | ALIPURDUAR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1278 | BANKURA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1279 | BIRBHUM |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1280 | COOCHBEHAR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1281 | DAKSHIN DINAJPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1282 | DARJEELING |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1283 | HOOGHLY |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1284 | HOWRAH |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1285 | JALPAIGURI |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1286 | JHARGRAM |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1287 | KALIMPONG |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1288 | MALDAH |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1289 | MURSHIDABAD |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1290 | NADIA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1291 | NORTH 24 PARGANAS |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1292 | PASCHIM BARDHAMAN |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1293 | PASCHIM MEDINIPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1294 | PURBA BARDHAMAN |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1295 | PURBA MEDINIPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1296 | PURULIA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1297 | SOUTH 24 PARGANAS |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1298 | UTTAR DINAJPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Alipurduar District water testing laboratory under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000307/2023-2024 | 2171/ALD | 06/10/2023 | 05/11/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1299 | ALIPURDUAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1300 | BANKURA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1301 | BIRBHUM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1302 | COOCHBEHAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1303 | DAKSHIN DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1304 | DARJEELING |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1305 | HOOGHLY |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1306 | HOWRAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1307 | JALPAIGURI |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1308 | JHARGRAM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1309 | KALIMPONG |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1310 | MALDAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1311 | MURSHIDABAD |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1312 | NADIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1313 | NORTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1314 | PASCHIM BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1315 | PASCHIM MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1316 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1317 | PURBA MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1318 | PURULIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1319 | SOUTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1320 | UTTAR DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Renovation, extension and modification of proposed Monteswar Water Testing Laboratory under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000707/2023-2024 | 4520/BWD | 12/10/2023 | 11/12/2023 | PRONAB KUMAR DEY | 6.36 | 5.82 | 91.59 | 100
1321 | ALIPURDUAR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1322 | BANKURA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1323 | BIRBHUM |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1324 | COOCHBEHAR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1325 | DAKSHIN DINAJPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1326 | DARJEELING |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1327 | HOOGHLY |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1328 | HOWRAH |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1329 | JALPAIGURI |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1330 | JHARGRAM |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1331 | KALIMPONG |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1332 | MALDAH |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1333 | MURSHIDABAD |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1334 | NADIA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1335 | NORTH 24 PARGANAS |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1336 | PASCHIM BARDHAMAN |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1337 | PASCHIM MEDINIPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1338 | PURBA BARDHAMAN |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1339 | PURBA MEDINIPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1340 | PURULIA |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1341 | SOUTH 24 PARGANAS |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1342 | UTTAR DINAJPUR |  | Purulia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Civil, Electrical & Sanitary plumbing works related to NABL Recognition of PARA Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 1361/PD | 13/09/2023 | 11/03/2024 | AMIT PATHAK | 19.42 | 19.29 | 99.37 | 100
1343 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1344 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1345 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1346 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1347 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1348 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1349 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1350 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1351 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1352 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1353 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1354 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1355 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1356 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1357 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1358 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1359 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1360 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1361 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1362 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1363 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1364 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Chanchal Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000510/2023-2024 | 3602/MD | 21/09/2023 | 21/10/2023 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 100
1365 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1366 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1367 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1368 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1369 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1370 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1371 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1372 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1373 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1374 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1375 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1376 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1377 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1378 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1379 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1380 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1381 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1382 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1383 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1384 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1385 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1386 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Canning Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000906/2023-2024 | 449/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1387 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1388 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1389 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1390 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1391 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1392 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1393 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1394 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1395 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1396 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1397 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1398 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1399 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1400 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1401 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1402 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1403 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1404 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1405 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1406 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1407 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1408 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Kakdwip Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000914/2023-2024 | 451/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1409 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1410 | BANKURA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1411 | BIRBHUM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1412 | COOCHBEHAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1413 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1414 | DARJEELING |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1415 | HOOGHLY |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1416 | HOWRAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1417 | JALPAIGURI |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1418 | JHARGRAM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1419 | KALIMPONG |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1420 | MALDAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1421 | MURSHIDABAD |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1422 | NADIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1423 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1424 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1425 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1426 | PURBA BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1427 | PURBA MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1428 | PURULIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1429 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1430 | UTTAR DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Chalsa Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000343/2023-2024 | 1113/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.77 | 86.08 | 100
1431 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1432 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1433 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1434 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1435 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1436 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1437 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1438 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1439 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1440 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1441 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1442 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1443 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1444 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1445 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1446 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1447 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1448 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1449 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1450 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1451 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1452 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Bakkhali Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000946/2023-2024 | 457/RWS | 03/10/2023 | 02/11/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1453 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1454 | BANKURA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1455 | BIRBHUM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1456 | COOCHBEHAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1457 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1458 | DARJEELING |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1459 | HOOGHLY |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1460 | HOWRAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1461 | JALPAIGURI |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1462 | JHARGRAM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1463 | KALIMPONG |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1464 | MALDAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1465 | MURSHIDABAD |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1466 | NADIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1467 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1468 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1469 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1470 | PURBA BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1471 | PURBA MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1472 | PURULIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1473 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1474 | UTTAR DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Water Quality Testing Block level Laboratory under The Executive Engineer, Jalpaiguri Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site surveillance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL: Dhupguri Sub-District Laboratory) | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1112/RWS | 27/09/2023 | 27/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
1475 | ALIPURDUAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1476 | BANKURA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1477 | BIRBHUM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1478 | COOCHBEHAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1479 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1480 | DARJEELING |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1481 | HOOGHLY |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1482 | HOWRAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1483 | JALPAIGURI |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1484 | JHARGRAM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1485 | KALIMPONG |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1486 | MALDAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1487 | MURSHIDABAD |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1488 | NADIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1489 | NORTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1490 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1491 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1492 | PURBA BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1493 | PURBA MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1494 | PURULIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1495 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1496 | UTTAR DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Procurement of services and consumables for continuance of NABL Accreditation for 11 mandatory water quality parameters of 16 District level drinking water testing laboratories throughout the Stateunder PHE Department, Govt. of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1307/RS | 24/04/2023 | 23/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 65.85 | 65.85 | 100 | 69
1497 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1498 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1499 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1500 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1501 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1502 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1503 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1504 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1505 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1506 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1507 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1508 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1509 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1510 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1511 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1512 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1513 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1514 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1515 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1516 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1517 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1518 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Basanti Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000911/2023-2024 | 450/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1519 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1520 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1521 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1522 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1523 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1524 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1525 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1526 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1527 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1528 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1529 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1530 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1531 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1532 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1533 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1534 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1535 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1536 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1537 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1538 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1539 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1540 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Diamond Harbour Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000941/2023-2024 | 453/RWS | 29/09/2023 | 29/10/2023 | DULAL MAJUMDER | 0.89 | 0.89 | 100 | 100
1541 | ALIPURDUAR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1542 | BANKURA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1543 | BIRBHUM |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1544 | COOCHBEHAR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1545 | DAKSHIN DINAJPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1546 | DARJEELING |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1547 | HOOGHLY |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1548 | HOWRAH |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1549 | JALPAIGURI |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1550 | JHARGRAM |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1551 | KALIMPONG |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1552 | MALDAH |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1553 | MURSHIDABAD |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1554 | NADIA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1555 | NORTH 24 PARGANAS |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1556 | PASCHIM BARDHAMAN |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1557 | PASCHIM MEDINIPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1558 | PURBA BARDHAMAN |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1559 | PURBA MEDINIPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1560 | PURULIA |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1561 | SOUTH 24 PARGANAS |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1562 | UTTAR DINAJPUR |  | Alipurduar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar RWS Sub-Division, PHE Dte. | Alipurduar RWS |  | ORD/000422/2022-2023 | 2825/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0.64 | 100 | 100
1563 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1564 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1565 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1566 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1567 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1568 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1569 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1570 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1571 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1572 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1573 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1574 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1575 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1576 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1577 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1578 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1579 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1580 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1581 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1582 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1583 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1584 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Balichak Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000152/2023-2024 | 217/RWS/MID | 26/05/2023 | 02/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1585 | ALIPURDUAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1586 | BANKURA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1587 | BIRBHUM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1588 | COOCHBEHAR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1589 | DAKSHIN DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1590 | DARJEELING |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1591 | HOOGHLY |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1592 | HOWRAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1593 | JALPAIGURI |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1594 | JHARGRAM |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1595 | KALIMPONG |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1596 | MALDAH |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1597 | MURSHIDABAD |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1598 | NADIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1599 | NORTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1600 | PASCHIM BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1601 | PASCHIM MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1602 | PURBA BARDHAMAN |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1603 | PURBA MEDINIPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1604 | PURULIA |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1605 | SOUTH 24 PARGANAS |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1606 | UTTAR DINAJPUR |  | Midnapore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition of Dantan Sub District Laboratory, under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000158/2023-2024 | 227/RWS/MID | 05/06/2023 | 12/06/2023 | UTSAV AGENCY | 0.96 | 0.96 | 100 | 100
1607 | ALIPURDUAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1608 | BANKURA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1609 | BIRBHUM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1610 | COOCHBEHAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1611 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1612 | DARJEELING |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1613 | HOOGHLY |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1614 | HOWRAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1615 | JALPAIGURI |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1616 | JHARGRAM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1617 | KALIMPONG |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1618 | MALDAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1619 | MURSHIDABAD |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1620 | NADIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1621 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1622 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1623 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1624 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1625 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1626 | PURULIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1627 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1628 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Providing NABL related expenses for renewal audit of Kalyani State referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000112/2023-2024 | 307/AE-I/NAD-I | 28/07/2023 | 27/08/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1629 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1630 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1631 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1632 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1633 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1634 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1635 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1636 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1637 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1638 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1639 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1640 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1641 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1642 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1643 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1644 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1645 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1646 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1647 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1648 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1649 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1650 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Estimates for chemicals and other required items related to smooth functioning of NABL Recognition of Buita Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer,HQ-II |  | ORD/000936/2023-2024 | 452/RWS | 29/09/2023 | 29/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0.88 | 100 | 95
1651 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1652 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1653 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1654 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1655 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1656 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1657 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1658 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1659 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1660 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1661 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1662 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1663 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1664 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1665 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1666 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1667 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1668 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1669 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1670 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1671 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1672 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Haroa Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001269/2023-2024 | 817/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1673 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1674 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1675 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1676 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1677 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1678 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1679 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1680 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1681 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1682 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1683 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1684 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1685 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1686 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1687 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1688 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1689 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1690 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1691 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1692 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1693 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1694 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Gokna Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001270/2023-2024 | 819/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1695 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1696 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1697 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1698 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1699 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1700 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1701 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1702 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1703 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1704 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1705 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1706 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1707 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1708 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1709 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1710 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1711 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1712 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1713 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1714 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1715 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1716 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Basirhat Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 ) under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001271/2023-2024 | 820/BST | 12/09/2023 | 11/12/2023 | M/S LAXMI ENTERPRISE | 0.9 | 0.9 | 100 | 100
1717 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1718 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1719 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1720 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1721 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1722 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1723 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1724 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1725 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1726 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1727 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1728 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1729 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1730 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1731 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1732 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1733 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1734 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1735 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1736 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1737 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1738 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Asesh Roy Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001273/2023-2024 | 857/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 62
1739 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1740 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1741 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1742 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1743 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1744 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1745 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1746 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1747 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1748 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1749 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1750 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1751 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1752 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1753 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1754 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1755 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1756 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1757 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1758 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1759 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1760 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Habra Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001274/2023-2024 | 858/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 60
1761 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1762 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1763 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1764 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1765 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1766 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1767 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1768 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1769 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1770 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1771 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1772 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1773 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1774 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1775 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1776 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1777 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1778 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1779 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1780 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1781 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1782 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Chandpara Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001275/2023-2024 | 860/BST | 20/09/2023 | 19/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 59
1783 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1784 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1785 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1786 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1787 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1788 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1789 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1790 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1791 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1792 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1793 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1794 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1795 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1796 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1797 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1798 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1799 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1800 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1801 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1802 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1803 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1804 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bodai Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001276/2023-2024 | 863/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 64
1805 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1806 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1807 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1808 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1809 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1810 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1811 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1812 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1813 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1814 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1815 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1816 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1817 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1818 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1819 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1820 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1821 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1822 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1823 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1824 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1825 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1826 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognised Bishnupur Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001277/2023-2024 | 866/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 63
1827 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1828 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1829 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1830 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1831 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1832 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1833 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1834 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1835 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1836 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1837 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1838 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1839 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1840 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1841 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1842 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1843 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1844 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1845 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1846 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1847 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1848 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Bagdah Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site survelliance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. | Assistant Engineer |  | ORD/001278/2023-2024 | 867/BST | 26/09/2023 | 25/12/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 61
1849 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1850 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1851 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1852 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1853 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1854 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1855 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1856 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1857 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1858 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1859 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1860 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1861 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1862 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1863 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1864 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1865 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1866 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1867 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1868 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1869 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1870 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrear Enhanced Monthly Remuneration Engagement of 9 (Four) Nos Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant & Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gopiballavpur, Belpahari, Lalgarh & Gidhni Sub District Laboratory within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000368/2023-2024 | 289/JRWS | 28/11/2023 | 28/10/2024 | M/S. CARE | 4.78 | 4.78 | 100 | 100
1871 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1872 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1873 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1874 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1875 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1876 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1877 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1878 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1879 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1880 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1881 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1882 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1883 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1884 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1885 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1886 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1887 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1888 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1889 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1890 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1891 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1892 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000377/2023-2024 | 2040/JHD | 07/12/2023 | 07/12/2024 | M/S. EL-CON | 15.55 | 14.52 | 93.41 | 75
1893 | ALIPURDUAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1894 | BANKURA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1895 | BIRBHUM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1896 | COOCHBEHAR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1897 | DAKSHIN DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1898 | DARJEELING |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1899 | HOOGHLY |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1900 | HOWRAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1901 | JALPAIGURI |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1902 | JHARGRAM |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1903 | KALIMPONG |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1904 | MALDAH |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1905 | MURSHIDABAD |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1906 | NADIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1907 | NORTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1908 | PASCHIM BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1909 | PASCHIM MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1910 | PURBA BARDHAMAN |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1911 | PURBA MEDINIPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1912 | PURULIA |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1913 | SOUTH 24 PARGANAS |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1914 | UTTAR DINAJPUR |  | Nadia Arsenic Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and installation of spare parts of TSQ Duo Mass Spectro Trace 1310 model-Thermo Scientific Tliple Quadrapole of GC-MS/MS System under Nadia Arsenic Division-I, PHED. | Assistant Engineer-I | Junior Engineer-I | ORD/000244/2023-2024 | 531/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.72 | 2.72 | 100 | 100
1915 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1916 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1917 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1918 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1919 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1920 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1921 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1922 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1923 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1924 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1925 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1926 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1927 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1928 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1929 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1930 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1931 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1932 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1933 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1934 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1935 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1936 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000376/2023-2024 | 2039/JHD | 07/12/2023 | 07/12/2024 | CANVAS | 14.04 | 14.04 | 100 | 75
1937 | ALIPURDUAR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1938 | BANKURA |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1939 | BIRBHUM |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1940 | COOCHBEHAR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1941 | DAKSHIN DINAJPUR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1942 | DARJEELING |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1943 | HOOGHLY |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1944 | HOWRAH |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1945 | JALPAIGURI |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1946 | JHARGRAM |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1947 | KALIMPONG |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1948 | MALDAH |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1949 | MURSHIDABAD |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1950 | NADIA |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1951 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1952 | PASCHIM BARDHAMAN |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1953 | PASCHIM MEDINIPUR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1954 | PURBA BARDHAMAN |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1955 | PURBA MEDINIPUR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1956 | PURULIA |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1957 | SOUTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1958 | UTTAR DINAJPUR |  | North 24 Pgs W/S Division I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL related expenses, PT Test, NABL Application Fees, Pre-Audit, Final Audit, Annual NABL Accreditation Fees, Auditor-travel, Food, Lodging. Note:- The Rate is inclusive of GST, Cess and all other Taxes as Applicable. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000200/2023-2024 | 1828/NWSD-I | 09/11/2023 | 09/12/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
1959 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1960 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1961 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1962 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1963 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1964 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1965 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1966 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1967 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1968 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1969 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1970 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1971 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1972 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1973 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1974 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1975 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1976 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1977 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1978 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1979 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1980 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Nalhati Sub-District Water Testing Laboratory at Nalhati ) | AE | Estimator,JE2 | ORD/000441/2023-2024 | 443/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
1981 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1982 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1983 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1984 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1985 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1986 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1987 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1988 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1989 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1990 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1991 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1992 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1993 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1994 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1995 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1996 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1997 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1998 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
1999 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2000 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2001 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2002 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Murarai Sub-District Water Testing Laboratory at Murarai) | AE | Estimator,JE2 | ORD/000434/2023-2024 | 437/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2003 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2004 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2005 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2006 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2007 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2008 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2009 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2010 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2011 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2012 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2013 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2014 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2015 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2016 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2017 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2018 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2019 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2020 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2021 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2022 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2023 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2024 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Patelnagar Sub-District Water Testing Laboratory at Patelnagar | AE | Estimator,JE2 | ORD/000435/2023-2024 | 438/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2025 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2026 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2027 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2028 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2029 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2030 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2031 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2032 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2033 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2034 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2035 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2036 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2037 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2038 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2039 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2040 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2041 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2042 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2043 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2044 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2045 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2046 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Mayureswar Sub-District Water Testing Laboratory at Mayureswar. | AE | Estimator,JE2 | ORD/000437/2023-2024 | 440/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2047 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2048 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2049 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2050 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2051 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2052 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2053 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2054 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2055 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2056 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2057 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2058 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2059 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2060 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2061 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2062 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2063 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2064 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2065 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2066 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2067 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2068 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Paschim Banga Vigyan Mancha Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001676/2023-2024 | 1187/BST | 22/12/2023 | 21/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 95
2069 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2070 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2071 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2072 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2073 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2074 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2075 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2076 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2077 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2078 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2079 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2080 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2081 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2082 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2083 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2084 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2085 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2086 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2087 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2088 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2089 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2090 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Rampurhat Sub-District Water Testing Laboratory at Rampurhat | AE | Estimator,JE2 | ORD/000440/2023-2024 | 442/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2091 | ALIPURDUAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2092 | BANKURA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2093 | BIRBHUM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2094 | COOCHBEHAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2095 | DAKSHIN DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2096 | DARJEELING |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2097 | HOOGHLY |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2098 | HOWRAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2099 | JALPAIGURI |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2100 | JHARGRAM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2101 | KALIMPONG |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2102 | MALDAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2103 | MURSHIDABAD |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2104 | NADIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2105 | NORTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2106 | PASCHIM BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2107 | PASCHIM MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2108 | PURBA BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2109 | PURBA MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2110 | PURULIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2111 | SOUTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2112 | UTTAR DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Assigning Resource persons for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, PHE Dte. Government of West Bengal. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000426/2023-2024 | 3234/RD/PHE | 22/11/2023 | 18/02/2024 | LAB. SOLUTION | 16.45 | 16.45 | 100 | 100
2113 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2114 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2115 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2116 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2117 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2118 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2119 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2120 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2121 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2122 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2123 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2124 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2125 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2126 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2127 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2128 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2129 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2130 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2131 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2132 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2133 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2134 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Khayrasole Pally Mongal Samityi Sub-District Water Testing Laboratory at Khayrasole ) | AE | Estimator,JE2 | ORD/000438/2023-2024 | 441/RWS | 10/10/2023 | 17/10/2023 | DULAL MAJUMDAR | 0.9 | 0.9 | 100 | 100
2135 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2136 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2137 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2138 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2139 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2140 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2141 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2142 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2143 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2144 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2145 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2146 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2147 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2148 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2149 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2150 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2151 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2152 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2153 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2154 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2155 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2156 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Ahmedpur Sub-District Water Testing Laboratory at Ahmedpur | AE | Estimator,JE2 | ORD/000436/2023-2024 | 439/RWS | 10/10/2023 | 17/10/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
2157 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2158 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2159 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2160 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2161 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2162 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2163 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2164 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2165 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2166 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2167 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2168 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2169 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2170 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2171 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2172 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2173 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2174 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2175 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2176 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2177 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2178 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL regognised Water Quality Testing Block level Laboratory under the Assistant Engineer, RWS, Birbhum Sub-Division,PHE Dte. Government of West Bengal by assigining team of competent resource personnel who will be engaged for complete supervision for retaining NABL regognition and compilation of preparatory upto date documentation, Calibration for on site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of Water Testing Laboratory:- Kanachi Khadi Bhandar Sub-District Water Testing Laboratory at Kanachi Khadi Bhandar | AE | Estimator,JE2 | ORD/000442/2023-2024 | 444/RWS | 10/10/2023 | 17/10/2023 | LAB ANALYTICS | 0.9 | 0.9 | 100 | 100
2179 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2180 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2181 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2182 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2183 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2184 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2185 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2186 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2187 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2188 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2189 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2190 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2191 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2192 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2193 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2194 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2195 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2196 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2197 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2198 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2199 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2200 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supervision and extend support to NABL recognized Forum of Scientists Engineers & Technologists Sub-District Water Testing Laboratory by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and completion of preparatory up to date documentation, Proficiency Test (PT) & Calibration for on-site surveillance by NABL (as per NABL 139 )under Barasat Division , P.H. E. Dte. |  | Junior Engineer | ORD/001677/2023-2024 | 1196/BST | 29/12/2023 | 28/03/2024 | LAB. SOLUTION | 0.9 | 0.9 | 100 | 90
2201 | ALIPURDUAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2202 | BANKURA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2203 | BIRBHUM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2204 | COOCHBEHAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2205 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2206 | DARJEELING |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2207 | HOOGHLY |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2208 | HOWRAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2209 | JALPAIGURI |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2210 | JHARGRAM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2211 | KALIMPONG |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2212 | MALDAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2213 | MURSHIDABAD |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2214 | NADIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2215 | NORTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2216 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2217 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2218 | PURBA BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2219 | PURBA MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2220 | PURULIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2221 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2222 | UTTAR DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF ONLINE TRAINING FEE (ANNEXURE-I) REALTED TO 2 DAY'S ONLINE TRAINING ON LABORATORY MANAGEMENT SYSTEM AND INTERNAL AUDIT FOR ASSISTANT ENGINEER, JUNIOUR ENGINEER & CHEMIST OF DISTRICT LEVEL RURAL WATER QUALITY TESTING LABORATORIES OF PHED FOR CERTIFICATION AS PER ISO/IEC 17025: 2017 HELD ON 10TH JUNE'23 TO 11TH JUNE'23 TO GREEN ECONOMY COALITION FOUNDATION PRIVATE LIMITED. |  |  | BILL/00346/2023-2024 | BP-2023-24-336 | 19/06/2023 | 19/06/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2223 | ALIPURDUAR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2224 | BANKURA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2225 | BIRBHUM |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2226 | COOCHBEHAR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2227 | DAKSHIN DINAJPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2228 | DARJEELING |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2229 | HOOGHLY |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2230 | HOWRAH |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2231 | JALPAIGURI |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2232 | JHARGRAM |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2233 | KALIMPONG |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2234 | MALDAH |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2235 | MURSHIDABAD |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2236 | NADIA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2237 | NORTH 24 PARGANAS |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2238 | PASCHIM BARDHAMAN |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2239 | PASCHIM MEDINIPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2240 | PURBA BARDHAMAN |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2241 | PURBA MEDINIPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2242 | PURULIA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2243 | SOUTH 24 PARGANAS |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2244 | UTTAR DINAJPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SURVILLANCE ASSESMENT FEE CONDUCTED ON 18 JUNE 2023 |  |  | BILL/00222/2023-2024 | BP-2023-24-77 | 10/10/2023 | 10/10/2023 | QUALITY COUNCIL OF INDIA | 0.25 | 0 | 0 | 0
2245 | ALIPURDUAR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2246 | BANKURA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2247 | BIRBHUM |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2248 | COOCHBEHAR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2249 | DAKSHIN DINAJPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2250 | DARJEELING |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2251 | HOOGHLY |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2252 | HOWRAH |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2253 | JALPAIGURI |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2254 | JHARGRAM |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2255 | KALIMPONG |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2256 | MALDAH |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2257 | MURSHIDABAD |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2258 | NADIA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2259 | NORTH 24 PARGANAS |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2260 | PASCHIM BARDHAMAN |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2261 | PASCHIM MEDINIPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2262 | PURBA BARDHAMAN |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2263 | PURBA MEDINIPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2264 | PURULIA |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2265 | SOUTH 24 PARGANAS |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2266 | UTTAR DINAJPUR |  | Siliguri W/S Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fee of Darjeeling District Laboratory (T-7055), Fulbari |  |  | BILL/00007/2023-2024 | BP-2023-24-3 | 28/04/2023 | 28/04/2023 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
2267 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2268 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2269 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2270 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2271 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2272 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2273 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2274 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2275 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2276 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2277 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2278 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2279 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2280 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2281 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2282 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2283 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2284 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2285 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2286 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2287 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2288 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnaganj Sub-District Laboratory |  |  | BILL/00296/2022-2023 | 403/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2289 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2290 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2291 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2292 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2293 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2294 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2295 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2296 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2297 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2298 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2299 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2300 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2301 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2302 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2303 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2304 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2305 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2306 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2307 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2308 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2309 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2310 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Logistic expenses for Auditors for Malda District Water Testing Laboratory. |  |  | BILL/00135/2023-2024 | BP-2023-24-79 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2311 | ALIPURDUAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2312 | BANKURA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2313 | BIRBHUM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2314 | COOCHBEHAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2315 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2316 | DARJEELING |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2317 | HOOGHLY |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2318 | HOWRAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2319 | JALPAIGURI |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2320 | JHARGRAM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2321 | KALIMPONG |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2322 | MALDAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2323 | MURSHIDABAD |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2324 | NADIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2325 | NORTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2326 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2327 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2328 | PURBA BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2329 | PURBA MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2330 | PURULIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2331 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2332 | UTTAR DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PAYMENT OF RESOURCE PERSON FEES FOR TRAINING AT DAKSHIN ROYPUR ,STATE REFERRAL LABORATORY ON ISO/IEC 17025:2017,DATED 22ND-23RD APRIL,2023. |  |  | BILL/00093/2023-2024 | BP-2023-24-149 | 16/05/2023 | 16/05/2023 | GREEN ECONOMY COALITION FOUNDATION | 0.25 | 0 | 0 | 0
2333 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2334 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2335 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2336 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2337 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2338 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2339 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2340 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2341 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2342 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2343 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2344 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2345 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2346 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2347 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2348 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2349 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2350 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2351 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2352 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2353 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2354 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Reimbursement of application fees for NABL G Lap for Three Laboratories under The Executive Enginner, Malda Division, PHE Dte. |  |  | BILL/00579/2022-2023 | BP-2022-23-229 | 30/03/2023 | 30/03/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.53 | 0 | 0 | 0
2355 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2356 | BANKURA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2357 | BIRBHUM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2358 | COOCHBEHAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2359 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2360 | DARJEELING |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2361 | HOOGHLY |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2362 | HOWRAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2363 | JALPAIGURI |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2364 | JHARGRAM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2365 | KALIMPONG |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2366 | MALDAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2367 | MURSHIDABAD |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2368 | NADIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2369 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2370 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2371 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2372 | PURBA BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2373 | PURBA MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2374 | PURULIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2375 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2376 | UTTAR DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual surveillance fees for Jalpaiguri District Water Testing Laboratory |  |  | BILL/00236/2023-2024 | BP-2023-24-234 | 19/07/2023 | 19/07/2023 | QUALITY COUNXIL OF INDIA | 0.39 | 0 | 0 | 0
2377 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2378 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2379 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2380 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2381 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2382 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2383 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2384 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2385 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2386 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2387 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2388 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2389 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2390 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2391 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2392 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2393 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2394 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2395 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2396 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2397 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2398 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Krishnagar Sub-District Laboratory |  |  | BILL/00294/2022-2023 | 402 | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2399 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2400 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2401 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2402 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2403 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2404 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2405 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2406 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2407 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2408 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2409 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2410 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2411 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2412 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2413 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2414 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2415 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2416 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2417 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2418 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2419 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2420 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Habippur Sub-District Laboratory |  |  | BILL/00291/2022-2023 | 400/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2421 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2422 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2423 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2424 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2425 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2426 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2427 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2428 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2429 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2430 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2431 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2432 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2433 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2434 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2435 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2436 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2437 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2438 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2439 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2440 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2441 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2442 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Bagula Sub-District Laboratory |  |  | BILL/00293/2022-2023 | 401/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2443 | ALIPURDUAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2444 | BANKURA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2445 | BIRBHUM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2446 | COOCHBEHAR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2447 | DAKSHIN DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2448 | DARJEELING |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2449 | HOOGHLY |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2450 | HOWRAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2451 | JALPAIGURI |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2452 | JHARGRAM |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2453 | KALIMPONG |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2454 | MALDAH |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2455 | MURSHIDABAD |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2456 | NADIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2457 | NORTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2458 | PASCHIM BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2459 | PASCHIM MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2460 | PURBA BARDHAMAN |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2461 | PURBA MEDINIPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2462 | PURULIA |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2463 | SOUTH 24 PARGANAS |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2464 | UTTAR DINAJPUR |  | Nadia Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment regarding participation in proficiency Testing (Pt) Program for all Water Quality Parameters mentioned under scope of Accreditation / Recognition for Tehatta Sub-District Laboratory |  |  | BILL/00297/2022-2023 | 404/PFMS | 02/02/2023 | 02/02/2023 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0 | 0
2465 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2466 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2467 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2468 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2469 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2470 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2471 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2472 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2473 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2474 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2475 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2476 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2477 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2478 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2479 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2480 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2481 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2482 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2483 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2484 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2485 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2486 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Payment of Annual NABL Accreditation fee for Malda District Water Testing Laboratory. |  |  | BILL/00134/2023-2024 | BP-2023-24-80 | 14/06/2023 | 14/06/2023 | QUALITY COUNCIL OF INDIA BOARD: NABL | 0.28 | 0 | 0 | 0
2487 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2488 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2489 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2490 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2491 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2492 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2493 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2494 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2495 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2496 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2497 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2498 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2499 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2500 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2501 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2502 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2503 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2504 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2505 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2506 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2507 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2508 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PETTY REPAIR OF 04 NOS SUB - DISTRICT LABORATORY (LALGARH, GIDHNI, BELPAHARI AND GOPIBALLAVPUR) UNDER JHARGRAM DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000022/2024-2025 | 141/JRWS | 14/06/2024 | 29/06/2024 | MANDAL ENTERPRISE | 0.25 | 0 | 0 | 0
2509 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2510 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2511 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2512 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2513 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2514 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2515 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2516 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2517 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2518 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2519 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2520 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2521 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2522 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2523 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2524 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2525 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2526 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2527 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2528 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2529 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2530 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item no: 02,03,04,05,06,07,08,10,12,13,14,16,17,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,39,40,41,42,43,44,46,47,48) |  |  | ORD/000059/2024-2025 | 2384/HUG | 24/06/2024 | 14/07/2024 | M/S LAXMI ENTERPRISE | 5.15 | 0 | 0 | 0
2531 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2532 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2533 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2534 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2535 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2536 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2537 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2538 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2539 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2540 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2541 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2542 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2543 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2544 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2545 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2546 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2547 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2548 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2549 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2550 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2551 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2552 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {21(Twenty One) Nos. Item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000394/2024-2025 | 4705/MD | 09/09/2024 | 24/09/2024 | LAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
2553 | ALIPURDUAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2554 | BANKURA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2555 | BIRBHUM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2556 | COOCHBEHAR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2557 | DAKSHIN DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2558 | DARJEELING |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2559 | HOOGHLY |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2560 | HOWRAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2561 | JALPAIGURI |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2562 | JHARGRAM |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2563 | KALIMPONG |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2564 | MALDAH |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2565 | MURSHIDABAD |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2566 | NADIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2567 | NORTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2568 | PASCHIM BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2569 | PASCHIM MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2570 | PURBA BARDHAMAN |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2571 | PURBA MEDINIPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2572 | PURULIA |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2573 | SOUTH 24 PARGANAS |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2574 | UTTAR DINAJPUR |  | Malda Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Delivery of Chemicals,reagent, glassware and other necessary accessories to extend support to NABL recognised Water Quality Testing Block level Laboratories for a period of one month from the date of commencement for Chanchol Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. {4(Four) Nos. item} | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000395/2024-2025 | 4706/MD | 09/09/2024 | 23/11/2024 | LAB. SOLUTION | 0.26 | 0 | 0 | 100
2575 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2576 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2577 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2578 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2579 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2580 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2581 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2582 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2583 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2584 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2585 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2586 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2587 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2588 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2589 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2590 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2591 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2592 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2593 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2594 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2595 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2596 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) |  | ORD/001810/2024-2025 | 234/HQ/HUG | 23/09/2024 | 28/09/2024 | PRADIP KUMAR ADHYA | 0.84 | 0 | 0 | 0
2597 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2598 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2599 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2600 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2601 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2602 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2603 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2604 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2605 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2606 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2607 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2608 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2609 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2610 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2611 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2612 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2613 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2614 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2615 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2616 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2617 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2618 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monittoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the Period of 1 (one) months. (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000300/2024-2025 | 2060/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 0 | 0 | 0
2619 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2620 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2621 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2622 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2623 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2624 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2625 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2626 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2627 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2628 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2629 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2630 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2631 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2632 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2633 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2634 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2635 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2636 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2637 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2638 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2639 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2640 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | 4th Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD: 3 MONTHS (01.07.2024 TO 30.09.2024) | Assistant Engineer(HQ) |  | ORD/002206/2024-2025 | 162/HQ/HUG | 28/06/2024 | 28/09/2024 | DAS TRADING | 0.75 | 0 | 0 | 0
2641 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2642 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2643 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2644 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2645 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2646 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2647 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2648 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2649 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2650 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2651 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2652 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2653 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2654 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2655 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2656 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2657 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2658 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2659 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2660 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2661 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2662 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply & Installtion of 1 No existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000462/2023-2024 | 13/RWS | 25/01/2024 | 09/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2663 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2664 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2665 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2666 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2667 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2668 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2669 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2670 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2671 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2672 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2673 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2674 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2675 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2676 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2677 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2678 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2679 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2680 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2681 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2682 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2683 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2684 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation Work Order for Supply & installation of 1 No. existing AC machine & other work related to NABL Requirement at Birbhum District Water Testing Laboratory at Suri under Birbhum Division PHE Dte. | AE | JE2 | ORD/000587/2023-2024 | 15/RWS | 02/02/2024 | 17/02/2024 | M/S SARADA CONSTRUCTION. | 0.7 | 0.7 | 100 | 100
2685 | ALIPURDUAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2686 | BANKURA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2687 | BIRBHUM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2688 | COOCHBEHAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2689 | DAKSHIN DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2690 | DARJEELING |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2691 | HOOGHLY |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2692 | HOWRAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2693 | JALPAIGURI |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2694 | JHARGRAM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2695 | KALIMPONG |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2696 | MALDAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2697 | MURSHIDABAD |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2698 | NADIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2699 | NORTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2700 | PASCHIM BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2701 | PASCHIM MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2702 | PURBA BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2703 | PURBA MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2704 | PURULIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2705 | SOUTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2706 | UTTAR DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration of necessary Instrument ,Glasswares as per ISO/IEC 17025:2017 of Cooch Behar District Water Testing Laboratory under Cooch Behar Division P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000777/2023-2024 | 543/CD | 29/02/2024 | 07/03/2024 | SAYAN SAHA | 0.46 | 0.46 | 100 | 100
2707 | ALIPURDUAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2708 | BANKURA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2709 | BIRBHUM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2710 | COOCHBEHAR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2711 | DAKSHIN DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2712 | DARJEELING |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2713 | HOOGHLY |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2714 | HOWRAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2715 | JALPAIGURI |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2716 | JHARGRAM |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2717 | KALIMPONG |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2718 | MALDAH |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2719 | MURSHIDABAD |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2720 | NADIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2721 | NORTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2722 | PASCHIM BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2723 | PASCHIM MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2724 | PURBA BARDHAMAN |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2725 | PURBA MEDINIPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2726 | PURULIA |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2727 | SOUTH 24 PARGANAS |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2728 | UTTAR DINAJPUR |  | Barasat Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | NABL accreditation related expenses PT sample charges , NABL application fees, Pre Audit , Final Audit, Annual Accreditation Fees, Audit -travel, logistic expenses for North 24 Parganas District Water testing Laboratory. |  | Junior Engineer | ORD/001817/2023-2024 | 123/BST | 25/01/2024 | 25/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 1.28 | 1.28 | 100 | 60
2729 | ALIPURDUAR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2730 | BANKURA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2731 | BIRBHUM |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2732 | COOCHBEHAR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2733 | DAKSHIN DINAJPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2734 | DARJEELING |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2735 | HOOGHLY |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2736 | HOWRAH |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2737 | JALPAIGURI |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2738 | JHARGRAM |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2739 | KALIMPONG |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2740 | MALDAH |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2741 | MURSHIDABAD |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2742 | NADIA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2743 | NORTH 24 PARGANAS |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2744 | PASCHIM BARDHAMAN |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2745 | PASCHIM MEDINIPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2746 | PURBA BARDHAMAN |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2747 | PURBA MEDINIPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2748 | PURULIA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2749 | SOUTH 24 PARGANAS |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2750 | UTTAR DINAJPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals, consumbles for the Laudoha Sub District Water Testing laboratory, Gopalpur Sub-District Water Testing Laboratory & Paschim Bardhaman District Water Testing Laboratory under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001055/2023-2024 | 703/RCD-I | 29/02/2024 | 10/03/2024 | BABA LOKNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
2751 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2752 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2753 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2754 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2755 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2756 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2757 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2758 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2759 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2760 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2761 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2762 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2763 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2764 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2765 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2766 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2767 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2768 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2769 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2770 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2771 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2772 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Chemicals & Cosumables to Water Quality Monitoring & Surveillance for Sagar Water Testing Laboratory under Alipore Division | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000325/2024-2025 | 190/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.02 | 1.02 | 100 | 100
2773 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2774 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2775 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2776 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2777 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2778 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2779 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2780 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2781 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2782 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2783 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2784 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2785 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2786 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2787 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2788 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2789 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2790 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2791 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2792 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2793 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2794 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. (Item No. 01,09,11,15,18,37,38,45) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000058/2024-2025 | 2383/HUG | 24/06/2024 | 22/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 8.98 | 0 | 0 | 100
2795 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2796 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2797 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2798 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2799 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2800 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2801 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2802 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2803 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2804 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2805 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2806 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2807 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2808 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2809 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2810 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2811 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2812 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2813 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2814 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2815 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2816 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Turbidity Meter requirement part for NABL accrediation at Basanti Sub-District Water Testing Laboratory as per ISO/IEC: 17025:2017 under Alipore Division, PHE Dtein the District of South 24 Parganas | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000323/2024-2025 | 188/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.08 | 1.08 | 100 | 100
2817 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2818 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2819 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2820 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2821 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2822 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2823 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2824 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2825 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2826 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2827 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2828 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2829 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2830 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2831 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2832 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2833 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2834 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2835 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2836 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2837 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2838 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Repairing of Thermo Aquamate VIS AQ 7000 Spectrophotometer with allied works of Gangasagar Water Testing Laboratory to maintain un-interrupted sample testing under Executive Engineer, Alipore Division, PHE Dte | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000324/2024-2025 | 189/RWS | 14/06/2024 | 21/06/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.52 | 1.52 | 100 | 100
2839 | ALIPURDUAR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2840 | BANKURA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2841 | BIRBHUM |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2842 | COOCHBEHAR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2843 | DAKSHIN DINAJPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2844 | DARJEELING |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2845 | HOOGHLY |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2846 | HOWRAH |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2847 | JALPAIGURI |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2848 | JHARGRAM |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2849 | KALIMPONG |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2850 | MALDAH |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2851 | MURSHIDABAD |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2852 | NADIA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2853 | NORTH 24 PARGANAS |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2854 | PASCHIM BARDHAMAN |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2855 | PASCHIM MEDINIPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2856 | PURBA BARDHAMAN |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2857 | PURBA MEDINIPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2858 | PURULIA |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2859 | SOUTH 24 PARGANAS |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2860 | UTTAR DINAJPUR |  | Howrah Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of Chemicals and other required items related to smooth functioning of NABL Recognition of different Sub District Laboratories, under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000055/2024-2025 | 2925/HD | 27/06/2024 | 11/08/2024 | LAB. SOLUTION | 2.95 | 2.95 | 100 | 100
2861 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2862 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2863 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2864 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2865 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2866 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2867 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2868 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2869 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2870 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2871 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2872 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2873 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2874 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2875 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2876 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2877 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2878 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2879 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2880 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2881 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2882 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001559/2024-2025 | 231/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2883 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2884 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2885 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2886 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2887 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2888 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2889 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2890 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2891 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2892 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2893 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2894 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2895 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2896 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2897 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2898 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2899 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2900 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2901 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2902 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2903 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2904 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001556/2024-2025 | 227/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
2905 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2906 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2907 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2908 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2909 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2910 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2911 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2912 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2913 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2914 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2915 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2916 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2917 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2918 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2919 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2920 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2921 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2922 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2923 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2924 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2925 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2926 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001558/2024-2025 | 230/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
2927 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2928 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2929 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2930 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2931 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2932 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2933 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2934 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2935 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2936 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2937 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2938 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2939 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2940 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2941 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2942 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2943 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2944 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2945 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2946 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2947 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2948 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Belpahari Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000188/2024-2025 | 262/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2949 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2950 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2951 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2952 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2953 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2954 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2955 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2956 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2957 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2958 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2959 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2960 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2961 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2962 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2963 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2964 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2965 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2966 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2967 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2968 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2969 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2970 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gopiballavpur Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000191/2024-2025 | 265/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
2971 | ALIPURDUAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2972 | BANKURA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2973 | BIRBHUM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2974 | COOCHBEHAR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2975 | DAKSHIN DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2976 | DARJEELING |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2977 | HOOGHLY |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2978 | HOWRAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2979 | JALPAIGURI |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2980 | JHARGRAM |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2981 | KALIMPONG |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2982 | MALDAH |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2983 | MURSHIDABAD |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2984 | NADIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2985 | NORTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2986 | PASCHIM BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2987 | PASCHIM MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2988 | PURBA BARDHAMAN |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2989 | PURBA MEDINIPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2990 | PURULIA |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2991 | SOUTH 24 PARGANAS |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2992 | UTTAR DINAJPUR |  | Alipore Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | chemicals and other required items related to smooth functioning of NABL Recognition of Raidighi Sub District Water Testing Laboratory, under Alipore Division PHE Dte. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000566/2024-2025 | 167/RWS | 07/06/2024 | 07/07/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.88 | 0 | 0 | 100
2993 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2994 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2995 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2996 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2997 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2998 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
2999 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3000 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3001 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3002 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3003 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3004 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3005 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3006 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3007 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3008 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3009 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3010 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3011 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3012 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3013 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3014 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 03 NOS. UNDER HOOGHLY DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001551/2024-2025 | 224/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3015 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3016 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3017 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3018 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3019 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3020 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3021 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3022 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3023 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3024 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3025 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3026 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3027 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3028 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3029 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3030 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3031 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3032 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3033 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3034 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3035 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3036 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY RESIDUAL CHLORINE KIT 03 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001553/2024-2025 | 225/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.83 | 0 | 0 | 100
3037 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3038 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3039 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3040 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3041 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3042 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3043 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3044 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3045 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3046 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3047 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3048 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3049 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3050 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3051 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3052 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3053 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3054 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3055 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3056 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3057 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3058 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001561/2024-2025 | 233/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3059 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3060 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3061 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3062 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3063 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3064 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3065 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3066 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3067 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3068 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3069 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3070 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3071 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3072 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3073 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3074 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3075 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3076 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3077 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3078 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3079 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3080 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Lalgarh Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000189/2024-2025 | 263/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3081 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3082 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3083 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3084 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3085 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3086 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3087 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3088 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3089 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3090 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3091 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3092 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3093 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3094 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3095 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3096 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3097 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3098 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3099 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3100 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3101 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3102 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 7 (Seven) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist, Two Laboratory Assistant & One Nos. Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Gidhni Sub District Laboratary & Lalgarh Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 01 (one) month (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000301/2024-2025 | 2261/JHD | 29/11/2024 | 30/12/2024 | M/S. EL-CON | 1.26 | 1.26 | 100 | 100
3103 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3104 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3105 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3106 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3107 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3108 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3109 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3110 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3111 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3112 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3113 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3114 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3115 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3116 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3117 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3118 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3119 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3120 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3121 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3122 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3123 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3124 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000506/2024-2025 | 289/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.65 | 0 | 0 | 100
3125 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3126 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3127 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3128 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3129 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3130 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3131 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3132 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3133 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3134 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3135 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3136 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3137 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3138 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3139 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3140 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3141 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3142 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3143 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3144 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3145 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3146 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001555/2024-2025 | 226/HQ/HUG | 20/09/2024 | 03/05/2025 | LAB SOLUTION | 0.56 | 0 | 0 | 100
3147 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3148 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3149 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3150 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3151 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3152 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3153 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3154 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3155 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3156 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3157 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3158 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3159 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3160 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3161 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3162 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3163 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3164 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3165 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3166 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3167 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3168 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001560/2024-2025 | 232/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3169 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3170 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3171 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3172 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3173 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3174 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3175 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3176 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3177 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3178 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3179 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3180 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3181 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3182 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3183 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3184 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3185 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3186 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3187 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3188 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3189 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3190 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY OF CHEMICALS AND CONSUMABLES REQUIRED FOR DISTRICT WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000505/2024-2025 | 288/HQ/HUG | 11/12/2024 | 16/12/2024 | LAB ANALYTICS | 0.97 | 0 | 0 | 100
3191 | ALIPURDUAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3192 | BANKURA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3193 | BIRBHUM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3194 | COOCHBEHAR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3195 | DAKSHIN DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3196 | DARJEELING |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3197 | HOOGHLY |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3198 | HOWRAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3199 | JALPAIGURI |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3200 | JHARGRAM |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3201 | KALIMPONG |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3202 | MALDAH |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3203 | MURSHIDABAD |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3204 | NADIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3205 | NORTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3206 | PASCHIM BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3207 | PASCHIM MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3208 | PURBA BARDHAMAN |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3209 | PURBA MEDINIPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3210 | PURULIA |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3211 | SOUTH 24 PARGANAS |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3212 | UTTAR DINAJPUR |  | Hooghly Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | SUPPLY AND DELIVERY LOVIBOND RESIDUAL CHLORINE KIT 02 NOS. UNDER SUB-DISTRICT LAB UNDER HOOGHLY DIVISION, P.H.E. DTE. | Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/001557/2024-2025 | 229/HQ/HUG | 23/09/2024 | 06/05/2025 | LAB SOLUTION | 0.53 | 0 | 0 | 100
3213 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3214 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3215 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3216 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3217 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3218 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3219 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3220 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3221 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3222 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3223 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3224 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3225 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3226 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3227 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3228 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3229 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3230 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3231 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3232 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3233 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3234 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Calibration and other Chemical required related to smooth functioning of NABL Recognition of Gidhni Sub District Laboratory, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000190/2024-2025 | 264/JRWS | 09/08/2024 | 24/08/2024 | UTSAV AGENCY | 0.96 | 0 | 0 | 100
3235 | ALIPURDUAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3236 | BANKURA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3237 | BIRBHUM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3238 | COOCHBEHAR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3239 | DAKSHIN DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3240 | DARJEELING |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3241 | HOOGHLY |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3242 | HOWRAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3243 | JALPAIGURI |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3244 | JHARGRAM |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3245 | KALIMPONG |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3246 | MALDAH |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3247 | MURSHIDABAD |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3248 | NADIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3249 | NORTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3250 | PASCHIM BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3251 | PASCHIM MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3252 | PURBA BARDHAMAN |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3253 | PURBA MEDINIPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3254 | PURULIA |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3255 | SOUTH 24 PARGANAS |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3256 | UTTAR DINAJPUR |  | Coochbehar Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of chemicals and Glasswere for Cooch Behar District, Water Testing Laboratary under Cooch Behar Division, PHE Dte. for NABL purpose. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000480/2024-2025 | 1108/CD | 06/06/2024 | 13/06/2024 | LAB. SOLUTION | 0.52 | 0 | 0 | 100
3257 | ALIPURDUAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3258 | BANKURA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3259 | BIRBHUM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3260 | COOCHBEHAR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3261 | DAKSHIN DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3262 | DARJEELING |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3263 | HOOGHLY |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3264 | HOWRAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3265 | JALPAIGURI |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3266 | JHARGRAM |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3267 | KALIMPONG |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3268 | MALDAH |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3269 | MURSHIDABAD |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3270 | NADIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3271 | NORTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3272 | PASCHIM BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3273 | PASCHIM MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3274 | PURBA BARDHAMAN |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3275 | PURBA MEDINIPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3276 | PURULIA |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3277 | SOUTH 24 PARGANAS |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3278 | UTTAR DINAJPUR |  | Jhargram Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Continuation for Engagement of 6 (Six) Nos Laboratory Personnel (Two Chemist, Two Bacteriologist &Two Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Belpahari Sub District Laboratary & Gopiballavpur Sub District Laboratary within Jhargram Sub-Division under Jhargram Division, P.H.E. Dte. For the period of 1(one) months (01/12/2024 to 31/12/2024) | Assistant Engineer | Junior Engineer-II | ORD/000302/2024-2025 | 2260/JHD | 29/11/2024 | 30/12/2024 | CANVAS | 1.14 | 1.14 | 100 | 100
3279 | ALIPURDUAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3280 | BANKURA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3281 | BIRBHUM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3282 | COOCHBEHAR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3283 | DAKSHIN DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3284 | DARJEELING |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3285 | HOOGHLY |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3286 | HOWRAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3287 | JALPAIGURI |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3288 | JHARGRAM |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3289 | KALIMPONG |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3290 | MALDAH |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3291 | MURSHIDABAD |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3292 | NADIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3293 | NORTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3294 | PASCHIM BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3295 | PASCHIM MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3296 | PURBA BARDHAMAN |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3297 | PURBA MEDINIPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3298 | PURULIA |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3299 | SOUTH 24 PARGANAS |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3300 | UTTAR DINAJPUR |  | Raiganj Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | PT testing charges, Annual Surveillance/Renewal Pre-Audit & Final Audit fees, Annual NABL Accreditation fee, logistic expenses for Auditors for Uttar Dinajpur District Level Water Testing Laboratory. (GO2223009622PH dated 11.11.2022, Scheme code: SM/13633) |  |  | BILL/00120/2024-2025 | BP-2024-25-102 | 28/06/2024 | 28/06/2024 | EXECUTIVE ENGINEER | 0.66 | 0 | 0 | 0
3301 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3302 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3303 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3304 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3305 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3306 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3307 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3308 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3309 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3310 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3311 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3312 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3313 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3314 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3315 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3316 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3317 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3318 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3319 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3320 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3321 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3322 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | TC-10930 CERTIFICATE PERIOD 24.08.2022-23.08.2024 DUE PERIOD 24.08.2023-23.08.2024 (Chemical year of Accreditation Cycle) |  |  | BILL/00246/2024-2025 | BP-2024-25-111 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.28 | 0 | 0 | 0
3323 | ALIPURDUAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3324 | BANKURA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3325 | BIRBHUM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3326 | COOCHBEHAR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3327 | DAKSHIN DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3328 | DARJEELING |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3329 | HOOGHLY |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3330 | HOWRAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3331 | JALPAIGURI |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3332 | JHARGRAM |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3333 | KALIMPONG |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3334 | MALDAH |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3335 | MURSHIDABAD |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3336 | NADIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3337 | NORTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3338 | PASCHIM BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3339 | PASCHIM MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3340 | PURBA BARDHAMAN |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3341 | PURBA MEDINIPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3342 | PURULIA |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3343 | SOUTH 24 PARGANAS |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3344 | UTTAR DINAJPUR |  | Birbhum Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Surveillance conducted on 9 Sep'23 to 10 Sep'23 honorarium of Rajni kant sharma DR Papia Das |  |  | BILL/00245/2024-2025 | BP-2024-25-112 | 28/06/2024 | 28/06/2024 | QUALITY COUNCIL OF INDIA | 0.39 | 0 | 0 | 0
3345 | ALIPURDUAR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3346 | BANKURA |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3347 | BIRBHUM |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3348 | COOCHBEHAR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3349 | DAKSHIN DINAJPUR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3350 | DARJEELING |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3351 | HOOGHLY |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3352 | HOWRAH |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3353 | JALPAIGURI |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3354 | JHARGRAM |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3355 | KALIMPONG |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3356 | MALDAH |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3357 | MURSHIDABAD |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3358 | NADIA |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3359 | NORTH 24 PARGANAS |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3360 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3361 | PASCHIM MEDINIPUR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3362 | PURBA BARDHAMAN |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3363 | PURBA MEDINIPUR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3364 | PURULIA |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3365 | SOUTH 24 PARGANAS |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3366 | UTTAR DINAJPUR |  | Bankura Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Annual accreditation fees for Bankura District Water Testing Laboratory under Bankura Division, P.H.E.Dte. |  |  | BILL/00293/2024-2025 | BP-132/2024-25 | 25/06/2024 | 25/06/2024 | QUALITY COUNCIL OF INDIA | 0.68 | 0 | 0 | 0
3367 | ALIPURDUAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3368 | BANKURA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3369 | BIRBHUM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3370 | COOCHBEHAR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3371 | DAKSHIN DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3372 | DARJEELING |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3373 | HOOGHLY |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3374 | HOWRAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3375 | JALPAIGURI |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3376 | JHARGRAM |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3377 | KALIMPONG |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3378 | MALDAH |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3379 | MURSHIDABAD |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3380 | NADIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3381 | NORTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3382 | PASCHIM BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3383 | PASCHIM MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3384 | PURBA BARDHAMAN |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3385 | PURBA MEDINIPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3386 | PURULIA |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3387 | SOUTH 24 PARGANAS |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3388 | UTTAR DINAJPUR |  | Resource | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Arrangement of refreshment for the meeting facilitating training programme of District Consultants (WQ)and State/District level Bacteriologists on 'Preparedness of NABL accredition for microbiological paramaters ' at JKB,1st floor conference room on 29/08/24. |  |  | BILL/00639/2024-2025 | BP-2024-25-655 | 05/09/2024 | 05/09/2024 | SRI KRISHNA ENTERPRISE | 0.17 | 0 | 0 | 0
3389 | ALIPURDUAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3390 | BANKURA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3391 | BIRBHUM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3392 | COOCHBEHAR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3393 | DAKSHIN DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3394 | DARJEELING |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3395 | HOOGHLY |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3396 | HOWRAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3397 | JALPAIGURI |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3398 | JHARGRAM |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3399 | KALIMPONG |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3400 | MALDAH |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3401 | MURSHIDABAD |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3402 | NADIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3403 | NORTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3404 | PASCHIM BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3405 | PASCHIM MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3406 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3407 | PURBA MEDINIPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3408 | PURULIA |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3409 | SOUTH 24 PARGANAS |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3410 | UTTAR DINAJPUR |  | Burdwan Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Expenditure for the Training of Assistant Engineer (QM), Junior Engineer(DQMO), District Consultants (WQ),Assistant District Consultant (WQ) and State/District level Bacteriologists on Preparedness of NABL accreditation for microbiological parameter. |  |  | BILL/00674/2024-2025 | 859/JJM | 20/09/2024 | 20/09/2024 | KHUSI BHAKAT | 0.06 | 0 | 0 | 0
3411 | ALIPURDUAR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3412 | BANKURA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3413 | BIRBHUM |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3414 | COOCHBEHAR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3415 | DAKSHIN DINAJPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3416 | DARJEELING |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3417 | HOOGHLY |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3418 | HOWRAH |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3419 | JALPAIGURI |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3420 | JHARGRAM |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3421 | KALIMPONG |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3422 | MALDAH |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3423 | MURSHIDABAD |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3424 | NADIA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3425 | NORTH 24 PARGANAS |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3426 | PASCHIM BARDHAMAN |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3427 | PASCHIM MEDINIPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3428 | PURBA BARDHAMAN |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3429 | PURBA MEDINIPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3430 | PURULIA |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3431 | SOUTH 24 PARGANAS |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3432 | UTTAR DINAJPUR |  | RCFA Division -I | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply and delivery Hircrome Chromogenic Coliform Agar (CCA Agar) under RCFA Div-I PHE Dte. Work order No. 1913-A/RCD-I 07-08-2024 Work order No. 1916-A/RCD-I 07-08-2024 |  |  | BILL/01244/2024-2025 | 500/24-25 | 28/03/2025 | 28/03/2025 | M/S. BANDANA ENTERPRISE | 0.18 | 0 | 0 | 0
3433 | ALIPURDUAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3434 | BANKURA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3435 | BIRBHUM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3436 | COOCHBEHAR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3437 | DAKSHIN DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3438 | DARJEELING |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3439 | HOOGHLY |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3440 | HOWRAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3441 | JALPAIGURI |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3442 | JHARGRAM |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3443 | KALIMPONG |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3444 | MALDAH |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3445 | MURSHIDABAD |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3446 | NADIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3447 | NORTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3448 | PASCHIM BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3449 | PASCHIM MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3450 | PURBA BARDHAMAN |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3451 | PURBA MEDINIPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3452 | PURULIA |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3453 | SOUTH 24 PARGANAS |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
3454 | UTTAR DINAJPUR |  | Jalpaiguri Division | Procurement of services & consumables for continuance of NABL Accreditation and Recognition of District and Sub District Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Programme under jal Jeevan Mission | SM/13633 | Support-WQMSP | Supply of different items for the work of water testing at jalpaiguri District laboratory of the office of the Assistant Engineer, Jalpaiguri R.W.S Sub-Division, P.H.E Dte. under Jalpaiguri Division, P.H.E Dte. |  |  | BILL/01056/2024-2025 | BP-2024-25-565 | 09/01/2025 | 09/01/2025 | NORTHERN SCIENTIFIC MART | 0.08 | 0 | 0 | 0
Total | [13 empty] | 8029.53 | 6047.44 | 75.31