## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
2 | BANKURA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
3 | BIRBHUM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
4 | COOCHBEHAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
5 | DAKSHIN DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
6 | DARJEELING |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
7 | HOOGHLY |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
8 | HOWRAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
9 | JALPAIGURI |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
10 | JHARGRAM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
11 | KALIMPONG |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
12 | MALDAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
13 | MURSHIDABAD |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
14 | NADIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
15 | NORTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
16 | PASCHIM BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
17 | PASCHIM MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
18 | PURBA BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
19 | PURBA MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
20 | PURULIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
21 | SOUTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
22 | UTTAR DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Alipurduar, Birbhum, Jalpaiguri, Coochbehar, Darjeeling, Kalimpong, Maldah, Uttar Dinajpur & Dakshin Dinajpur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3321/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 201.85 | 0 | 0 | 80
23 | ALIPURDUAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
24 | BANKURA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
25 | BIRBHUM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
26 | COOCHBEHAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
27 | DAKSHIN DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
28 | DARJEELING |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
29 | HOOGHLY |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
30 | HOWRAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
31 | JALPAIGURI |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
32 | JHARGRAM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
33 | KALIMPONG |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
34 | MALDAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
35 | MURSHIDABAD |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
36 | NADIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
37 | NORTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
38 | PASCHIM BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
39 | PASCHIM MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
40 | PURBA BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
41 | PURBA MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
42 | PURULIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
43 | SOUTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
44 | UTTAR DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Hooghly, purba Barddhaman, Paschim Barddhaman, Nadia, North & South 24 Parganas under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 3319/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 212.37 | 0 | 0 | 95
45 | ALIPURDUAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
46 | BANKURA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
47 | BIRBHUM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
48 | COOCHBEHAR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
49 | DAKSHIN DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
50 | DARJEELING |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
51 | HOOGHLY |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
52 | HOWRAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
53 | JALPAIGURI |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
54 | JHARGRAM |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
55 | KALIMPONG |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
56 | MALDAH |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
57 | MURSHIDABAD |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
58 | NADIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
59 | NORTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
60 | PASCHIM BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
61 | PASCHIM MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
62 | PURBA BARDHAMAN |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
63 | PURBA MEDINIPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
64 | PURULIA |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
65 | SOUTH 24 PARGANAS |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
66 | UTTAR DINAJPUR |  | Resource | Procurement of Field Test Kits(FTKs) related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/13821 | Support-WQMSP | Supply & distribution of portable multi-parameter water quality testing device (Field Test kits) to each BMOH, facilitating block level training/orientation program on testing, awareness generation & data integration from the field both online/offline through monitoring & reporting on water safety status of rural drinking water sources in the district of Bankura, Murshidabad, Jhargram, Purulia, Purba & Paschim Medinipur under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 3320/RS | 03/11/2023 | 01/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 154.18 | 0 | 0 | 95
Total | [13 empty] | 12504.97 | 0 | 0