## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
2 | BANKURA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
3 | BIRBHUM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
4 | COOCHBEHAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
5 | DAKSHIN DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
6 | DARJEELING |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
7 | HOOGHLY |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
8 | HOWRAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
9 | JALPAIGURI |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
10 | JHARGRAM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
11 | KALIMPONG |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
12 | MALDAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
13 | MURSHIDABAD |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
14 | NADIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
15 | NORTH 24 PARAGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
16 | PASCHIM BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
17 | PASCHIM MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
18 | PURBA BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
19 | PURBA MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
20 | PURULIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
21 | SOUTH 24 PARAGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
22 | UTTAR DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 27.5 | 50 | 8
Total | [13 empty] | 1209.92 | 604.96 | 50