## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
2 | BANKURA |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
3 | BIRBHUM |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
4 | COOCHBEHAR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
5 | DAKSHIN DINAJPUR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
6 | DARJEELING |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
7 | HOOGHLY |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
8 | HOWRAH |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
9 | JALPAIGURI |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
10 | JHARGRAM |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
11 | KALIMPONG |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
12 | MALDAH |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
13 | MURSHIDABAD |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
14 | NADIA |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
15 | NORTH 24 PARGANAS |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
16 | PASCHIM BARDHAMAN |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
17 | PASCHIM MEDINIPUR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
18 | PURBA BARDHAMAN |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
19 | PURBA MEDINIPUR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
20 | PURULIA |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
21 | SOUTH 24 PARGANAS |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
22 | UTTAR DINAJPUR |  | Resource | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Design, layout, preparation, printing and supply of PHE Department's Diary ( Notepad) 2023 highlighting departmental activities & achievement in rural drinking water sector under PHE Department, Govt. of West Bengal. |  |  | ORD/000831/2022-2023 | 356/RS | 27/01/2023 | 11/02/2023 | SUMAN INDUSTRIES PVT. LTD. | 4.66 | 4.66 | 100 | 0
23 | ALIPURDUAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
24 | BANKURA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
25 | BIRBHUM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
26 | COOCHBEHAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
27 | DAKSHIN DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
28 | DARJEELING |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
29 | HOOGHLY |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
30 | HOWRAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
31 | JALPAIGURI |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
32 | JHARGRAM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
33 | KALIMPONG |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
34 | MALDAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
35 | MURSHIDABAD |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
36 | NADIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
37 | NORTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
38 | PASCHIM BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
39 | PASCHIM MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
40 | PURBA BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
41 | PURBA MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
42 | PURULIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
43 | SOUTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
44 | UTTAR DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 0 | 0 | 8
45 | ALIPURDUAR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
46 | BANKURA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
47 | BIRBHUM |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
48 | COOCHBEHAR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
50 | DARJEELING |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
51 | HOOGHLY |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
52 | HOWRAH |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
53 | JALPAIGURI |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
54 | JHARGRAM |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
55 | KALIMPONG |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
56 | MALDAH |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
57 | MURSHIDABAD |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
58 | NADIA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
64 | PURULIA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
Total | [13 empty] | 2951.84 | 102.56 | 3.47