## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
2 | BANKURA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
3 | BIRBHUM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
4 | COOCHBEHAR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
5 | DAKSHIN DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
6 | DARJEELING |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
7 | HOOGHLY |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
8 | HOWRAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
9 | JALPAIGURI |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
10 | JHARGRAM |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
11 | KALIMPONG |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
12 | MALDAH |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
13 | MURSHIDABAD |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
14 | NADIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
15 | NORTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
16 | PASCHIM BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
17 | PASCHIM MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
18 | PURBA BARDHAMAN |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
19 | PURBA MEDINIPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
20 | PURULIA |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
21 | SOUTH 24 PARGANAS |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
22 | UTTAR DINAJPUR |  | Barasat Division | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Logistics support in respect to awareness among communities and conducting different IEC activities aiming towards judicial & safe use of drinking water , water conservation under JJM in North 24 Parganas District under Barasat Division ,PHE dte. | Assistant Engineer |  | ORD/001538/2023-2024 | 125/BD | 11/01/2024 | 09/07/2024 | IMAGIN | 55 | 55 | 100 | 8
23 | ALIPURDUAR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
24 | BANKURA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
25 | BIRBHUM |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
26 | COOCHBEHAR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
27 | DAKSHIN DINAJPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
28 | DARJEELING |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
29 | HOOGHLY |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
30 | HOWRAH |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
31 | JALPAIGURI |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
32 | JHARGRAM |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
33 | KALIMPONG |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
34 | MALDAH |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
35 | MURSHIDABAD |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
36 | NADIA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
39 | PASCHIM MEDINIPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
42 | PURULIA |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
44 | UTTAR DINAJPUR |  | RCFA Division -I | Information Education Communication (IEC) activities with special emphasis on O&M, judicious & safe use of drinking water, water conservation, water quality issues and other WASH related issues under Jal Jeevan Mission (JJM) Support Activities | SM/17678 | Support-IEC | Acceptance cum work order for Execution of community sensitization/ mobilization activities using various mediums on acceptance of tap water, provision on legal provision damege or illigal connection of PWSS, safe handling & storage of safe water quality issues and wash related issues as per operational guideline of JJM in 8 Blocks consisting 62 GPs at Paschim Bardhaman district under RCFA Div-I, PHE Dte, Govt of WB |  |  | ORD/000445/2025-2026 | 1979/RCD-I | 10/07/2025 | 10/01/2026 | DEBNATH BROTHERS | 74.52 | 0 | 0 | 0
Total | [13 empty] | 2849.28 | 1209.92 | 42.46