## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 100.76 | 100 | 50
2 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 100.76 | 100 | 50
3 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 100.76 | 100 | 50
4 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 100.76 | 100 | 50
5 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 73.57 | 100 | 99
6 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 73.57 | 100 | 99
7 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 73.57 | 100 | 99
8 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 73.57 | 100 | 99
9 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 94.36 | 92.37 | 50
10 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 94.36 | 92.37 | 50
11 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 94.36 | 92.37 | 50
12 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 94.36 | 92.37 | 50
13 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 41.49 | 92.37 | 50
14 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 41.49 | 92.37 | 50
15 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 41.49 | 92.37 | 50
16 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 41.49 | 92.37 | 50
17 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
18 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
19 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
20 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
21 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | (Continuation) Engagement of Implementation Support Agency(ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong Districts Under Jal Jeevan Mission (JJM) Support Activities. For the period of 01/01/2025 to 31/03/2025. | Assistant Engineer II | Junior Engineer I | ORD/000220/2024-2025 | 2413/NKWSMD | 31/12/2024 | 31/03/2025 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE AND MONITORING ADVANCEMENT FOUNDATION | 38.5 | 0 | 0 | 100
22 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | (Continuation) Engagement of Implementation Support Agency(ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong Districts Under Jal Jeevan Mission (JJM) Support Activities. For the period of 01/01/2025 to 31/03/2025. | Assistant Engineer II | Junior Engineer I | ORD/000220/2024-2025 | 2413/NKWSMD | 31/12/2024 | 31/03/2025 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE AND MONITORING ADVANCEMENT FOUNDATION | 38.5 | 0 | 0 | 100
23 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | (Continuation) Engagement of Implementation Support Agency(ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong Districts Under Jal Jeevan Mission (JJM) Support Activities. For the period of 01/01/2025 to 31/03/2025. | Assistant Engineer II | Junior Engineer I | ORD/000220/2024-2025 | 2413/NKWSMD | 31/12/2024 | 31/03/2025 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE AND MONITORING ADVANCEMENT FOUNDATION | 38.5 | 0 | 0 | 100
24 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | (Continuation) Engagement of Implementation Support Agency(ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong Districts Under Jal Jeevan Mission (JJM) Support Activities. For the period of 01/01/2025 to 31/03/2025. | Assistant Engineer II | Junior Engineer I | ORD/000220/2024-2025 | 2413/NKWSMD | 31/12/2024 | 31/03/2025 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE AND MONITORING ADVANCEMENT FOUNDATION | 38.5 | 0 | 0 | 100
Total | [13 empty] | 1769.87 | 1240.73 | 70.1