## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 0 | 0 | 50
2 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 0 | 0 | 50
3 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 0 | 0 | 50
4 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. | Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 2698/RS | 30/08/2023 | 28/02/2024 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 100.76 | 0 | 0 | 50
5 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 0 | 0 | 99
6 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 0 | 0 | 99
7 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 0 | 0 | 99
8 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Alipurduar District. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 2762/RS | 07/09/2023 | 07/03/2024 | KHAGRABARI RURAL ENERGY DEVELOPMENT ASSOCIATION | 73.57 | 0 | 0 | 99
9 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 0 | 0 | 50
10 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 0 | 0 | 50
11 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 0 | 0 | 50
12 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 3114/RS | 10/10/2023 | 07/04/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 102.15 | 0 | 0 | 50
13 | ALIPURDUAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 0 | 0 | 50
14 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 0 | 0 | 50
15 | DARJEELING |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 0 | 0 | 50
16 | JALPAIGURI |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 3288/RS | 31/10/2023 | 30/04/2024 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 44.92 | 0 | 0 | 50
Total | [13 empty] | 1285.6 | 0 | 0