## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
2 | COOCHBEHAR |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
4 | JALPAIGURI |  | Neorakhola W/S & Mtc.Div. | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Siliguri MP, Coochbehar, Jalpaiguri , Darjeeling (Hill) and Alipurduar districts Under Jal Jeevan Mission (JJM) Support Ac | SM/18997 |  | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization & capacity building activities at Darjeeling (Hill) & Kalimpong districts Under Jal Jeevan Mission (JJM) Support Activities. (from 01.04.2025 to 30.09.2025). | Assistant Engineer II | Junior Engineer I | ORD/000224/2024-2025 | 424/NKWSMD | 28/03/2025 | 28/09/2025 | LIMRA SOCIAL WELFARE SOCIETY | 82.57 | 0 | 0 | 40
Total | [13 empty] | 330.28 | 0 | 0