## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
2 | BANKURA |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
3 | BIRBHUM |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
4 | COOCHBEHAR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
5 | DAKSHIN DINAJPUR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
6 | DARJEELING |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
7 | HOOGHLY |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
8 | HOWRAH |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
9 | JALPAIGURI |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
10 | JHARGRAM |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
11 | KALIMPONG |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
12 | MALDAH |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
13 | MURSHIDABAD |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
14 | NADIA |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
15 | NORTH 24 PARGANAS |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
16 | PASCHIM BARDHAMAN |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
17 | PASCHIM MEDINIPUR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
18 | PURBA BARDHAMAN |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
19 | PURBA MEDINIPUR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
20 | PURULIA |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
21 | SOUTH 24 PARGANAS |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
22 | UTTAR DINAJPUR |  | Resource | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Department and Designing & Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vect | SM/19003 | Support-MIS | Updation of the Settlement Layers for the entire State along with hosting in WebGIS of PHED Departmentand Designing &Layout preparation of Maps related to Water Supply coverage at District/ Block level, Preparation of Thematic Maps in both Raster & Vector formats | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3714/RS | 11/12/2023 | 08/06/2025 | HORIZEN | 84 | 0 | 0 | 23
Total | [13 empty] | 1847.96 | 0 | 0