## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
2 | BANKURA |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
3 | BIRBHUM |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
4 | COOCHBEHAR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
5 | DAKSHIN DINAJPUR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
6 | DARJEELING |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
7 | HOOGHLY |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
8 | HOWRAH |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
9 | JALPAIGURI |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
10 | JHARGRAM |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
11 | KALIMPONG |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
12 | MALDAH |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
13 | MURSHIDABAD |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
14 | NADIA |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
15 | NORTH 24 PARGANAS |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
16 | PASCHIM BARDHAMAN |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
17 | PASCHIM MEDINIPUR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
18 | PURBA BARDHAMAN |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
19 | PURBA MEDINIPUR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
20 | PURULIA |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
21 | SOUTH 24 PARGANAS |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
22 | UTTAR DINAJPUR |  | Resource | UPDATION OF SCHEME LEVEL MAPS REPRESENTING DIFFERENT FEATURES OF PIPED WATER SUPPLY SCHEMES AND FHTCS IN GIS ENVIRONMENT AND UPLODING THE SAME IN THE PHED WEB MODULE | SM/19007 | Support-MIS | Updation of Scheme Level maps representing different features of Piped Water Supply Schemes and FHTCs in GIS environment and uploading the same in the PHED Web Module | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 3697/RS | 11/12/2023 | 10/12/2024 | HORIZEN | 67.03 | 64 | 95.49 | 49
Total | [13 empty] | 1474.65 | 1408.1 | 95.49