## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
2 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
3 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
4 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
5 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
6 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
7 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
8 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
9 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
10 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
11 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
12 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
13 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
14 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
15 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
16 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
17 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
18 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
19 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
20 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
21 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
22 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 5.7 | 8.04 | 47
23 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
24 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
25 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
26 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
27 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
28 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
29 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
30 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
31 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
32 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
33 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
34 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
35 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
36 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
37 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
38 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
39 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
40 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
41 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
42 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
43 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
44 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
45 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
46 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
47 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
48 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
49 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
50 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
51 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
52 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
53 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
54 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
55 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
56 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
57 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
58 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
59 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
60 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
61 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
62 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
63 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
64 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
65 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
66 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Implementation of a Comprehensive Error-Checking and Data Validation Framework for Functionality Assessment through Jal Mitra Application of Public Health Engineering Department, Govt. of West Bengal, under Jal Jeevan Mission (JJM). | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 2032/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 67.63 | 0 | 0 | 17
67 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
68 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
69 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
70 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
71 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
72 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
73 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
74 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
75 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
76 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
77 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
78 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
79 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
80 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
81 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
82 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
83 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
84 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
85 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
86 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
87 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
88 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 302/RS | 06/02/2025 | 07/04/2025 | HORIZEN | 12.4 | 0 | 0 | 75
89 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
90 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
91 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
92 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
93 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
94 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
95 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
96 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
97 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
98 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
99 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
100 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
101 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
102 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
103 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
104 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
105 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
106 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
107 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
108 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
109 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
110 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design and Development of mobile and web application for generation of Unique Tap Water Identity (UTWID) number for the beneficiaries having FHTC connection in rural West Bengal for managing, monitoring, and sustaining water supply services in the post implementation phase of JJM. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1277/RS | 16/06/2025 | 14/09/2025 | HORIZEN | 25.7 | 0 | 0 | 99
Total | [13 empty] | 5053.2 | 125.4 | 2.48