## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
2 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
3 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
4 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
5 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
6 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
7 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
8 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
9 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
10 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
11 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
12 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
13 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
14 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
15 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
16 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
17 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
18 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
19 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
20 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
21 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
22 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000277/2023-2024 | 448/RS | 12/02/2024 | 10/08/2025 | HORIZEN | 70.91 | 0 | 0 | 47
23 | ALIPURDUAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
24 | BANKURA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
25 | BIRBHUM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
26 | COOCHBEHAR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
27 | DAKSHIN DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
28 | DARJEELING |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
29 | HOOGHLY |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
30 | HOWRAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
31 | JALPAIGURI |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
32 | JHARGRAM |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
33 | KALIMPONG |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
34 | MALDAH |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
35 | MURSHIDABAD |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
36 | NADIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
37 | NORTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
38 | PASCHIM BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
39 | PASCHIM MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
40 | PURBA BARDHAMAN |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
41 | PURBA MEDINIPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
42 | PURULIA |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
43 | SOUTH 24 PARGANAS |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
44 | UTTAR DINAJPUR |  | Resource | DESIGN, DEVOLOPMENT AND MAINTENANCE OF A MONITORING SYSTEM FOR THE ACTIVITIES EXECUTED BY THE IMPLEMENTATION SUPPORT AGENCIES (ISA) FOR ESTABLISHING A DECISION SUPPORT SYSTEM | SM/19008 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 3012/RS | 03/12/2024 | 02/05/2025 | HORIZEN | 53.05 | 0 | 0 | 35
Total | [13 empty] | 2726.94 | 0 | 0