## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
2 | BANKURA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
3 | BIRBHUM |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
4 | COOCHBEHAR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
5 | DAKSHIN DINAJPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
6 | DARJEELING |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
7 | HOOGHLY |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
8 | HOWRAH |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
9 | JALPAIGURI |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
10 | JHARGRAM |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
11 | KALIMPONG |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
12 | MALDAH |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
13 | MURSHIDABAD |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
14 | NADIA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
15 | NORTH 24 PARGANAS |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
16 | PASCHIM BARDHAMAN |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
17 | PASCHIM MEDINIPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
18 | PURBA BARDHAMAN |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
19 | PURBA MEDINIPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
20 | PURULIA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
21 | SOUTH 24 PARGANAS |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
22 | UTTAR DINAJPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | Supply& delivery of 300 numbers android based rugged hand-held devices compatible with existing Water Quality Application linked with Water Quality Dashboard for capturing & managing water quality results onsite as per direction of EIC under Public Health Engineering Department, Government of West Bengal | Assistant Engineer | Junior Engineer | ORD/000261/2023-2024 | 62/RS | 08/01/2024 | 07/04/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 40.84 | 0 | 0 | 99
23 | ALIPURDUAR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
24 | BANKURA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
25 | BIRBHUM |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
26 | COOCHBEHAR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
27 | DAKSHIN DINAJPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
28 | DARJEELING |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
29 | HOOGHLY |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
30 | HOWRAH |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
31 | JALPAIGURI |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
32 | JHARGRAM |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
33 | KALIMPONG |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
34 | MALDAH |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
35 | MURSHIDABAD |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
36 | NADIA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
37 | NORTH 24 PARGANAS |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
38 | PASCHIM BARDHAMAN |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
39 | PASCHIM MEDINIPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
40 | PURBA BARDHAMAN |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
41 | PURBA MEDINIPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
42 | PURULIA |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
43 | SOUTH 24 PARGANAS |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
44 | UTTAR DINAJPUR |  | Resource | Up-gradation of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance activity under Jal Jeevan Mission | SM/19058 | Support-WQMSP | supply and installation of new instruments required for different water testing laboratories situated across the State related to Water quality monitoring and surveillance activities under Public Health Engineering Department, Government of West Bengal. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 284/RS | 25/01/2024 | 24/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 168.2 | 0 | 0 | 55
Total | [13 empty] | 4598.84 | 0 | 0