## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
2 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
3 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
4 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
5 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
6 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
7 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
8 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
9 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
10 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
11 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
12 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
13 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
14 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
15 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
16 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
17 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
18 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
19 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
20 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
21 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
22 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
23 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
24 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
25 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
26 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
27 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
28 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
29 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
30 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
31 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
32 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
33 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
34 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
35 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
36 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
37 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
38 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
39 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
40 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
41 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
42 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
43 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
44 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
45 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
46 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
47 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
48 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
49 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
50 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
51 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
52 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
53 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
54 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
55 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
56 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
57 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
58 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
59 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
60 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
61 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
62 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
63 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
64 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
65 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
66 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
67 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
68 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
69 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
70 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
71 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
72 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
73 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
74 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
75 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
76 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
77 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
78 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
79 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
80 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
81 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
82 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
83 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
84 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
85 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
86 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
87 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
88 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
89 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
90 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
91 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
92 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
93 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
94 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
95 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
96 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
97 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
98 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
99 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
100 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
101 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
102 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
103 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
104 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
105 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
106 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
107 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
108 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
109 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
110 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
111 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
112 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
113 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
114 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
115 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
116 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
117 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
118 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
119 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
120 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
121 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
122 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
123 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
124 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
125 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
126 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
127 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
128 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
129 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
130 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
131 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
132 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
133 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
134 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
135 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
136 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
137 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
138 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
139 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
140 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
141 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
142 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
143 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
144 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
145 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
146 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
147 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
148 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
149 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
150 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
151 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
152 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
153 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
154 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
Total | [13 empty] | 12675.32 | 7531.18 | 59.42