## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
2 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
3 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
4 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
5 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
6 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
7 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
8 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
9 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
10 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
11 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
12 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
13 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
14 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
15 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
16 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
17 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
18 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
19 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
20 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
21 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
22 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for maintenance of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 63/RS | 08/01/2024 | 07/01/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 126.17 | 119.29 | 94.54 | 38
23 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
24 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
25 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
26 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
27 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
28 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
29 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
30 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
31 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
32 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
33 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
34 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
35 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
36 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
37 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
38 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
39 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
40 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
41 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
42 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
43 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
44 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1666/RS | 18/06/2024 | 18/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 21.65 | 16.18 | 74.74 | 74
45 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
46 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
47 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
48 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
49 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
50 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
51 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
52 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
53 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
54 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
55 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
56 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
57 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
58 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
59 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
60 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
61 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
62 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
63 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
64 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
65 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
66 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 253/RS | 17/01/2023 | 17/01/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 30.7 | 68.68 | 69
67 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
68 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
69 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
70 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
71 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
72 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
73 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
74 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
75 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
76 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
77 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
78 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
79 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
80 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
81 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
82 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
83 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
84 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
85 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
86 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
87 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
88 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Supply of spare parts for regular upkeep of Instruments and equipment for different Water testing laboratories related to Water Quality Monitoring & Surveillance Programme under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 2336/RS | 02/09/2024 | 22/09/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.81 | 3.81 | 100 | 99
89 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
90 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
91 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
92 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
93 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
94 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
95 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
96 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
97 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
98 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
99 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
100 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
101 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
102 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
103 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
104 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
105 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
106 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
107 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
108 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
109 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
110 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Regular upkeep of Double beam Atomic Absorption Spectrophotometer along with ultrapure water generator & uninterrupted online power back-up system present in different water testing laboratories throughout the State related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 662/RS | 27/02/2024 | 26/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 44.7 | 0 | 0 | 99
111 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
112 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
113 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
114 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
115 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
116 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
117 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
118 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
119 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
120 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
121 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
122 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
123 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
124 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
125 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
126 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
127 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
128 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
129 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
130 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
131 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
132 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Upkeep & refilling of laboratory safety equipment installed in 217 Water Testing Laboratories throughout the State under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 2108/RS | 08/08/2024 | 04/02/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 11.97 | 11.86 | 99.08 | 99
133 | ALIPURDUAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
134 | BANKURA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
135 | BIRBHUM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
136 | COOCHBEHAR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
137 | DAKSHIN DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
138 | DARJEELING |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
139 | HOOGHLY |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
140 | HOWRAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
141 | JALPAIGURI |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
142 | JHARGRAM |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
143 | KALIMPONG |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
144 | MALDAH |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
145 | MURSHIDABAD |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
146 | NADIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
147 | NORTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
148 | PASCHIM BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
149 | PASCHIM MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
150 | PURBA BARDHAMAN |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
151 | PURBA MEDINIPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
152 | PURULIA |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
153 | SOUTH 24 PARGANAS |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
154 | UTTAR DINAJPUR |  | Resource | Annual Service Contract of Laboratory Instruments, Onsite Mobile Analysis System (OMAS) & Fire Extinguisher related to Water Quality Monitoring & Surveillance Activity under Jal Jeevan Mission | SM/19059 | Support-WQMSP | Name of Work: Regular upkeep of laboratory Instruments & Equipment installed in 217 water testing laboratories throughout the State under PHE Department, Govt. of West Bengal | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2209/RS | 20/08/2024 | 20/08/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 323.16 | 160.49 | 49.66 | 25
Total | [13 empty] | 12675.32 | 7531.18 | 59.42