## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
2 | BANKURA |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
3 | BIRBHUM |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
4 | COOCHBEHAR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
5 | DAKSHIN DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
6 | DARJEELING |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
7 | HOOGHLY |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
8 | HOWRAH |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
9 | JALPAIGURI |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
10 | JHARGRAM |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
11 | KALIMPONG |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
12 | MALDAH |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
13 | MURSHIDABAD |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
14 | NADIA |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
15 | NORTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
16 | PASCHIM BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
17 | PASCHIM MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
18 | PURBA BARDHAMAN |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
19 | PURBA MEDINIPUR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
20 | PURULIA |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
21 | SOUTH 24 PARGANAS |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
22 | UTTAR DINAJPUR |  | Resource | Water Quality Monitoring, Programme Management & its Implementation in the State related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission | SM/19060 | Support-WQMSP | Operation, Maintenance, Upgradation and management of FTK mobile Application (Android Version) and Web Interface of Water Quality Data Integrated to State Water Quality Dashboard, Generating Results, Reports, Graph and Summary, Maintaining database on a regular basis in the State of West Bengal under Public Health Engineering Department | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 2224/RS | 11/07/2023 | 10/07/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 42.51 | 0 | 0 | 33
Total | [13 empty] | 935.16 | 0 | 0